Middlemount – PRCP Schedule
(RA1) Rehabilitation Area 1
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA1

	Relevant activities
	Waste Rock Emplacement (slope <16%)

	Total rehabilitation area size (ha)
	752764

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (RE 11.5.3) (with non-native grasses)

	Date area is available
	10/12/2023
	10/12/2024
	10/12/2028
	10/12/2032
	10/12/2035
	10/12/2038
	10/12/2041

	Cumulative area available (ha)
	79101	Comment by RS: More rehab completed than initially scheduled
	247
	381387
	583589
	752764
	752764
	752764

	Milestone complete by
	10/12/2024
	10/12/2028
	10/12/2032
	10/12/2035
	10/12/2038
	10/12/2041
	10/12/2044

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	79101
	247
	381387
	583589
	752764
	
	

	RM2
	79101
	247
	381387
	583589
	752764
	
	

	RM3
	79101
	247
	381387
	583589
	752764
	
	

	RM4
	79101
	247
	381387
	583589
	752764
	
	

	RM5
	79101
	247
	381387
	583589
	752764
	
	

	RM6
	
	79101
	247
	381387
	538589
	752764
	

	RM7
	
	
	79101
	247
	381387
	538589
	752764




(RA2) Rehabilitation Area 2	Comment by RS: No Change
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA2

	Relevant activities
	Waste Rock Emplacement – Existing Rehabilitation (slopes ≤33⁰)

	Total rehabilitation area size (ha)
	52

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (RE11.5.3) (with non-native grasses)

	Date area is available
	10/12/2023
	10/12/2024
	10/12/2037
	10/12/2044

	Cumulative area available (ha)
	28
	52
	52
	52

	Milestone complete by
	10/12/2024
	10/12/2037
	10/12/2044
	10/12/2049

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	28
	52
	
	

	RM2
	28
	52
	
	

	RM3
	28
	52
	
	

	RM4
	28
	52
	
	

	RM5
	28
	52
	
	

	RM6
	
	28
	52
	

	RM7
	
	
	28
	52




(RA3) Rehabilitation Area 3
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA3

	Relevant activities
	Waste Rock Emplacement (Flat/Undulating)

	Total rehabilitation area size (ha)
	12091205	Comment by RS: Reflects the reduction in total disturbance footprint for this RA

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (RE11.5.3)

	Date area is available
	10/12/2023
	10/12/2025
	10/12/2032
	10/12/2036
	10/12/2040
	10/12/2043

	Cumulative area available (ha)
	20978
	740736
	1050
	12091205
	12091205
	12091205

	Milestone complete by
	10/12/2025
	10/12/2032
	10/12/2036
	10/12/2040
	10/12/2043
	10/12/2046

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	20978
	740736
	1050
	12091205
	
	

	RM2
	20978
	740736
	1050
	12091205
	
	

	RM3
	20978
	740736
	1050
	12091205
	
	

	RM4
	20978
	740736
	1050
	12091205
	
	

	RM5
	20978
	740736
	1050
	12091205
	
	

	RM6
	
	20978
	740736
	1050
	12091205
	

	RM7
	
	
	20978
	740736
	1050
	12091205





(RA4) Rehabilitation Area 4	Comment by RS: No Change
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA4

	Relevant activities
	Tailings Storage Facility

	Total rehabilitation area size (ha)
	23

	Commencement of first milestone:
RM1
	10/12/2044

	PMLU
	Native Ecosystem (RE11.7.2)

	Date area is available
	10/12/2044
	10/12/2046
	10/12/2049

	Cumulative area available (ha)
	23
	23
	23

	Milestone complete by
	10/12/2046
	10/12/2049
	10/12/2052

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	23
	
	

	RM2
	23
	
	

	RM3
	23
	
	

	RM4
	23
	
	

	RM5
	23
	
	

	RM6
	
	23
	

	RM7
	
	
	23




(RA5) Rehabilitation Area 5
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA5

	Relevant activities
	Infrastructure Area

	Total rehabilitation area size (ha)
	382394

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (RE11.5.9)

	Date area is available
	10/12/2023
	10/12/2026
	10/12/2030
	10/12/2044
	10/12/2049
	10/12/2053

	Cumulative area available (ha)
	3216
	32
	32
	382394
	382394
	382394

	Milestone complete by
	10/12/2026
	10/12/2030
	10/12/2034
	10/12/2049
	10/12/2053
	10/12/2057

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	3216
	 32
	32 
	382394
	
	

	RM2
	3216
	32
	32
	382394
	
	

	RM3
	3216
	32
	32
	382394
	
	

	RM4
	3216
	32
	32
	382394
	
	

	RM5
	3216
	32
	32
	382394
	
	

	RM6
	 	Comment by RS: Reflects delay to  SEP EPBC approval
	3216
	32
	
	382394
	

	RM7
	
	
	3216
	32
	
	382394




(RA6) Rehabilitation Area 6	Comment by RS: No Change
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA6

	Relevant activities
	Water Management Infrastructure (Mine Water Dams)

	Total rehabilitation area size (ha)
	57

	Commencement of first milestone:
RM1
	10/12/2044

	PMLU
	Native Ecosystem 11.3.27 (Retained Water Management Infrastructure)

	Date area is available
	10/12/2044
	10/12/2049

	Cumulative area available (ha)
	57
	57

	Milestone complete by
	10/12/2048
	10/12/2053

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	57
	

	RM2
	57
	

	RM3
	57
	

	RM8
	
	57




(RA7) Rehabilitation Area 7	Comment by RS: No Change
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA7

	Relevant activities
	Water Management Infrastructure (Sediment Dams)

	Total rehabilitation area size (ha)
	23

	Commencement of first milestone:
RM1
	10/12/2044

	PMLU
	Native Ecosystem 11.3.27 (Retained Water Management Infrastructure)

	Date area is available
	10/12/2044
	10/12/2049

	Cumulative area available (ha)
	23
	23

	Milestone complete by
	10/12/2049
	10/12/2053

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	23
	

	RM2
	23
	

	RM3
	23
	

	RM8
	
	23




(RA8) Rehabilitation Area 8
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA8

	Relevant activities
	Water Diversions

	Total rehabilitation area size (ha)
	58

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Naïve Ecosystem (RE11.3.25) (with non-native grasses)

	Date area is available
	10/12/2023
	10/12/2024
	10/12/2032
	10/12/2036
	10/12/
	10/12/2053

	Cumulative area available (ha)
	1615
	3215
	5031
	58
	58
	58

	Milestone complete by
	10/12/2024
	10/12/2028
	10/12/2032
	10/12/2036
	10/12/2039
	10/12/2043

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	1615
	3215
	5031
	58
	
	

	RM2
	1615
	3215
	5031
	58
	
	

	RM3
	1615
	3215
	5031
	58
	
	

	RM4
	1615
	3215
	5031
	58
	
	

	RM5
	1615
	3215
	5031
	58
	
	

	RM6	Comment by RS: Corrected mapping/rounding error
	 
	1615
	3215
	5031
	58
	

	RM7
	
	 	Comment by RS: Update to reflect delay in Roper Creek 2 Diversion, or delete column
	1615	Comment by RS: Assumes Roper Creek 2 Diversion is built ~2027/28
	3231
	5031
	58





(RA9) Rehabilitation Area 9
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA9

	Relevant activities
	Waste Rock Emplacement – Existing Rehabilitation (slop <16%)

	Total rehabilitation area size (ha)
	7872	Comment by RS: Mapping corrected to show actual area of existing rehab at date of PRCP approval

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (RE11.5.3) (with non-native grasses)

	Date area is available
	10/12/2023
	10/12/2024
	10/12/2028

	Cumulative area available (ha)
	7872
	7872
	7872

	Milestone complete by
	10/12/2024
	10/12/2028
	10/12/2032

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	7872
	
	

	RM2
	7872
	
	

	RM3
	7872
	
	

	RM4
	7872
	
	

	RM5
	7872
	
	

	RM6
	
	7872
	

	RM7
	
	
	7872




(RA10) Rehabilitation Area 10
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA10

	Relevant activities
	Waste Rock Emplacement – Existing Rehabilitation (Flat/Undulating)

	Total rehabilitation area size (ha)
	151116	Comment by RS: Mapping corrected to show actual area of existing rehab as at time of PRCP approval

	Commencement of first milestone:
RM1
	10/12/2023

	PMLU
	Native Ecosystem (11.5.3) (with non-native grasses)

	Date area is available
	10/12/2023
	10/12/2024
	10/12/2028

	Cumulative area available (ha)
	151116
	151116
	151116

	Milestone complete by
	10/12/2024
	10/12/2028
	2032

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	151116
	
	

	RM2
	151116
	
	

	RM3
	151116
	
	

	RM4
	151116
	
	

	RM5
	151116
	
	

	RM6
	
	151116
	

	RM7
	
	
	151116
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