(RA1) Rehabilitation Area 1

| Post-mining land uses (PMLU) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA1 |  |  |  |  |  |
| Relevant activities |  | Waste Rock Emplacement (slope <16%) |  |  |  |  |  |
| Total rehabilitation area size (ha) |  | 764 |  |  |  |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |  |  |  |
| PMLU |  | Native Ecosystem (RE 11.5.3) (with non-native grasses) |  |  |  |  |  |
| Date area is available | 10/12/2023 | 10/12/2024 | 10/12/2028 | 10/12/2032 | 10/12/2035 | 10/12/2038 | 10/12/2041 |
| Cumulative area available (ha) | 101 | 247 | 387 | 589 | 764 | 764 | 764 |
| Milestone complete by | 10/12/2024 | 10/12/2028 | 10/12/2032 | 10/12/2035 | 10/12/2038 | 10/12/2041 | 10/12/2044 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |
| RM1 | 101 | 247 | 387 | 589 | 764 |  |  |
| RM2 | 101 | 247 | 387 | 589 | 764 |  |  |
| RM3 | 101 | 247 | 387 | 589 | 764 |  |  |
| RM4 | 101 | 247 | 387 | 589 | 764 |  |  |
| RM5 | 101 | 247 | 387 | 589 | 764 |  |  |
| RM6 |  | 101 | 247 | 387 | 589 | 764 |  |
| RM7 |  |  | 101 | 247 | 387 | 589 | 764 |

(RA2) Rehabilitation Area 2

| Post-mining land uses (PMLU) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA2 |  |  |  |
| Relevant activities |  | Waste Rock Emplacement – Existing Rehabilitation (slopes ≤33⁰) |  |  |  |
| Total rehabilitation area size (ha) |  | 52 |  |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |  |
| PMLU |  | Native Ecosystem (RE11.5.3) (with non-native grasses) |  |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2024 | 10/12/2037 | 10/12/2044 |
| Cumulative area available (ha) | 28 |  | 52 | 52 | 52 |
| Milestone complete by | 10/12/2024 |  | 10/12/2037 | 10/12/2044 | 10/12/2049 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |
| RM1 | 28 |  | 52 |  |  |
| RM2 | 28 |  | 52 |  |  |
| RM3 | 28 |  | 52 |  |  |
| RM4 | 28 |  | 52 |  |  |
| RM5 | 28 |  | 52 |  |  |
| RM6 |  |  | 28 | 52 |  |
| RM7 |  |  |  | 28 | 52 |

(RA3) Rehabilitation Area 3

| Post-mining land uses (PMLU) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA3 |  |  |  |  |  |
| Relevant activities |  | Waste Rock Emplacement (Flat/Undulating) |  |  |  |  |  |
| Total rehabilitation area size (ha) |  | 1205 |  |  |  |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |  |  |  |
| PMLU |  | Native Ecosystem (RE11.5.3) |  |  |  |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2025 | 10/12/2032 | 10/12/2036 | 10/12/2040 | 10/12/2043 |
| Cumulative area available (ha) | 78 |  | 736 | 1050 | 1205 | 1205 | 1205 |
| Milestone complete by | 10/12/2025 |  | 10/12/2032 | 10/12/2036 | 10/12/2040 | 10/12/2043 | 10/12/2046 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |
| RM1 | 78 |  | 736 | 1050 | 1205 |  |  |
| RM2 | 78 |  | 736 | 1050 | 1205 |  |  |
| RM3 | 78 |  | 736 | 1050 | 1205 |  |  |
| RM4 | 78 |  | 736 | 1050 | 1205 |  |  |
| RM5 | 78 |  | 736 | 1050 | 1205 |  |  |
| RM6 |  |  | 78 | 736 | 1050 | 1205 |  |
| RM7 |  |  |  | 78 | 736 | 1050 | 1205 |

(RA4) Rehabilitation Area 4

| Post-mining land uses (PMLU) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA4 |  |  |
| Relevant activities |  | Tailings Storage Facility |  |  |
| Total rehabilitation area size (ha) |  | 23 |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2044 |  |  |
| PMLU |  | Native Ecosystem (RE11.7.2) |  |  |
| Date area is available | 10/12/2044 |  | 10/12/2046 | 10/12/2049 |
| Cumulative area available (ha) | 23 |  | 23 | 23 |
| Milestone complete by | 10/12/2046 |  | 10/12/2049 | 10/12/2052 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |
| RM1 | 23 |  |  |  |
| RM2 | 23 |  |  |  |
| RM3 | 23 |  |  |  |
| RM4 | 23 |  |  |  |
| RM5 | 23 |  |  |  |
| RM6 |  |  | 23 |  |
| RM7 |  |  |  | 23 |

(RA5) Rehabilitation Area 5

| Post-mining land uses (PMLU) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA5 |  |  |  |  |  |
| Relevant activities |  | Infrastructure Area |  |  |  |  |  |
| Total rehabilitation area size (ha) |  | 394 |  |  |  |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |  |  |  |
| PMLU |  | Native Ecosystem (RE11.5.9) |  |  |  |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2026 | 10/12/2030 | 10/12/2044 | 10/12/2049 | 10/12/2053 |
| Cumulative area available (ha) | 16 |  | 32 | 32 | 394 | 394 | 394 |
| Milestone complete by | 10/12/2026 |  | 10/12/2030 | 10/12/2034 | 10/12/2049 | 10/12/2053 | 10/12/2057 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |
| RM1 | 16 |  | 32 | 32 | 394 |  |  |
| RM2 | 16 |  | 32 | 32 | 394 |  |  |
| RM3 | 16 |  | 32 | 32 | 394 |  |  |
| RM4 | 16 |  | 32 | 32 | 394 |  |  |
| RM5 | 16 |  | 32 | 32 | 394 |  |  |
| RM6 |  |  | 16 | 32 |  | 394 |  |
| RM7 |  |  |  | 16 | 32 |  | 394 |

(RA6) Rehabilitation Area 6

| Post-mining land uses (PMLU) |  |  |  |
| --- | --- | --- | --- |
| Rehabilitation area |  | RA6 |  |
| Relevant activities |  | Water Management Infrastructure (Mine Water Dams) |  |
| Total rehabilitation area size (ha) |  | 57 |  |
| Commencement of first milestone: RM1 |  | 10/12/2044 |  |
| PMLU |  | Native Ecosystem 11.3.27 (Retained Water Management Infrastructure) |  |
| Date area is available | 10/12/2044 |  | 10/12/2049 |
| Cumulative area available (ha) | 57 |  | 57 |
| Milestone complete by | 10/12/2048 |  | 10/12/2053 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |
| RM1 | 57 |  |  |
| RM2 | 57 |  |  |
| RM3 | 57 |  |  |
| RM8 |  |  | 57 |

(RA7) Rehabilitation Area 7

| Post-mining land uses (PMLU) |  |  |  |
| --- | --- | --- | --- |
| Rehabilitation area |  | RA7 |  |
| Relevant activities |  | Water Management Infrastructure (Sediment Dams) |  |
| Total rehabilitation area size (ha) |  | 23 |  |
| Commencement of first milestone: RM1 |  | 10/12/2044 |  |
| PMLU |  | Native Ecosystem 11.3.27 (Retained Water Management Infrastructure) |  |
| Date area is available | 10/12/2044 |  | 10/12/2049 |
| Cumulative area available (ha) | 23 |  | 23 |
| Milestone complete by | 10/12/2049 |  | 10/12/2053 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |
| RM1 | 23 |  |  |
| RM2 | 23 |  |  |
| RM3 | 23 |  |  |
| RM8 |  |  | 23 |

(RA8) Rehabilitation Area 8

| Post-mining land uses (PMLU) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA8 |  |  |  |  |  |
| Relevant activities |  | Water Diversions |  |  |  |  |  |
| Total rehabilitation area size (ha) |  | 58 |  |  |  |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |  |  |  |
| PMLU |  | Naïve Ecosystem (RE11.3.25) (with non-native grasses) |  |  |  |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2024 | 10/12/2032 | 10/12/2036 | 10/12/ | 10/12/2053 |
| Cumulative area available (ha) | 15 |  | 15 | 31 | 58 | 58 | 58 |
| Milestone complete by | 10/12/2024 |  | 10/12/2028 | 10/12/2032 | 10/12/2036 | 10/12/2039 | 10/12/2043 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |
| RM1 | 15 |  | 15 | 31 | 58 |  |  |
| RM2 | 15 |  | 15 | 31 | 58 |  |  |
| RM3 | 15 |  | 15 | 31 | 58 |  |  |
| RM4 | 15 |  | 15 | 31 | 58 |  |  |
| RM5 | 15 |  | 15 | 31 | 58 |  |  |
| RM6 |  |  | 15 | 15 | 31 | 58 |  |
| RM7 |  |  |  | 15 | 31 | 31 | 58 |

(RA9) Rehabilitation Area 9

| Post-mining land uses (PMLU) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA9 |  |  |
| Relevant activities |  | Waste Rock Emplacement – Existing Rehabilitation (slop <16%) |  |  |
| Total rehabilitation area size (ha) |  | 72 |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |
| PMLU |  | Native Ecosystem (RE11.5.3) (with non-native grasses) |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2024 | 10/12/2028 |
| Cumulative area available (ha) | 72 |  | 72 | 72 |
| Milestone complete by | 10/12/2024 |  | 10/12/2028 | 10/12/2032 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |
| RM1 | 72 |  |  |  |
| RM2 | 72 |  |  |  |
| RM3 | 72 |  |  |  |
| RM4 | 72 |  |  |  |
| RM5 | 72 |  |  |  |
| RM6 |  |  | 72 |  |
| RM7 |  |  |  | 72 |

(RA10) Rehabilitation Area 10

| Post-mining land uses (PMLU) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Rehabilitation area |  | RA10 |  |  |
| Relevant activities |  | Waste Rock Emplacement – Existing Rehabilitation (Flat/Undulating) |  |  |
| Total rehabilitation area size (ha) |  | 116 |  |  |
| Commencement of first milestone: RM1 |  | 10/12/2023 |  |  |
| PMLU |  | Native Ecosystem (11.5.3) (with non-native grasses) |  |  |
| Date area is available | 10/12/2023 |  | 10/12/2024 | 10/12/2028 |
| Cumulative area available (ha) | 116 |  | 116 | 116 |
| Milestone complete by | 10/12/2024 |  | 10/12/2028 | 2032 |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |
| RM1 | 116 |  |  |  |
| RM2 | 116 |  |  |  |
| RM3 | 116 |  |  |  |
| RM4 | 116 |  |  |  |
| RM5 | 116 |  |  |  |
| RM6 |  |  | 116 |  |
| RM7 |  |  |  | 116 |