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General Instructions
· This form or ERS/2019/5103 must be used for completing a proposed PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan). 
· See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
Rehabilitation area (RA) and improvement area (IA) table
· Each RA and IA table contains two parts (yellow and blue) for recording the time-based rehabilitation milestones. 
· A default value of one (1) RA is represented by one RA table below (RA1). 
· To record additional RAs for your project, make a copy of the RA table below and update it to the relevant RA number (.e.g., RA2).
· A default value of one (1) IA is represented by one IA table below (IA1).
· To record additional IAs for your project make a copy of the IA table below and update it to the relevant IA number (e.g., IA2).
· Delete the IA table below if there is no IA for your project.
· Add a new column or row to each table as required for your information requirements.
RA milestones and IA milestones
· Two (2) separate tables below exist for recording the "Rehabilitation area milestones" and "Improvement area milestones". 
· Delete the Improvement area milestones table if it does not apply to your project.
· Delete additional rows in either table if they do not apply to your project.
· See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.


Further Instructions when inputting Post-Mining Land Uses (PMLUs)
Headings under RA table
· Rehabilitation area - The rehabilitation area must align with the reference maps included in the rehabilitation planning part of the PRC plan and the spatial data submitted with the application. This area must have the same PMLU and same milestones applied to the whole area. 
· Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation. 
· Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares. 
· First milestone reference to commence - The milestone number for the first milestone to commence must be specified. This will often be RM1 but may be a later milestone if RM1 (or later milestones) does not apply to the RA.
· Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. 
· PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan including the proposed final site design and the spatial data submitted with the application. 
· Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas become available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan. 
· Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time. 
· Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed. All completion dates must be 10 December of the relevant year, as required in section 4.1 step 7 of the PRCP Guideline.
· Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones table with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones table
· Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be written in a manner that delivers on SMART principles and demonstrate achievement of the milestone. 
Further Instructions when inputting Non-Use Management Areas (NUMAs)
Headings under Improvement Area (IA) tables
· Improvement area - The improvement area must align with the reference maps included in the rehabilitation planning part of the PRC plan and the spatial data submitted with the application. This area must have the same NUMA and same milestones applied to the whole area. 
· Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement. 
· Total size (ha) - Total size of improvement area in hectares. 
· First milestone reference to commence - The milestone number for the first milestone to commence must be specified. This will often be MM1 but may be a later milestone if MM1 (or later milestones) does not apply to the IA, or if earlier milestones were achieved prior to the commencement of the PRCP schedule.
· Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence.
· NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan including the proposed final site design and the spatial data submitted with the application. 
· Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas become available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan. 
· Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time. 
· Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed. 
· Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones table with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones table
· Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.










Conditions
	PRCP #
	Condition

	PRCP3
	Where land becomes available for rehabilitation/improvement earlier than the nominated date in the schedule, the holder must: 
a) Notify the administering authority in writing within 30 days of the land becoming ‘available for rehabilitation’; 
b) Describe in the notification why or why not it considers that it would be reasonable and appropriate to amend this schedule; and 
c) Unless otherwise agreed to by the administering authority in writing, amend this schedule in a way that maximises the progressive rehabilitation to a stable condition within the timeframe specified by the administering authority.

Note:  
1) Reference to "earlier than the nominated date in the schedule" means a date that is greater than 5 years prior to the date nominated in the schedule. 
2) Assessment of land becoming available is undertaken on a nominally annual basis. 
3) Rehabilitation of land size must be practicable and economical. 
4) The dates by which milestones are to be completed is brought forward, to the extent it is reasonably practicable to do so, by the same amount of time as the commencement was brought forward.

	PRCP5
	The holder must make and keep records to demonstrate achievement and maintenance of achievement of each rehabilitation milestone criteria of this schedule.

	PRCP6
	The holder must make and keep records on relevant matters which document the condition of each 
rehabilitation area with respect to environmental performance, rehabilitation milestone criteria and 
compliance obligations of this schedule. 
Relevant matters for this condition include, but are not limited to, the following: 
a) Rehabilitation activities and the results of those activities;
b) Maintenance activities and the results of maintenance activities; 
c) Monitoring activities and the results of monitoring; 
d) Designs, drawings, specifications or any similar documents relating to a rehabilitation activity; and 
e) Certifications, assessments, investigations, inspections, audits or any similar processes carried out in relation to rehabilitation milestones or milestone criteria.

	PRCP7
	Summary report of key records under PRCP5 and PRCP6 is maintained until the relevant environmental authority has been surrendered or progressive rehabilitation certification is achieved.

	PRCP8
	Records made under PRCP7 must be provided to the administering authority in the specified format within 20 business days of a written request or a longer duration as agreed by the administering authority.

	PRCP11
	With respect to groundwater: 
a) The monitoring bores listed in Table 70: Groundwater monitoring locations must be installed by 2050; and
b) Following monitoring bore installation as per PRCP11a), groundwater quality must be monitored six monthly at bores specified in Table 70: Groundwater monitoring locations; and
c) The holder must develop site-specific groundwater quality limits by 2055 for the bores listed in Table 70: Groundwater monitoring locations; and
d) The groundwater model and water balance model must be recalibrated and predictions rerun at least every five years commencing from 2050.

	PRCP12
	 With respect to groundwater: 
a) Groundwater quality results for compliance bores have not exceeded the site-specific groundwater quality limits, for three (3) consecutive results within the five-year period immediately prior to surrender; and
b) Predictive groundwater modelling as per the Australian Groundwater Modelling Guidelines (current version), undertaken at the completion of all mining, confirms the network of residual voids will collectively develop into groundwater sinks and prevent environmental harm through the release of contaminants from the void lakes beyond the tenure boundaries post-closure.

	PRCP13
	With respect to surface water: 
a) The holder must install monitoring equipment at the relevant surface water monitoring locations specified in Table 69: Surface water monitoring locations by 2050;   
b) The holder must develop site-specific surface water quality limits by 2055 for the watercourses listed in Table 69: Surface water monitoring locations; 
c) Following completion of PRCP13a), surface water quality must be monitored at least once per month during flow at downstream locations specified in Table 69: Surface water monitoring locations when flows at the downstream gauging station record 1m3/second for Phillips Creek and Hughes Creek and 0.5m3/second for One Mile Creek, when safe to collect samples.

	PRCP14
	With respect to surface water: 
a) Surface water quality monitored as per PRCP13c) must not exceed the site-specific surface water quality limits, within the five (5) year period immediately prior to surrender; and  
b) If the surface water quality exceeds criteria PRCP14a), the applicable upstream site must be compared to the downstream site result; and quality result measured at a downstream site must be equal to or less than the quality result measured at the applicable upstream site.  

	PRCP15
	Where the surface water quality at the downstream site exceeds the upstream site result as per PRCP14b), an AQP must complete an assessment of the cause of the exceedance and risk of rehabilitation not achieving a stable condition within the schedule timeframe and: 
a) Where there is low risk to achieving a stable condition from the mining tenure (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021), then no further action is to be taken; or 
b) Where there is a risk greater than low to achieve a stable condition, then an assessment of potential environment harm and any changes or rectification actions to rehabilitation activities must be determined and implemented; 
c) The holder will be non-compliant with PRCP14a), if PRCP15b) is triggered more than three (3) times over five (5) consecutive years prior to surrender and PRCP14a) is reset; and   
d) The assessment/s under PRCP15 must be completed and provided to the administering authority within six (6) months of receiving the relevant sampling results.   

	PRCP21
	The holder may develop site-based criteria with which to assess tunnel erosion within 5 years of the approval of the transitional PRCP schedule (4 September 2024). Criteria should be sufficient to quantify where tunnel erosion exists within the landscape which would not pose risk to final landform stability. The criteria should be supported by evidence and reviewed and approved by an AQP.  

	PRCPX
	With respect to improvement area (IA1), the holder must develop Groundwater Level Monitoring Network (GLMN) inclusive of following steps:  
a) Identify by 2094 (or 4-years prior to the planned end of mining at SRM), relevant regional aquifers (hydrogeological units) likely to be affected/connected individually or collectively by each residual void in (IA1); 
b) Identify by 2094 (or 4-years prior to the planned end of mining at SRM), relevant existing groundwater bores (from Table 70: Groundwater monitoring locations) and new additional groundwater monitoring bores if determined by an AQP as required to ensure sufficient monitoring coverage for each regional aquifer mapped in accordance with PRCPX a);   
c) Independent AQP endorse the proposed GLMN as per PRCPX a) and PRCPX b) is fit for purpose that is, to monitor and support predictions of residual voids behaviour as a sink;  
d) For existing groundwater monitoring bores identified in accordance with PRCPX b) and approved as per PRCPX c), update the Table 70: Groundwater monitoring locations before end of 2097 (or within 3 years of completion of PRCPX b) to reflect water level (mAHD) for the relevant bores; and
e) Depending on outcomes of PRCPX b) and PRCPX c), update the Table 70: Groundwater monitoring locations before end of 2097 (or within 3 years of completion of PRCPX b) with new additional groundwater monitoring bores’ location co-ordinates, hydrogeological unit and water level (mAHD).   

	PRCPXX
	Groundwater level must be monitored annually, at the bores identified under the GLMN (PRCPX), starting from 2098 or within 1 year of the end of SRM mining, whichever is earlier. 



Definitions
	Appropriately qualified person (AQP)
	Means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods or literature.

	Groundcover
	Anything in contact with the soil surface, for example, live cover, standing dry cover, organic litter (including leaves, hay, woody debris) or rocks

	Index of Diversion Condition modified method
	For watercourse rehabilitation not within a diversion (i.e. crossings/culverts), a modified IDC method with a reduced number of monitoring points within each reach will be used
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PART 1: Post mining land uses
[bookmark: _Toc65157987](RA1) Rehabilitation area 1
	[bookmark: _Toc65157990]Post-mining land uses (PMLU)

	Rehabilitation area
	RA1

	Relevant activities
	Spoil Dumps

	Total rehabilitation area size (ha)
	6775

	Commencement of first milestone: RM2
	10/12/2023

	PMLU
	Woodland Habitat

	Date area is available
	10/12/2023
	10/12/2028
	10/12/2033
	10/12/2038
	10/12/2043
	10/12/2048
	10/12/2053
	10/12/2058
	10/12/2063
	10/12/2068

	Cumulative area available (ha)
	51
	193
	431
	582
	794
	1030
	1303
	1703
	2343
	2743

	Milestone completed by
	10/12/2028
	10/12/2033
	10/12/2038
	10/12/2043
	10/12/2048
	10/12/2053
	10/12/2058
	10/12/2063
	10/12/2068
	10/12/2073

	Milestone Reference
	Cumulative area achieved (ha)

	RM2
	51
	193
	431
	582
	794
	1030
	1303
	1703
	2343
	2743

	RM3
	
	51
	193
	431
	582
	794
	1030
	1303
	1703
	2343

	RM5
	
	51
	193
	431
	582
	794
	1030
	1303
	1703
	2343

	RM8
	
	51
	193
	431
	582
	794
	1030
	1303
	1703
	2343

	RM11
	
	
	
	51
	193
	431
	582
	794
	1030
	1303

	RM14
	
	
	
	
	
	51
	193
	431
	582
	794



	Post-mining land uses (PMLU)

	Rehabilitation area
	RA1

	Relevant activities
	Spoil Dumps

	Total rehabilitation area size (ha)
	6775

	Commencement of first milestone: RM2
	10/12/2023

	PMLU
	Woodland Habitat

	Date area is available
	10/12/2073
	10/12/2078
	10/12/2083
	10/12/2088
	10/12/2093
	10/12/2098
	
	
	
	

	Cumulative area available (ha)
	3143
	3663
	4722
	5161
	5461
	6775
	
	
	
	

	Milestone completed by
	10/12/2078
	10/12/2083
	10/12/2088
	10/12/2093
	10/12/2098
	10/12/2103
	10/12/2108
	10/12/2113
	10/12/2118
	10/12/2123

	Milestone Reference
	Cumulative area achieved (ha)

	RM2
	3143
	3663
	4722
	5161
	5461
	6775
	
	
	
	

	RM3
	2743
	3143
	3663
	4722
	5161
	5461
	6123
	6775
	
	

	RM5
	2743
	3143
	3663
	4722
	5161
	5461
	6123
	6775
	
	

	RM8
	2743
	3143
	3663
	4722
	5161
	5461
	6123
	6775
	
	

	RM11
	1703
	2343
	2743
	3143
	3663
	4722
	5161
	5461
	6123
	6775

	RM14
	1030
	1303
	1703
	2343
	2743
	3143
	3663
	4722
	5161
	5461




	Post-mining land uses (PMLU)

	Rehabilitation area
	RA1

	Relevant activities
	Spoil Dumps

	Total rehabilitation area size (ha)
	6775

	Commencement of first milestone: RM2
	10/12/2023

	PMLU
	Woodland Habitat

	Date area is available
	
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2128
	10/12/2133
	
	
	
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM2
	
	
	
	
	
	
	
	
	
	

	RM3
	
	
	
	
	
	
	
	
	
	

	RM5
	
	
	
	
	
	
	
	
	
	

	RM8
	
	
	
	
	
	
	
	
	
	

	RM11
	
	
	
	
	
	
	
	
	
	

	RM14
	6123
	6775
	
	
	
	
	
	
	
	





(RA2) Rehabilitation area 2
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA2

	Relevant activities
	Creek diversions and crossings

	Total rehabilitation area size (ha)
	211

	Commencement of first milestone: RM1
	10/12/2042

	PMLU
	Watercourse

	Date area is available
	10/12/2042
	10/12/2052
	10/12/2062
	10/12/2065
	10/12/2079
	10/12/2082
	10/12/2085
	10/12/2099
	11/12/2104
	

	Cumulative area available (ha)
	41
	89
	128
	128
	176
	176
	176
	178
	211
	

	Milestone completed by
	10/12/2045
	10/12/2055
	10/12/2065
	10/12/2075
	10/12/2082
	10/12/2085
	10/12/2092
	10/12/2102
	10/12/2107
	10/12/2112

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	41
	89
	128
	
	176
	
	
	178
	211
	

	RM3
	41
	89
	128
	
	176
	
	
	178
	211
	

	RM6
	41
	89
	128
	
	176
	
	
	178
	211
	

	RM9
	41
	89
	128
	
	176
	
	
	178
	211
	

	RM12
	
	41
	89
	128
	
	
	176
	
	
	178

	RM15
	
	
	41
	89
	
	128
	
	176
	
	



	Post-mining land uses (PMLU)

	Rehabilitation area
	RA2

	Relevant activities
	Creek diversions and crossings

	Total rehabilitation area size (ha)
	211

	Commencement of first milestone: RM1
	10/12/2042

	PMLU
	Watercourse

	Date area is available
	
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2117
	10/12/2122
	10/12/2127
	
	
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	
	
	
	
	
	
	
	
	
	

	RM3
	
	
	
	
	
	
	
	
	
	

	RM6
	
	
	
	
	
	
	
	
	
	

	RM9
	
	
	
	
	
	
	
	
	
	

	RM12
	211
	
	
	
	
	
	
	
	
	

	RM15
	
	178
	211
	
	
	
	
	
	
	





(RA3) Rehabilitation area 3
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA3

	Relevant activities
	Infrastructure Areas - MIA, workshop, dams, coal stockpiles, roads, general infrastructure

	Total rehabilitation area size (ha)
	906

	Commencement of first milestone: RM1
	10/12/2099

	PMLU
	Cattle Grazing

	Date area is available
	10/12/2099
	10/12/2104
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	693
	906
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2102
	10/12/2107
	10/12/2112
	10/12/2114
	10/12/2117
	10/12/2119
	10/12/2122
	10/12/2124
	10/12/2127
	10/12/2129

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	693
	906
	
	
	
	
	
	
	
	

	RM2
	
	
	665
	
	860
	
	888
	
	906
	

	RM3
	
	
	
	665
	
	860
	
	888
	
	906

	RM4
	
	
	
	665
	
	860
	
	888
	
	906

	RM7
	
	
	
	665
	
	860
	
	888
	
	906

	RM10
	
	
	
	
	
	
	
	665
	
	860

	RM13
	
	
	
	
	
	
	
	
	
	665



	Post-mining land uses (PMLU)

	Rehabilitation area
	RA3

	Relevant activities
	Infrastructure Areas - MIA, workshop, dams, coal stockpiles, roads, general infrastructure

	Total rehabilitation area size (ha)
	906

	Commencement of first milestone: RM1
	10/12/2099

	PMLU
	Cattle Grazing

	Date area is available
	
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2134
	10/12/2139
	10/12/2144
	
	
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	
	
	
	
	
	
	
	
	
	

	RM2
	
	
	
	
	
	
	
	
	
	

	RM3
	
	
	
	
	
	
	
	
	
	

	RM4
	
	
	
	
	
	
	
	
	
	

	RM7
	
	
	
	
	
	
	
	
	
	

	RM10
	888
	906
	
	
	
	
	
	
	
	

	RM13
	860
	888
	906
	
	
	
	
	
	
	




(RA4) Rehabilitation area 4
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA4

	Relevant activities
	Roads, creek corridor areas, exploration and general infrastructure 

	Total rehabilitation area size (ha)
	707

	Commencement of first milestone: RM1
	10/12/2026

	PMLU
	Woodland Habitat

	Date area is available
	10/12/2026
	10/12/2028
	10/12/2031
	10/12/2036
	10/12/2099
	10/12/2101
	10/12/2104
	
	
	

	Cumulative area available (ha)
	105
	105
	105
	105
	448
	448
	707
	
	
	

	Milestone completed by
	10/12/2028
	10/12/2031
	10/12/2041
	10/12/2051
	10/12/2101
	10/12/2104
	10/12/2106
	10/12/2109
	10/12/2114
	10/12/2119

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	105
	
	
	
	448
	
	707
	
	
	

	RM3
	
	105
	
	
	
	448
	
	707
	
	

	RM5
	
	105
	
	
	
	448
	
	707
	
	

	RM8
	
	105
	
	
	
	448
	
	707
	
	

	RM11
	
	
	105
	
	
	
	
	
	448
	707

	RM14
	
	
	
	105
	
	
	
	
	
	



	Post-mining land uses (PMLU)

	Rehabilitation area
	RA4

	Relevant activities
	Roads, creek corridor areas, exploration and general infrastructure 

	Total rehabilitation area size (ha)
	707

	Commencement of first milestone: RM1
	10/12/2026

	PMLU
	Woodland Habitat

	Date area is available
	
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2124
	10/12/2129
	
	
	
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	
	
	
	
	
	
	
	
	
	

	RM3
	
	
	
	
	
	
	
	
	
	

	RM5
	
	
	
	
	
	
	
	
	
	

	RM8
	
	
	
	
	
	
	
	
	
	

	RM11
	
	
	
	
	
	
	
	
	
	

	RM14
	448
	707
	
	
	
	
	
	
	
	





(RA7) Rehabilitation area 7
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA7

	Relevant activities
	Existing Rehabilitation

	Total rehabilitation area size (ha)
	161

	Commencement of first milestone: RM10
	10/12/2023

	PMLU
	Cattle Grazing

	Date area is available
	10/12/2023
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	161
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2033
	10/12/2038
	
	
	
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM10
	161
	
	
	
	
	
	
	
	
	

	RM17
	
	161
	
	
	
	
	
	
	
	







(RA9) Rehabilitation area 9
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA9

	Relevant activities
	TSF3

	Total rehabilitation area size (ha)
	41

	Commencement of first milestone: RM1
	10/12/2023

	PMLU
	Grassland

	Date area is available
	10/12/2023
	10/12/2033
	10/12/2036
	10/12/2046
	10/12/2104
	
	
	
	
	

	Cumulative area available (ha)
	24
	24
	24
	24
	41
	
	
	
	
	

	Milestone completed by
	10/12/2033
	10/12/2036
	10/12/2046
	10/12/2056
	10/12/2106
	10/12/2116
	10/12/2119
	10/12/2129
	10/12/2139
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM1
	24
	
	
	
	41
	
	
	
	
	

	RM2
	24
	
	
	
	
	41
	
	
	
	

	RM3
	
	24
	
	
	
	
	41
	
	
	

	RM4
	
	24
	
	
	
	
	41
	
	
	

	RM7
	
	24
	
	
	
	
	41
	
	
	

	RM19
	
	
	24
	
	
	
	
	41
	
	

	RM20
	
	
	
	24
	
	
	
	
	41
	



(RA10) Rehabilitation area 10
	Post-mining land uses (PMLU)

	Rehabilitation area
	RA10

	Relevant activities
	Existing Rehabilitation

	Total rehabilitation area size (ha)
	96

	Commencement of first milestone: RM8
	10/12/2023

	PMLU
	Woodland Habitat

	Date area is available
	10/12/2023
	
	
	
	
	
	
	
	
	

	Cumulative area available (ha)
	96
	
	
	
	
	
	
	
	
	

	Milestone completed by
	10/12/2023
	10/12/2025
	10/12/2033
	10/12/2035
	10/12/2038
	10/12/2043
	10/12/2045
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	RM8
	54
	96
	
	
	
	
	
	
	
	

	RM11
	49
	
	54
	96
	
	
	
	
	
	

	RM18
	
	
	
	
	49
	54
	96
	
	
	






Rehabilitation area milestones 
	Milestone reference
	Rehabilitation milestone
	Milestone criteria

	RM1
	Infrastructure decommissioning and removal
	1.1 All infrastructure to be retained onsite must be safe, stable and not cause environmental harm.
1.2 All infrastructure and services to be retained onsite must have a signed landholder statement, declaring that they will accept responsibility for the infrastructure (except for those items in 1.3).
1.3 Below-ground infrastructure, services and waste (as per the Environmental Authority (EPML00862313) waste schedule) deeper than 0.5m in relation to the final landform surface can be retained provided it can meet the following: 
a) All pipelines have been drained; and 
b) All below-ground infrastructure (installed after the approval date of the transitional PRCP (4 September 2024)) to be retained must be mapped; and 
c) The intended PMLU is not compromised. 
1.4 With the exception of 1.2 and 1.3 above, the following are complete: 
a) All services disconnected, terminated and removed
b) All buildings and associated infrastructure dismantled and removed
c) All hardstand, concrete areas and roads (bitumen, blue metal, aggregate) removed
d) All pipelines drained and removed
e) All waste, not authorised under the Environmental Authority (EPML00862313) waste schedule, removed
f) All surface water drainage infrastructure removed
g) All drillholes, bores, sediment ponds and sumps decommissioned
h) All machinery and equipment not required for rehabilitation works removed from site 
i) Mine water dams are decommissioned
j) Watercourse crossings and culverts removed.
1.5 Assessment of mine water dams to be retained post closure is completed by an AQP and identified sediment and water management actions to ensure the dams are safe and stable for post mine use are completed.

	RM2
	Remediation and/or management of contaminated land
	2.1 Contaminated Land Investigation Document completed in accordance with the Environmental Protection Act 1994, including a site investigation report, and, where required, a Validation Report and/or a draft Site Management Plan.
2.2 The Contaminated Land Investigation Document confirms the area within the mining leases (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021) does not present an unacceptable risk to the post-mining land use.
2.3 Despite 2.1 and 2.2, where contaminated land investigations are undertaken for individual areas of progressive rehabilitation that do not cover an entire Lot on Plan, the investigations will be undertaken by a Suitably Qualified Person to a standard, that at the time of investigation, would be suitable to form part of a future Environmental Protection Act 1994 compliant Contaminated Land Investigation Document for that property, and does not need to achieve all requirements for a contaminated land submission to the administering authority.

	RM3
	Landform development and reshaping
	All rehabilitation areas
3.1 Erosion and sediment control systems are designed by an AQP, installed, and fit for purpose.
3.2 Appropriate mitigative measures in place for outer landform slopes that interact with flood waters up to a 0.1% AEP, as modelled on the closure landform, and designed by an AQP to minimise potential instability of the landforms from interaction with floodwaters.
3.3 The reshaped landforms are geotechnically stable with RA1 and RA9 achieving FoS ≥1.5.

Woodland Habitat (RA1, RA4)
3.4 Landforms reshaped with:  
a) RA1: ≤30% slopes, with >15% slopes covered with minimum 0.5m rock
b) RA1: Runoff to be restricted from the top of the landform onto the batter slopes if required using appropriate measures of erosion control as advised and designed by an AQP
c) RA1: Rejects to be covered with at least 2m of competent benign spoil, unless alternative depth is justified by an AQP
d) RA4: ≤15% slopes.

Watercourses (RA2)
3.5 Disturbed natural watercourse bed and banks returned to a profile similar to the pre-disturbance condition.

Cattle Grazing (RA3)
3.6 RA3 landforms are reshaped with slopes: ≤12%.

Grassland (RA9) - Installation of cover
3.7 An AQP to determine appropriate cover which at minimum achieves the following: 
e) Tailings to be capped with at least 2m of competent benign spoil;
f) Reduces risk of upward movement of contaminants into the topsoil layer above the cover and reduce risk of environmental harm from contaminated seepage; 
g) Landforms are reshaped with slopes ≤30%;
h) >15% slopes to be covered with minimum 0.5m rock, unless an alternative is justified by an AQP; and
i) Landform surface to be free draining.
3.8 An independent AQP to endorse installation of the cover system as per 3.7.

Retained water structure 
3.9 Water storages are safe for stock access and have vegetated banks.

	RM4
	Surface preparation (cattle grazing, grassland)
	4.1 Topsoil placed at minimum depth of 150mm in areas where topsoil has previously been removed.
4.2 Assessment of growth media characteristics is completed by an AQP:
a) To target land suitability class ≤3 as per Table 24: Regional land suitability framework for beef cattle grazing PMLU rehabilitation in the Bowen Basin (Short, 2025) (RA3), and
b) For target vegetation establishment suitable for designated PMLU (RA9).
4.3 Ameliorant and physical treatments are applied as identified in criteria 4.2.
4.4 Rip at least 300mm into soil/subsoil profile along contour of slopes.

	RM5
	Surface preparation (woodland habitat)
	5.1 Topsoil placed at minimum depth of 100mm, or alternative growth media at minimum depth of 300mm, in areas where topsoil has previously been removed.
5.2 Assessment of growth media characteristics is completed by an AQP for target vegetation establishment suitable for designed PMLU.
5.3 Ameliorant and physical treatments are applied as identified in criteria 5.2.
5.4 Rip at least 300mm into soil/subsoil profile along contour of slopes.

	RM6
	Surface preparation (watercourse)
	6.1 Topsoil placed at minimum depth of 150mm in areas where topsoil has previously been removed.
6.2 Assessment of growth media characteristics is completed by an AQP for target vegetation establishment suitable for designed PMLU.
6.3 Ameliorant and physical treatments s are applied as identified in criteria 6.2.
6.4 Rip at least 300mm into soil/subsoil profile along contour of slopes.

	RM7
	Revegetation (cattle grazing, grassland)
	7.1 Completed seeding in accordance with Table 36: Recommended species list and seeding rates for cattle grazing and grassland PMLUs.
7.2 For cattle grazing PMLU, at least 4 species of 3P pasture species and two legumes from Table 36: Recommended species list and seeding rates for cattle grazing and grassland PMLUs.

	RM8
	Revegetation (woodland habitat)
	8.1 Completed seeding in accordance with Table 38: Recommended species list and seeding rates for woodland habitat PMLU
(RA1)1, or as recommended by an AQP where vegetation is targeting a specific regional ecosystem (RA4)2.
1If recommended species are not available, substitute with species from RE 11.5.3, RE 11.5.9, RE 11.10.1 or RE 11.10.3.
2Seed application may not be required in all RA4 areas.

	RM9
	Revegetation (watercourse)
	9.1 Completed seeding in accordance with Table 39: Recommended species list and seeding rates for watercourse revegetation PMLU – upper and mid banks and Table 40: Recommended species list and seeding rates for watercourse revegetation PMLU – lower banks.

	RM10
	Achievement of surface requirements (cattle grazing)
	10.1 >50% vegetation groundcover (RA7), of which ≥50% of dry matter yield is 3P pasture species as listed in Table 36: Recommended species list and seeding rates for cattle grazing and grassland PMLUs (RA3). 
10.2 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity (RA3).
10.3 With respect to erosion in rehabilitated landforms: 
a) All erosion, inclusive of tunnel erosion, as per Table 59: Erosion type and severity is assessed by an AQP and repaired if assessed as requiring intervention to ensure the stable PMLU is achieved, and evidence that it is repaired as per AQP advice; and 
b) Mass movement is absent.

	RM11
	Achievement of surface requirements (woodland habitat)
	11.1 Groundcover:
a) >15% slopes must achieve ≥80% groundcover, or
b) ≤15% slopes must achieve ≥50% groundcover. 
11.2 Vegetation meets the following:
a) BioCondition score of ≥18/60 based on the averaged benchmarks for the representative regional ecosystems as listed in Table 64: BioCondition benchmarks and scoring of site-based attributes for representative regional ecosystems and as assessed by an AQP using the modified ‘BioCondition Assessment Manual’ (version 2.2) methodology (RA1, RA4), or
b) Species richness of ≥2 native trees, ≥3 native shrubs and ≥4 ground species (exotic or native) (RA10).
11.3 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity (RA1, RA4).
11.4 With respect to erosion in rehabilitated landforms: 
a) All erosion, inclusive of tunnel erosion, as per  Table 59: Erosion type and severity is assessed by an AQP and repaired if assessed as requiring intervention to ensure the stable PMLU is achieved, and evidence that it is repaired as per AQP advice; and 
b) Mass movement is absent.

	RM12
	Achievement of surface requirements (watercourse)
	12.1 Landform slopes must achieve ≥50% groundcover. 
12.2 Geomorphic index score: greater than or equal to upstream or downstream values (Index of Diversion Condition method).
12.3 Vegetation meets the following:
a) Species richness: 
i. ≥2 native trees; 
ii. ≥2 native shrubs representative of RE 11.3.25; and
iii. ≥2 grasses (exotic or native)
12.4 With respect to erosion in rehabilitated landforms: 
a) All erosion, inclusive of tunnel erosion, as per Table 59: Erosion type and severity if assessed as requiring intervention to ensure the stable PMLU is achieved, and evidence that it is repaired as per AQP advice; and 
b) Mass movement is absent.

	RM13
	Achievement of post-mining land use to a stable condition (cattle grazing – RA3)
	13.1 Hazard assessment completed by an AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
13.2 Groundcover: >50% vegetation groundcover, with ≥50% of dry matter yield is 3P grasses as listed in Table 36: Recommended species list and seeding rates for cattle grazing and grassland PMLUs. 
13.3 Achievement of land suitability class ≤3 as per Table 24: Regional land suitability framework for beef cattle grazing PMLU rehabilitation in the Bowen Basin (Short, 2025), or ≥4 if not different from pre-mining class. 
13.4 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement is absent; and 
c) An AQP determines that any erosion present, including tunnel erosion, will not compromise the achievement of a PMLU to a stable condition.
13.5 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity.
13.6 Leucaena leucocephala plants >2m high do not exceed stem density of 250 stems per hectare (1 per 40m2) mean of total area.
13.7 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.
13.8 Final landform survey confirms no built infrastructure remains other than those that form part of landholder agreement and meets exception as per 1.3.

Retained infrastructure/ Water storage 
13.9 Infrastructure to be transitioned to a future landholder is deemed fit for purpose, safe and stable by AQP and accepted, by signed agreement with the future landholder. 
13.10 All retained dams are safe, stable for native animals and stock access and have vegetated banks. 
13.11 Water storages monitored for water quality annually must meet ANZECC 2000 stock water guideline values, for a minimum of 5 consecutive years.

	RM14
	Achievement of post-mining land use to a stable condition (woodland habitat – RA1, RA4)
	14.1 Hazard assessment completed by an AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
14.2 Rehabilitation is assessed as geotechnically stable by an AQP with FoS ≥1.5 (RA1).
14.3 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement is absent; and 
c) An AQP determines that any erosion present, including tunnel erosion, will not compromise the achievement of a PMLU to a stable condition.   
14.4 Groundcover:
a) >15% slopes must achieve ≥80% groundcover, or
b) ≤15% slopes must achieve ≥50% groundcover. 
14.5 Vegetation meets the following: BioCondition score of ≥35/60 based on the averaged benchmarks for the representative regional ecosystems as listed in Table 64: BioCondition benchmarks and scoring of site-based attributes for representative regional ecosystems and as assessed by an AQP using the modified ‘BioCondition Assessment Manual’ (version 2.2) methodology. 
14.6 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.
14.7 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity.
14.8 Final landform survey confirms no built infrastructure remains other than those that form part of landholder agreement and meets exception as per 1.3.

	RM15
	Achievement of post-mining land use to a stable condition (watercourse – RA2)
	15.1 Hazard assessment completed by an AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
15.2 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement is absent; and 
c) An AQP determines that any erosion present, including tunnel erosion will not compromise the achievement of the PMLU to a stable condition.
15.3 Geomorphic index score: greater than or equal to upstream or downstream values (Index of Diversion Condition method).
15.4 Watercourse vegetation meets the following:
a) Riparian vegetation index score: greater than or equal to upstream or downstream values (Index of Diversion Condition method)
b) Species richness: 
I. ≥2 native trees;  
II. ≥2 native shrubs;
III. ≥2 grasses (native or exotic)
c) Tree canopy cover ≥13%.
15.5 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.
15.6 Diversion has an IDC score >10 as defined in ‘Criteria for functioning river landscape units in mining and post-mining. landscapes’ (ACARP Project number C20017). 
15.7 AQP must consider the following in closure design determination for diversions being retained in the landform:
a) Incorporate natural features (including geomorphic and vegetation) present at the location of the diversion;
b) Maintain the pre-existing hydrologic characteristics of surface water for the area in which the watercourse diversion is located;
c) Maintain the hydraulic characteristics of the local watercourses without requiring on-going maintenance; 
d) Maintain sediment transport and water quality regimes that allow the diversion to be self-sustaining, while minimising any impacts to upstream and downstream water quality, geomorphology, or vegetation;
e) Maintain equilibrium and functionality in all substrate conditions at the location of the diversion; and
f) Geotechnically and erosionally stable.
15.8 Final landform survey confirms no built infrastructure remains other than those that form part of a landholder agreement and meets exception as per 1.3.

	RM17
	Achievement of post-mining land use to a stable condition (cattle grazing - existing rehabilitation – RA7)
	17.1 Hazard assessment completed by an AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
17.2 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement is absent; and 
c) An AQP determines that any erosion present, including tunnel erosion, will not compromise the achievement of the PMLU to a stable condition.
17.3 Final landform survey confirms no built infrastructure remains other than those that form part of a landholder agreement and meets exception as per 1.3.
17.4 Groundcover: >50% vegetation groundcover, of which ≥50% of dry matter yield is 3P pasture species.  
17.5 Land condition: assessed as Good (A) or Fair (B) condition using Table 62: Grazing Land Management ABCD Land Condition Framework (DES, 2022a).
17.6 Leucaena leucocephala plants >2m high do not exceed stem density of 250 stems per hectare (1 per 40m2) mean of total area.
17.7 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.

	RM18
	Achievement of post-mining land use to a stable condition (woodland habitat - existing rehabilitation –RA10)
	18.1 Hazard assessment completed by AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
18.2 Groundcover:
a) >15% slopes must achieve ≥80% groundcover, or
b) ≤15% slopes must achieve ≥50% groundcover. 
18.3 Vegetation meets the following:
a) Species richness: 
i. ≥2 native trees, 
ii. ≥3 native shrubs, and 
iii. ≥4 grasses (native or exotic)
b) Tree canopy cover ≥16%.
18.4 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.
18.5 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement is absent; and 
c) An AQP determines that any erosion present, including tunnel erosion, will not compromise the achievement of the PMLU to a stable condition.

	RM19
	Achievement of surface requirements (grassland)
	19.1 Groundcover:
a) >15% slopes: ≥80% groundcover, 
b) ≤15% slopes: ≥50% groundcover,
c) ≤5% slopes: ≥50% groundcover, consisting of at least 50% vegetation groundcover.
19.2 With respect to erosion in rehabilitated landforms:
a) All erosion as per Table 59: Erosion type and severity is assessed by an AQP and repaired if assessed as requiring intervention to ensure a stable PMLU is achieved, and evidence that it is repaired as per AQP advice; and 
b) Mass movement and tunnel erosion are absent.
19.3 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity.

	RM20
	Achievement of post-mining land use to a stable condition (grassland – RA9)
	20.1 Hazard assessment completed by an AQP to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
20.2 Rehabilitation is assessed as geotechnically stable by an AQP with FoS ≥1.5.
20.3 With respect to erosion in rehabilitated landforms: 
a) No evidence of erosion classified as moderate or severe as defined by Table 59: Erosion type and severity; and 
b) Mass movement and tunnel erosion are absent; and 
c) An AQP determines that any erosion present will not compromise the achievement of the PMLU to a stable condition.
20.4 Vegetation: ≥2 grass species (native or exotic). 
20.5 Groundcover:
a) >15% slopes: ≥80% groundcover,
b) ≤15% slopes: ≥50% groundcover, 
c) ≤5% slopes: ≥50% groundcover, consisting of at least 50% vegetation groundcover.
20.6 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so, and the results are not significantly different to upstream values for pH, EC and turbidity.
20.7 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP as appropriately managed.
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PART 2: Non-use management areas 
[bookmark: _Toc65157992](IA1) Improvement area 1
	Non-use management area (NUMA)

	Improvement area
	IA1

	Relevant activities
	Void and set-backs

	Total size (ha)
	1838

	Commencement of first milestone: MM1
	10/12/2085

	NUMA
	NUMA

	Date area is available
	10/12/2085
	10/12/2087
	10/12/2098
	10/12/2105
	
	
	
	
	
	

	Cumulative area available (ha)
	624
	1080
	1335
	1838
	
	
	
	
	
	

	Milestone completed by
	10/12/2087
	10/12/2089
	10/12/2100
	10/12/2107
	10/12/2144
	
	
	
	
	

	Milestone Reference
	Cumulative area achieved (ha)

	MM1
	624
	1080
	1335
	1838
	
	
	
	
	
	

	MM2
	624
	1080
	1335
	1838
	
	
	
	
	
	

	MM3
	
	
	
	
	1838
	
	
	
	
	





[bookmark: _Toc65157995]Improvement area milestones 
	Milestone reference
	Management milestone
	Milestone criteria

	MM1
	Achievement of structural stability
	1.1 Highwall landforms must:
a) Prevent surface flow of floodwater into the void
b) Be geotechnically stable when floodwater is against the watercourse-side batter 
c) Prevent seepage flow of floodwater into the void 
d) Not be constructed with dispersive material
e) Have maximum 30% slopes with rock for scour protection. 
f) Minimum height to include appropriate freeboard for flood heights and materials.
1.2 The final design for highwall landform must be completed by an AQP based on the latest flood modelling and materials data prior to construction.
1.3 Final residual voids are not subject to inundation from floodwaters up to and including the 0.1% AEP.
1.4 The high-wall, end-wall and low-wall achieve a FoS ≥1.5 within the NUMA extents as determined by an AQP.  
1.5 A minimum distance of 50m is to be designed between the residual void crest and the toe of the safety bund, where against an external perimeter mining lease (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021) boundary or a watercourse.
1.6 The location of the voids and associated safety bunds does not cause instability or degradation to the land outside of the mining lease (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021) boundary.
1.7 Low-walls are free-draining into the void lake with a maximum 37 degree slopes.
1.8 Residual voids must not overtop.
1.9 Flood mitigation as per 1.3 have appropriate scour protection to sustain flood velocities.
1.10 Residual voids collectively act as groundwater sinks within the relevant mining lease (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021) boundary post closure as demonstrated by groundwater modelling defined in condition PRCP12.

	MM2
	Achievement of surface requirements
	2.1 Competent safety bund or equivalent landform in place around the perimeter of the residual void to prevent access to the residual void, at the geotechnical set-back distance.
2.2 Fencing erected, where required to prevent access to the residual void, around the perimeter of the safety bund.
2.3 Warning signage placed along the fence line (nominally one sign every 100m).
2.4 A minimum distance of 25m is to be designed between the residual void low-wall crest within the NUMA and the safety bund or equivalent landform in 2.1.
2.5 An area of 60ha of unmined land is retained between Grevillea residual void and the eastern boundary of mining lease ML700021.
2.6 Despite 2.5, the safety bund can be positioned within the 60ha area and located as close to the high wall as necessary to enable the eastern side of the bund wall to retain its current land use.

	MM3
	Achievement of sufficient improvement
	3.1 Certification from an AQP that: 
a) The residual void is safe to humans and livestock
b) Residual voids are monitored for water level annually, in accordance with condition PRCPXX, and are shown to be on a trajectory to the establishment of a residual void sink at surrender 
c) The water level and quality in the void will not cause environmental harm to the surrounding environment, as demonstrated by residual void water level, groundwater level, quality monitoring and modelling
d) Voids retain flood immunity, supported by flood modelling re-run at end of life and calibrated against the final landform 
e) The highwall landform has been constructed in accordance with the final design as per 1.2
f) Erosion and sediment control measures have been installed and are operating as per design
g) Appropriate safety infrastructure at the geotechnical set-back distance has been installed to prevent access to the NUMA
h) The residual void will not present an unacceptable risk of environmental harm outside of the relevant external perimeter mining lease (ML1775, ML1782, ML1784, ML2360, ML2410, ML70142, ML70294, ML70298, ML70328, ML700021) boundary
i) Erosion of the landform within the NUMA area will not negatively impact on the stability of any adjacent rehabilitation areas, or their ability to sustain their PMLU. 
3.2 Monitoring and maintenance of exclusion fences and bunds to be carried out to ensure they remain effective.



PART 3: Maps 
The following two maps must be included in the application and will form part of the approved PRCP Schedule (see PRCP Guideline (ESR/2019/4964) for examples). Attach the maps to the application as high-resolution jpeg files. 
Final site design 
A final site design has the purpose of showing the community what the site will look like post surrender, and must depict: 
· All Post Mining Land Uses (PMLU) and Non-Use Management Areas (NUMA) for all land within the relevant resource tenures, including undisturbed land 
· Maximum disturbance footprint 
· Resource tenure boundaries 
· Floodplain extent (if relevant). 
Reference map(s) 
Reference map(s) have the purpose of showing the boundary of each rehabilitation area (for PMLUs) and improvement area (for NUMAs). Reference maps may contain more than one rehabilitation area/improvement area and must be to a scale that allows for easy interpretation. Only areas of disturbance need to be included on these reference maps.
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