## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Dump
Total rehabilitation area size (ha) |  |  |  | 735.75
Commencement of first milestone: RM4 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2042-12-31 | 2045-12-31
Cumulative area available (ha) | 735.75 | 735.75 | 735.75
Milestone completed by | 2038-12-31 | 2045-12-31 | 2048-12-31
Milestone Reference | Cumulative area achieved (ha)
RM 4 | 735.75
RM 5 | 735.75
RM 6 | 735.75
RM 8 |  | 735.75
RM10 |  |  | 735.75
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | TSF
Total rehabilitation area size (ha) |  |  |  | 3.97
Commencement of first milestone: RM 3 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2043-12-31 | 2046-12-31
Cumulative area available (ha) | 3.97 | 3.97 | 3.97 | 3.97
Milestone completed by | 2034-12-31 | 2039-12-31 | 2046-12-31 | 2049-12-31
Milestone Reference | Cumulative area achieved (ha)
RM 3 | 3.97
RM 4 |  | 3.97
RM 5 |  | 3.97
RM 6 |  | 3.97
RM 8 |  |  | 3.97
RM 10 |  |  |  | 3.97
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | CHPP
Total rehabilitation area size (ha) |  |  |  | 12.87
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2044-12-31 | 2047-12-31
Cumulative area available (ha) | 12.87 | 12.87 | 12.87 | 12.87 | 12.87
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2047-12-31 | 2050-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 12.87
RM2 |  | 12.87
RM4 |  |  | 12.87
RM5 |  |  | 12.87
RM6 |  |  | 12.87
RM8 |  |  |  | 12.87
RM10 |  |  |  |  | 12.87
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure
Total rehabilitation area size (ha) |  |  |  | 73.15
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2044-12-31 | 2047-12-31
Cumulative area available (ha) | 73.15 | 73.15 | 73.15 | 73.15 | 73.15
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2047-12-31 | 2050-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 73.15
RM2 |  | 73.15
RM4 |  |  | 73.15
RM5 |  |  | 73.15
RM6 |  |  | 73.15
RM8 |  |  |  | 73.15
RM10 |  |  |  |  | 73.15
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Rail infrastructure
Total rehabilitation area size (ha) |  |  |  | 11.21
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2044-12-31 | 2047-12-31
Cumulative area available (ha) | 11.21 | 11.21 | 11.21 | 11.21 | 11.21
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2047-12-31 | 2050-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 11.21
RM2 |  | 11.21
RM4 |  |  | 11.21
RM5 |  |  | 11.21
RM6 |  |  | 11.21
RM8 |  |  |  | 11.21
RM10 |  |  |  |  | 11.21
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Road infrastructure
Total rehabilitation area size (ha) |  |  |  | 104
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2044-12-31 | 2047-12-31
Cumulative area available (ha) | 104 | 104 | 104 | 104 | 104
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2047-12-31 | 2050-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 104
RM2 |  | 104
RM4 |  |  | 104
RM5 |  |  | 104
RM6 |  |  | 104
RM8 |  |  |  | 104
RM10 |  |  |  |  | 104
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Water management
Total rehabilitation area size (ha) |  |  |  | 27.08
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2044-12-31 | 2047-12-31
Cumulative area available (ha) | 27.08 | 27.08 | 27.08 | 27.08 | 27.08
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2047-12-31 | 2050-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 27.08
RM2 |  | 27.08
RM4 |  |  | 27.08
RM5 |  |  | 27.08
RM6 |  |  | 27.08
RM8 |  |  |  | 27.08
RM10 |  |  |  |  | 27.08
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Existing rehabilitation (Grazing)
Total rehabilitation area size (ha) |  |  |  | 289.01
Commencement of first milestone: RM1 |  |  |  | 2023-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2023-12-31 | 2028-12-31 | 2030-12-30
Cumulative area available (ha) | 289.01 | 289.01 | 289.01
Milestone completed by | 2028-12-31 | 2030-12-30 | 1932-12-30
Milestone Reference | Cumulative area achieved (ha)
RM6 | 289.01
RM8 |  | 289.01
RM10 |  |  | 289.01
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Cleared areas
Total rehabilitation area size (ha) |  |  |  | 21.03
Commencement of first milestone: RM1 |  |  |  | 2023-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2023-12-31 | 2032-12-31 | 2035-12-30
Cumulative area available (ha) | 21.03 | 21.03 | 21.03
Milestone completed by | 2028-12-31 | 2035-12-30 | 2038-12-31
Milestone Reference | Cumulative area achieved (ha)
RM4 | 21.03
RM5 | 21.03
RM6 | 21.03
RM8 |  | 21.03
RM10 |  |  | 21.03
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10
Relevant activities |  |  |  | Native ecosystem
Total rehabilitation area size (ha) |  |  |  | 20.7
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Native ecosystem (RE 11.11.1 and RE 11.3.4)
Date area is available | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2040-12-31 | 2045-12-31
Cumulative area available (ha) | 20.7 | 20.7 | 20.7 | 20.7 | 20.7
Milestone completed by | 2034-12-31 | 2035-12-30 | 2040-12-31 | 2045-12-31 | 2055-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 20.7
RM2 |  | 20.7
RM4 |  |  | 20.7
RM5 |  |  | 20.7
RM7 |  |  | 20.7
RM9 |  |  |  | 20.7
RM11 |  |  |  |  | 20.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA11
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA11
Relevant activities |  |  |  | Existing rehabilitation (Native ecosystem)
Total rehabilitation area size (ha) |  |  |  | 20.89
Commencement of first milestone: RM1 |  |  |  | 2023-12-31
PMLU |  |  |  | Native ecosystem (RE 11.11.1 and RE 11.3.4)
Date area is available | 2023-12-31 | 2028-12-31 | 2029-12-30
Cumulative area available (ha) | 20.89 | 20.89 | 20.89
Milestone completed by | 2028-12-31 | 2029-12-30 | 1932-12-30
Milestone Reference | Cumulative area achieved (ha)
RM7 | 20.89
RM9 |  | 20.89
RM11 |  |  | 20.89
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA12
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA12
Relevant activities |  |  |  | Diversions
Total rehabilitation area size (ha) |  |  |  | 34.88
Commencement of first milestone: RM1 |  |  |  | 2033-12-31
PMLU |  |  |  | Light grazing pasture
Date area is available | 2033-12-31 | 2042-12-31 | 2045-12-31
Cumulative area available (ha) | 34.88 | 34.88 | 34.88
Milestone completed by | 2038-12-31 | 2045-12-30 | 2048-12-31
Milestone Reference | Cumulative area achieved (ha)
RM4 | 34.88
RM6 | 34.88
RM8 |  | 34.88
RM10 |  |  | 34.88
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  | IA1
Relevant activities |  |  | Residual void
Total size (ha) |  |  | 291.6
Commencement of first milestone: MM1 |  |  | 2033-12-31
NUMA |  |  | Water storage
Date area is available | 2033-12-31 | 2042-12-31
Cumulative area available (ha) | 291.6 | 291.6
Milestone completed by | 2042-12-30 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
MM1 | 291.6
MM2 | 291.6
MM3 | 291.6
MM4 |  | 291.6
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) decommissioning and removing services;
b) removing infrastructure;
c) decommissioning dams;
d) removing all general and regulated waste; and
e) decommissioning or converting water or monitoring bores, exploration drill holes.
RM2 | Remediation of contaminated land | a) removing or remediating contaminated land to a PMLU of grazing or native ecosystem;
b) all contaminated sediment is removed;
c) all plastic liners are removed and disposed;
d) site investigation report is prepared by an AQP; and
e) certification from an AQP that all contaminated land has been removed.
RM3 | Cover system installation | a) certification by an AQP that waste products generated from the washing of coal are buried under spoil with a minimum of cover thickness of 5 m.
RM4 | Landform development and reshaping or reprofiling | a) reshaping or recontouring the landform;
b) install drainage management structures;
c) all major earthworks completed;
d) stable landform and slope angles ~15 % average; and
e) landform is assessed as geotechnically stable by an AQP.
Diversions (RA12)
f) certification from an AQP that diversions are constructed as per the requirements of the certified design, and in accordance with DNRME’s Guideline: Works that interfere with water in a watercourse for a resource activity — watercourse diversions under the Water Act 2000 (OSW/2019/4599).
RM5 | Surface preparation | a) placement of a minimum of 0.15 m of topsoil;
b) contour ripping completed; and
c) fertiliser applied at rates of 250 kg/ha.
RM6 | Revegetation (grazing pasture) | a) direct seeding at application rate determined by an AQP;
b) seed mix applied contains a suitable range of trees, shrubs and perennial grass species and suitable leguminous species consistent with the surrounding area; and
c) stock exclusion fencing installed until achievement of surface requirements for grazing pasture.
RM7 | Revegetation (native ecosystem) | a) seed mix applied contains species consistent with RE 11.1.11 or RE 11.3.4;
b) species comprise ≥ 20 % of the average number of species described in RE 11.1.11 or RE 11.3.4 technical descriptions;
c) average height of each layer is ≥ 70 % of average layer height described in RE 11.1.11 or RE 11.3.4 technical descriptions; and
d) average fractional cover of each layer is ≥ 50 % of average fractional cover described in RE 11.1.11 or RE 11.3.4 technical description.
RM8 | Achievement of surface requirements (grazing pasture) | a) species richness and diversity achieved is consistent with the sown seed mix and similar to reference sites;
b) revegetation ≥70% comparable to analogue site;
c) no active areas of gully erosion and drainage follows appropriate drainage paths;
d) certification from an AQP that rehabilitation is resilient to fire; and
e) certification by an AQP that weeds and pest species are in densities no greater than at analogue sites.
Diversions (RA12)
f) an AQP prepares an assessment report annually based on the Index of Diversion Condition (IDC) assessment, where:
a. the diversions have achieved a target Geomorphic Index score of ≥ 95 % relative to baseline condition.
b. the riparian corridor has achieved a target Riparian Index score of ≥ 70 % relative to baseline condition.
RM9 | Achieving surface requirements (native ecosystem) | a) for RE 11.1.11 species richness ≥15 native species: - tree species richness ≥ 2 species, including Yellow Jacket (Corymbia liechhgardtii); - shrub species richness ≥ 3 species; - grass species richness ≥5 species; and - forb and other species richness ≥ 5 species
b) for RE 11.3.4 species richness ≥ 18 native species: - tree species richness ≥ 3 species, including Forest Red Gum (Eucalyptus tereticornis); - shrub species richness ≥ 4 species; - grass species richness ≥ 6 species; and - forb and other species richness ≥ 5 species.
c) revegetation ≥ average fractional cover derived from RE technical descriptions for RE 11.1.11: - trees cover ≥ 57.7 %; - shrubs ≥ 36.9 %; and - grasses and forbs cover ≥ 29.3 %.
d) revegetation ≥ average fractional cover derived from RE technical descriptions for the RE 11.3.4: - trees cover ≥ 37.1 %; - shrubs ≥ 4.3 %; and - grasses and forbs cover ≥ 61.6 %.
e) no active areas of gully erosion and drainage follows appropriate drainage paths;
f) certification from an AQP that rehabilitation is resilient to fire; and
g) certification by an AQP that weeds and pest species are in densities no greater than at analogue sites.
RM10 | Achievement of PMLU to stable condition (grazing pasture) | a) certification from an AQP that the area has achieved stable condition;
b) certification from an AQP that the landform achieved a factor of safety ≥ 1.5;
c) maximum erosion rate of < 10 t/ha/yr;
d) total percentage ground cover (vegetation, litter and rock combined) is > 70 %;
e) there are no declared Noxious Class 1 or Class 2 weeds;
f) native fauna identified at reference sites are present or indicators of these species are recorded;
g) water quality complies with Table C7 of EPML00876713.
Diversions (RA12)
h) prepare assessment report by an AQP certifying that the diversion is operating in accordance with, DNRME Guideline: Works that interfere with water in a watercourse for a resource activity — watercourse diversions under the Water Act 2000 (OSW/2019/4599) criteria and is in a stable condition. The report will include data from the IDC assessment, showing that Geomorphic Index has maintained a score of ≥ 95 % and the Riparian Vegetation Index has maintained a score of ≥ 70 % for two consecutive years.
i) certification from AQP that the diversions have achieved a stable condition, and are able to sustain a 0.1% AEP flood event.
RM11 | Achieving PMLU to stable condition (native ecosystem) | a) certification from an AQP that the area has achieved stable condition;
b) certification from an AQP that the landform achieved a factor of safety ≥ 1.5;
c) total percentage groundcover (vegetation, litter and rock combined) is ≥ 50 %;
d) maximum erosion rate of < 10 t/ha/yr;
e) there are no declared Noxious Class 1 or Class 2 weeds;
f) native fauna at reference sites are present or indicators of these species are recorded; and
g) water quality complies with Table C7 of EPML00876713.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Conversion of the void into a permanent waterbody | a) all major earthworks completed.
MM2 | Highwall and lowwall treatment | a) maximum slope of 16.7° (30%) in competent rock;
b) maximum slope of 8.5° (15%) in incompetent rock;
c) factor of safety ≥1.5; and
d) residual void complies with Condition F17 of EA EPML00876713.
MM3 | Achievement of surface requirements | a) fencing of 1.8 m high erected around the perimeter of the residual void;
b) warning signage posted around the perimeter of the residual void in accordance with the Technical Guidelines for the Environmental Management of Exploration and Mining in Queensland:
c) safety bund constructed at 2 m in height, 4 m in base width and 10 m beyond the area which may be affected by void edge instability; and
d) direct seeding of low walls with species and application rates determined by an AQP.
MM4 | Achievement of enough improvement | a) certification from an AQP that the residual void will not cause environmental harm outside of the relevant tenure boundary:
b) certification from an AQP that the residual void is safe to humans and livestock; and
c) certification from an AQP that the water level in the residual void will not cause environmental harm to the surrounding environment.
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones