## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1 - Open Cut Depression
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 Final pit void
Relevant activities |  |  |  | Open cut mining pits
Total rehabilitation area size (ha) |  |  |  | 94.25
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 94.25
Milestone completed by | 2032-12-10 | 2033-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 94.25
RM4 |  | 94.25
RM5 |  | 94.25
RM6 |  |  | 94.25
RM7 |  |  | 94.25
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2 - OOPD
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 Out of Pit Dump
Relevant activities |  |  |  | Overburden emplacement areas
Total rehabilitation area size (ha) |  |  |  | 74.39
Commencement of first milestone: RM3 |  |  |  | 2026-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2026-01-31 | 2027-01-31 | 2028-01-31 | 2029-01-31 | 31/01/230 | 2031-01-31 | 2032-01-31
Cumulative area available (ha) | 23.89 | 47.22 | 51.53 | 64.67 | 64.84 | 70.57 | 74.39
Milestone completed by | 2026-12-10 | 2027-12-10 | 2028-12-10 | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 418183
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM2 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM3 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM4 | 9.89 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM5 | 9.89 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM6 | 418183: 74.39
RM7 | 418183: 74.39
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3 - Inpit Dump
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 In pit Dump
Relevant activities |  |  |  | Overburden emplacement within open cut pit
Total rehabilitation area size (ha) |  |  |  | 195.98
Commencement of first milestone: RM3 |  |  |  | 2029-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2029-01-31 | 2030-01-31 | 2031-01-31 | 2032-01-31
Cumulative area available (ha) | 51.89 | 121.12 | 162.4 | 195.88
Milestone completed by | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2044-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 51.89 | 121.12 | 162.4 | 195.88
RM3 | 51.89 | 121.12 | 162.4 | 195.88
RM4 | 20.03 | 51.89 | 121.12 | 162.4 | 195.88
RM5 | 20.03 | 51.89 | 121.12 | 162.4 | 195.88
RM6 | [5 empty] | 195.88
RM7 | [5 empty] | 195.88
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4 - Infrastructure
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 Infrastructure
Relevant activities |  |  |  | ROM pad, Mine Infrastructure Area including office, workshop
Total rehabilitation area size (ha) |  |  |  | 82.47
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 94.25
Milestone completed by | 2032-12-10 | 2033-12-10 | 2043-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 82.47
RM2 | 82.47
RM3 |  | 82.47
RM4 |  | 82.47
RM5 |  | 82.47
RM6 |  |  | 82.47
RM7 |  |  | 82.47
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5 - Tracks & Roads
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5 Infrastructure disturbance
Relevant activities |  |  |  | Access Tracks and Haul Roads
Total rehabilitation area size (ha) |  |  |  | 16.07
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 16.07
Milestone completed by | 2032-12-10 | 2033-12-10 | 2043-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 16.07
RM2 | 16.07
RM3 |  | 16.07
RM4 |  | 16.07
RM5 |  | 16.07
RM6 |  |  | 16.07
RM7 |  |  | 16.07
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6 - Retained infrastructure
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6 Retained infrastructure
Relevant activities |  |  | Water Dams
Total rehabilitation area size (ha) |  |  | 2.08
Commencement of first milestone: RM3 |  |  | 2032-01-31
PMLU |  |  | Retained infrastructure
Date area is available | 2032-01-31
Cumulative area available (ha) | 2.08
Milestone completed by | 2032-12-10 | 2033-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 2.08
RM8 |  | 2.08
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | RM1.1 All built and service infrastructure demolished and removed (except for clean water management structure as agreed in writing with the landowner) RM1.2 All exploration drill holes and monitoring bores rehabilitated in accordance with the applicable Australian Standard or guideline. RM1.3 All aquifers isolated where exploration drill holes or monitoring bores have intersected more than one water bearing strata, in accordance with the ‘Minimum Construction Requirements for Water Bores in Australia’ (Australian Government, February 2012) or latest edition. RM1.4 Risk assessment documents identified potential risks and controls/mitigation measures successfully implemented post closure in accordance with relevant guidelines and Australian Standards such as ISO31000 Risk Management.
RM2 | Remediation of contaminated land | RM2.1 Potential hazardous materials identified during mine life and removed or selected capping material applied with cover thickness appropriate to the contaminant as determined by appropriately qualified person. RM2.2 Contaminated land assessment completed by a suitably qualified person and certified by an approved auditor. RM2.3 Sediment at the base of the dam retained for landholder complies with the levels outlined in the Draft Guidelines for the Assessment and Remediation of Contaminated Sites in Queensland or any later guideline. RM2.4 Land removed from the Environmental Management Register and the Contaminated Land Register where relevant.
RM3 | Landform development and reshaping/reprofiling | RM3.1 Major earthworks completed in accordance with design specifications for a final stable landform provided by a suitably qualified person. RM3.2 Natural drainage lines reinstated. Where necessary, erosion and sediment control systems are installed, fit for purpose and designed by a suitably qualified person. RM3.3 Dam to remain for landholder use is safe for livestock access. RM3.4 Coal seams fully capped by at least 2 metres of competent and benign material. RM3.5 No slopes steeper than 30%. RM3.6 Slopes between 15% and 30% consist of competent rock. RM3.7 Vertical intervals between slope breaks are 10m. RM3.8 No evidence of slumping identified as per the geotechnical assessment conducted by a suitably qualified and experienced person.
RM4 | Surface preparation | RM4.1 Surface roughness, infiltration capacity, aggregate stability and surface condition as defined in the Australian Soil and Land Survey Handbook are capable of sustaining the identified post closure land use. RM4.2 Topsoil has been managed according to the requirements of the environmental authority and the Topsoil Management Plan.
RM5 | Revegetation | RM5.1 Pasture species mix sown at appropriate rate.
RM6 | Achievement of surface requirements | RM6.1 Vegetation type and density are of species suited to the site’s characteristics including soil type, topography and climate. RM6.2 Species in rehabilitated areas show evidence of flowering, viable seed setting, germination and emergence, and will continue to do so. RM6.3 Vegetation in rehabilitated areas includes the presence of species suitable and complimentary to the post-mining land use, and are at a density and composition comparable to reference sites. RM6.4 Pasture productivity recovers following natural and man-made events (e.g. grazing, fire, slashing, and drought). RM6.5 The presence of weeds and pest species is no greater than the prevalence on the reference sites. RM6.6 Ground cover of at least 90% compared to the reference sites.
RM7 | Achievement of stable PMLU (grazing) | RM7.1 No evidence of spontaneous combustion post closure. RM7.2 No formation of erosion gullies and rill erosion. RM7.3 The erosion rates on the post closure landform are similar to rates of reference sites. RM7.4 Physical and chemical properties of surface soils are safe and able to support the identified post closure land use. RM7.5 Water quality in the void achieves stock water quality (ANZECC) demonstrated by surface water quality monitoring regime post closure. RM7.6 Water quality of surface water runoff does not exceed limits outlined in Environmental Protection (Water) Policy 2009; Mackenzie River Sub-basin Environmental Values and Water Quality Objectives. RM7.7 Groundwater quality does not exceed limits outlined in Environmental Protection (Water) Policy 2009; Mackenzie River Sub-basin Environmental Values and Water Quality Objectives. RM7.8 No significant decline in groundwater quality has occurred relative to historic (background) groundwater quality. RM7.9 Vegetation cover, types and densities comparable to relevant rehabilitation monitoring reference sites. RM7.10 Landform suitable for grazing activities and provides suitable access to water for stock and able to sustain pre-mining grazing capacity. RM7.11 Risk assessment documents identified potential risks and controls/mitigation measures successfully implemented post closure in accordance with relevant guidelines and Australian Standards such as ISO31000 Risk Management. RM7.12 Risks identified in risk assessment are low for Domain 1, Domain 2. Risks are moderate to low for Domain 4 or additional mitigation measures implemented.
RM8 | Achievement of stable condition for retained infrastructure | RM8.1 Final structure is fit for purpose as demonstrated. RM8.2 Spillway has adequate capacity to safely manage a 1:100 year flood event. RM8.3 Sediments/sludge removed from the structure. RM8.4 Water storage Infrastructure retained must not be a referral dam under the Water Supply (Safety and Reliability) Act 2008. RM8.5 No formation of erosion gullies and rill erosion. RM8.6 The erosion rates on post-closure landform are similar to rates of reference sites. RM8.7 Water quality achieves stock water quality (ANZECC) demonstrated by surface water quality monitoring regime post closure. RM8.8 Surface water quality does not exceed limits outlined in Environmental Protection (Water) Policy 2009; Mackenzie River Sub-basin Environmental Values and Water Quality Objectives. RM8.9 Groundwater quality does not exceed limits outlined in Environmental Protection (Water) Policy 2009; Mackenzie River Sub-basin Environmental Values and Water Quality Objectives. RM8.10 No significant decline in groundwater quality has occurred relative to historic (background) groundwater quality. RM8.11 Sign off by post mining landholder – asset transfer agreement; receiver of the structure is aware of risks. RM8.12 Risk assessment identified potential risks and controls/mitigation measures successfully implemented post closure in accordance with relevant guidelines and Australian Standards such as ISO31000 Risk Management. RM8.13 Risks identified in risk assessment are low.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones