## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1 - Open Cut Depression
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 - Open Cut Depression
Relevant activities |  |  |  | Rehabilitating the final Void
Total rehabilitation area size (ha) |  |  |  | 94.25
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 94.25
Milestone completed by | 2032-12-10 | 2033-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 94.25
RM4 |  | 94.25
RM5 |  | 94.25
RM6 |  |  | 94.25
RM7 |  |  | 94.25
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2 - OOPD
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 Out of Pit Dump
Relevant activities |  |  |  | Overburden emplacement areas
Total rehabilitation area size (ha) |  |  |  | 74.39
Commencement of first milestone: RM3 |  |  |  | 2026-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2027-01-31 | 2028-01-31 | 2029-01-31 | 2030-01-31 | 2031-01-31 | 2032-01-31 | 2033-01-31
Cumulative area available (ha) | 23.89 | 47.22 | 51.53 | 64.67 | 64.84 | 70.57 | 74.39
Milestone completed by | 2027-12-10 | 2028-12-10 | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 418183
Milestone Reference | 2027-12-10: Cumulative area achieved (ha)
RM3 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM4 | 9.89 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM5 | 9.89 | 23.89 | 47.23 | 51.38 | 64.67 | 64.84 | 70.57 | 74.39
RM6 | 418183: 74.39
RM7 | 418183: 74.39
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3 - Inpit Dump
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 In pit Dump
Relevant activities |  |  |  | Overburden emplacement within open cut pit
Total rehabilitation area size (ha) |  |  |  | 195.98
Commencement of first milestone: RM3 |  |  |  | 2029-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2029-01-31 | 2030-01-31 | 2031-01-31 | 2032-01-31
Cumulative area available (ha) | 51.89 | 121.12 | 162.4 | 195.88
Milestone completed by | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2044-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 51.89 | 121.12 | 162.4 | 195.88
RM4 | 20.03 | 51.89 | 121.12 | 162.4 | 195.88
RM5 | 20.03 | 51.89 | 121.12 | 162.4 | 195.88
RM6 | [5 empty] | 195.88
RM7 | [5 empty] | 195.88
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4 - Infrastructure
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 Infrastructure
Relevant activities |  |  |  | ROM pad, Mine Infrastructure Area including office, workshop
Total rehabilitation area size (ha) |  |  |  | 82.47
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 94.25
Milestone completed by | 2032-12-10 | 2033-12-10 | 2043-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 82.47
RM2 | 82.47
RM3 |  | 82.47
RM4 |  | 82.47
RM5 |  | 82.47
RM6 |  |  | 82.47
RM7 |  |  | 82.47
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5 - Tracks & Roads
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5 Infrastructure disturbance
Relevant activities |  |  |  | Access Tracks and Haul Roads
Total rehabilitation area size (ha) |  |  |  | 16.07
Commencement of first milestone: RM3 |  |  |  | 2032-01-31
PMLU |  |  |  | Low intensity cattle grazing
Date area is available | 2032-01-31
Cumulative area available (ha) | 16.07
Milestone completed by | 2032-12-10 | 2033-12-10 | 2043-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 16.07
RM3 |  | 16.07
RM4 |  | 16.07
RM5 |  | 16.07
RM6 |  |  | 16.07
RM7 |  |  | 16.07
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6 - Retained infrastructure
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6 Retained infrastructure
Relevant activities |  |  | Water Dams
Total rehabilitation area size (ha) |  |  | 2.08
Commencement of first milestone: RM3 |  |  | 2032-01-31
PMLU |  |  | Retained infrastructure
Date area is available | 2032-01-31
Cumulative area available (ha) | 2.08
Milestone completed by | 2032-12-10 | 2033-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 2.08
RM8 |  | 2.08
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | 1.1 With the exception of any infrastructure to remain as part of the post-mining land use (PMLU), where infrastructure is agreed to be retained by the landholder as evidenced by a signed landholder agreement, or required for rehabilitation activities, the following are complete: a) All services disconnected, terminated and removed. b) All buildings and infrastructure dismantled and removed offsite. c) All hardstand, concrete areas and roads (bitumen, blue metal, aggregate etc) removed. d) All fencing and associated foundations removed. e) All pipelines drained and removed. f) All waste not authorised to be disposed of on-site under Environmental Authority EA0002046 removed. g) All surface water drainage infrastructure that is not compatible with the sustainment of the PMLU is removed. h) All drillholes, bores, sediment ponds and sumps decommissioned except the bores required to comply with the monitoring requirements. i) All machinery and equipment removed from site. 1.2 All dams dewatered and desilted. 1.3 All infrastructure to be retained onsite must be safe, stable and not cause environmental harm.
RM2 | Identification, remediation and removal of contaminated land | 2.1 Preliminary Site Assessment including review of previous activities to assess whether contamination has the potential to exist in a mine domain and whether further investigation is needed to be completed by a Suitably Qualified Person (SQP). 2.2 Contaminated land investigations (investigation, remediation and validation) in accordance with the EP Act, including a site investigation report, and where required, a validation report and/or a draft Site Management Plan. 2.3 Contaminated water and sediment removed from dams. 2.4 Contaminated material either remediated in-situ or removed/transported to facility lawfully able to accept the material. 2.5 An AQP certifies that that no contamination unsuitable for the PMLU remains or is occurring.
RM3 | Landform development (re-profiling / re shaping) | 3.1 The surface and groundwater monitoring network is installed and monitoring underway (one year of sampling undertaken). 3.2 All major earthworks (including reshaping, pushing/trimming) are completed in accordance with a design specification provided by an AQP for the final landform design that: a) Has undergone landscape evolution modelling and demonstrated the landform is erosionally stable; b) Has undergone geotechnical assessment and demonstrates the ability to achieve FOS≥ 1.5; c) Is water shedding; and d) Is suitable to sustain the PMLU. 3.3 Any dams to remain for landholder use that are safe for use and access by livestock, where: a) Livestock access: slope <17% or 1:6 to minimise erosion and for safe entry and exit to water, or transfer to troughs to avoid erosion of dam walls; b) water quality pH <9 and TDS < 5000mg/L as per ANZG livestock drinking water guidelines. 3.4 No slopes in the final landform to exceed a slope gradient of 25% . 3.5 Vertical intervals between slope breaks are ≤10m to prevent erosion during rehabilitation. 3.6 Geotechnical assessment finds no evidence of sloping and that landform achieves the factor of safety (FOS) ≥ 1.5. 3.7 Rehabilitated outfacing slopes are <25% 3.8 5m bench/berms implemented where slopes >10% 3.9 If vertical height exceeds 1:15, split equally with middle bench/berm. RA1 3.10 Coal seams fully capped by at least 2 metres of competent and benign material.
RM4 | Soil profile preparation | 4.1 Topsoil has been applied at a minimum depth of 200mm. 4.2 Areas are deep ripped to at least 300mm. 4.3 Assessment of topsoil/growth media characteristics and the development of an amelioration and physical treatment plan is completed by an AQP. 4.4 Ameliorant and physical treatments such as fertiliser, lime, gypsum and/or organic matter are applied as identified in RM4.3. 4.5 An AQP certifies that: a) Soil stability Index post closure (LFA) is within 10% of median reference sites, the LFA infiltration capacity is within 10% and the Landscape Organization Index is 90% of median LOI score to achieve and sustain the grazing PMLU. b) Reconstituted soil profiles with chemical and physical attributes equal or better than: i. Minimum effective rooting depth of 300 mm ii. Emerson aggregate stability class >3 (LFA slake test). iii. Topsoil pH between 6-8.5. iv. Electrical Conductivity (saturated extract) (dS/m) < 2. v. Topsoil Exchangeable Sodium Percentage (ESP%) is <8% vi. Subsoil/other growth media Exchangeable Sodium Percentage (ESP%) is <10% vii. Total Organic Carbon > 1% . viii. No PAF material present.
RM5 | Revegetation (seeding) | 5.1 Seeding is completed at a rate of 19kg/ha (total) in accordance with Table 1: Seed Mixes. 5.2 At least six grass species of which three are 3P pasture species and three tree/shrub species are applied per application area. 5.3 Seeding includes cover crops (millet/sorghum/legume) specified in Table 1: Seed Mixes for rapid soil cover and stability. 5.4 Stock exclusion fencing installed to control grazing pressure on newly rehabilitated areas for at least one full growth cycle (Seed set and senescence achieved). Appropriate erosion controls are installed/placed and functioning as designed to ensure plant establishment is not significantly impacted from erosive events.
RM6 | Achievement of surface requirements/self-sustaining vegetation establishment | 6.1 Surface water runoff collected across representative areas of rehabilitation complies with Table 2: Surface water quality limits. 6.2 Weed presence is a less than 5% of total vegetative cover. 6.3 Total species count must include a minimum species richness (per ha (averaged)) of: a) >6 grass species (≥3 3P grass species) 6.4 Species in rehabilitated areas show evidence of propagation (flowering, viable seed setting, germination and emergence). 6.5 Foliage and ground cover achieves the following: • Bare ground <30%; • Vegetative groundcover > 60% • Woody fraction <10% • Overall groundcover consists of rock, dead and live plant matter. 6.6 Corrective action arising from the routine inspections program have been undertaken. 6.7 With respect to erosion: • No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Table 6 – Erosion classification framework; • Any erosion present will not compromise the achievement of a PMLU to a stable condition; and • Erosion requiring intervention has been remediated and does not impact achieving the PMLU. 6.8 No evidence of spontaneous combustion. 6.9 No acid or saline seepage areas.
RM7 | Achievement of stable PMLU (grazing) | 7.1 No evidence of spontaneous combustion post closure (RA1 Only). 7.2 Hazard and Safety Assessment completed by an AQP assesses hazards to be low risk with no significant increase in risk expected over time and comparable to the surrounding unmined landscape subject to the same land use. 7.3 No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Table 6 – Erosion classification framework. 7.4 Any erosion present will not compromise the achievement of a PMLU to a stable condition. 7.5 Rehabilitation is geotechnically stable and meets Factor of Safety (FoS) ≥ 1.5, unless an alternative is justified by an AQP. 7.6 An AQP certifies that the water quality in the void achieves stock water quality for 5 years (ANZECC) demonstrated by surface water quality monitoring regime post closure. 7.7 Slopes >15% achieve 60% groundcover. 7.8 Landform suitable for grazing activities with slopes < 25%, and vegetation type and density is sustainable and suitable for grazing capacity of 3t/ha. 7.9 All fencing used to prevent stock and machinery access to revegetated areas has been removed, except where fencing is agreed to be retained by the landholder as evidenced by a signed landholder agreement. 7.10 Post closure land suitability assessment by an AQP certifies that land has achieved land suitability class of 4 or better as defined in the ‘Guidelines for Agricultural Land Evaluation in Queensland’ (State Department of Queensland 2013). 7.11 Risk assessment documents identified potential risks and controls/mitigation measures successfully implemented post closure in accordance with relevant guidelines and Australian Standards such as ISO31000 Risk Management. 7.12 Risks identified in risk assessment are low for Domain 1, Domain 2. Risks are moderate to low for all RA’s or additional mitigation measures implemented.
RM8 | Achievement of stable condition for retained infrastructure | 8.1 All retained water storage is safe and stable. 8.2 Water storages monitored quarterly, water must be of a suitable quality for livestock ingestion and must not exceed the stock water guidelines (ANZECC 2000), for a minimum of 5 consecutive years. 8.3 Final retained structures are fit for purpose and will be transferred to a landholder as evidenced by a signed landholder agreement. 8.4 Water storage Infrastructure retained must not be a referral dam under the Water Supply (Safety and Reliability) Act 2008. 8.5 Certification and condition report on all water storage infrastructure to be proved for retention by post mining landholder. 8.6 An AQP certifies that the; a) Spillway has adequate capacity to safely manage a 1:100 year flood event. b) Sediments/sludge removed from the structure/s. c) Water level and quality in will not cause environmental harm to the surrounding environment. d) Retained structures will not cause environmental harm outside of the relevant tenure boundary, as demonstrated by long-term groundwater level and quality monitoring. 8.7 No formation of gully and/or rill erosion on retained infrastructure defined as "moderate" or "severe" as per LFA methodology 8.8 Risk assessment identified potential risks and controls/mitigation measures successfully implemented post closure in accordance with relevant guidelines and Australian Standards such as ISO31000 Risk Management. 8.9 Risks identified in risk assessment are low.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove 5.2 and 5.3 as they dont apply to Fairhill at all. Reply: done