## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 203
Commencement of first milestone: <insert milestone reference> |  |  |  | 2030-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10
Cumulative area available (ha) | 203 | 203 | 203
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4
RM5
RM6 | 203 | 203
RM7 |  |  | 203
RM8
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Infrastructure for Decommissioning
Total rehabilitation area size (ha) |  |  |  | 203
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2040 RM1
PMLU |  |  |  | Cattle Grazing
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Cumulative area available (ha) | 203 | 203 | 203 | 203 | 203 | 203 | 203 | 203
Milestone completed by | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10 | 2080-12-10
Milestone Reference | 2045-12-10: Cumulative area achieved (ha)
RM1 | 2045-12-10: 203
RM2 | 2050-12-10: 203
RM3 | 2055-12-10: 203
RM4 | 2055-12-10: 203
RM5 | 2060-12-10: 203; 2065-12-10: 203
RM6 | 2070-12-10: 203; 2075-12-10: 203
RM7 | 2080-12-10: 203
RM8
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Infrastructure to be Retained
Total rehabilitation area size (ha) |  |  |  | 42
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2040 RM2
PMLU |  |  |  | Cattle Grazing
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 42 | 42 | 42 | 42 | 42 | 42 | 42
Milestone completed by | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2 | 42
RM3 |  | 42
RM4 |  |  | 42
RM5 |  |  | 42 | 42
RM6 |  |  |  |  | 42 | 42
RM7 | [6 empty] | 42
RM8
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Landform Embankment
Total rehabilitation area size (ha) |  |  |  | 36
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2025 RM3
PMLU |  |  |  | Woodland Habitat
Date area is available | 2025-12-10 | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 31 | 31 | 34 | 34 | 36 | 36 | 36 | 36 | 36 | 36
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2030-12-10: Cumulative area achieved (ha)
RM1
RM2
RM3 | 2030-12-10: 31; 2035-12-10: 34; 2040-12-10: 34; 2045-12-10: 36
RM4 | 2035-12-10: 34; 2040-12-10: 34; 2045-12-10: 36
RM5 | 2035-12-10: 31; 2040-12-10: 34; 2045-12-10: 34; 2050-12-10: 36; 2055-12-10: 36
RM6 |  |  |  | 31 | 34 | 34 | 36 | 36 | 36
RM7
RM8 | 2060-12-10: 31; 2065-12-10: 34; 2070-12-10: 34; 2075-12-10: 36
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Waste Rock Dumps and Topsoil Dumps (PMLU Woodland)
Total rehabilitation area size (ha) |  |  |  | 569
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2035 RM3
PMLU |  |  |  | Woodland Habitat
Date area is available | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 35 | 569 | 569 | 569 | 569 | 569 | 569 | 569
Milestone completed by | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2040-12-10: Cumulative area achieved (ha)
RM1
RM2
RM3 | 2040-12-10: 35
RM4 | 2045-12-10: 569
RM5 | 2045-12-10: 35; 2050-12-10: 569; 2055-12-10: 569
RM6 | 2055-12-10: 35; 2060-12-10: 569; 2065-12-10: 569; 2070-12-10: 569
RM7
RM8 | 2070-12-10: 35; 2075-12-10: 569
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Waste Rock Dumps and Topsoil Dumps (PMLU Cattle Grazing)
Total rehabilitation area size (ha) |  |  |  | 1056
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2030 RM3
PMLU |  |  |  | Cattle Grazing
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 304 | 790 | 1029 | 1056 | 1056 | 1056 | 1056 | 1056 | 1056
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2035-12-10: Cumulative area achieved (ha)
RM1
RM2
RM3 | 2035-12-10: 304; 2040-12-10: 790; 2045-12-10: 1029; 2050-12-10: 1056
RM4 | 2035-12-10: 184; 2040-12-10: 587; 2045-12-10: 1029; 2050-12-10: 1056
RM5 | 2040-12-10: 304; 2045-12-10: 790; 2050-12-10: 1029; 2055-12-10: 1056
RM6 | 2050-12-10: 304; 2055-12-10: 790; 2060-12-10: 1029; 2065-12-10: 1056
RM7 | 2060-12-10: 304; 2065-12-10: 790; 2070-12-10: 1029; 2075-12-10: 1056
RM8
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Permanent Watercourse
Total rehabilitation area size (ha) |  |  |  | 45
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2030 RM6
PMLU |  |  |  | Watercourse
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10
Cumulative area available (ha) | 45 | 45 | 45
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4
RM5
RM6 | 45 | 45
RM7
RM8
RM9 |  |  | 45
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Infrastructure for Decommissioning (Riparian Buffer)
Total rehabilitation area size (ha) |  |  |  | 68
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2039 RM1
PMLU |  |  |  | Woodland Habitat
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Cumulative area available (ha) | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68
Milestone completed by | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10 | 2080-12-10
Milestone Reference | 2045-12-10: Cumulative area achieved (ha)
RM1 | 2045-12-10: 68
RM2 | 2050-12-10: 68
RM3 | 2050-12-10: 68
RM4 | 2055-12-10: 68
RM5 | 2060-12-10: 68
RM6 | 2065-12-10: 68; 2070-12-10: 68; 2075-12-10: 68
RM7
RM8 | 2080-12-10: 68
RM9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
New Chum Creek Diversion Disturbance
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | New Chum Creek Diversion Disturbance
Total rehabilitation area size (ha) |  |  |  | 2.6
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2025 RM3
PMLU |  |  |  | Watercourse
Date area is available | 2025-12-10 | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10
Cumulative area available (ha) | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3 | 2.6
RM4 |  | 2.6
RM5 |  | 2.6 | 2.6
RM6 |  |  |  | 2.6 | 2.6 | 2.6
RM7
RM8
RM9 | [6 empty] | 2.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final void being pit lake, low wall spoil, end wall, fence and bund and highwall
Total size (ha) |  |  |  | 316
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2040 MM1
NUMA |  |  |  | No use
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10
Cumulative area available (ha) | 316 | 316 | 316
Milestone completed by | 2045-10-12 | 2050-12-10 | 2055-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 316
MM2 |  | 316
MM3 |  |  | 316
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) Services with no beneficial PMLU re-use are disconnected and decommissioned. b) All buildings with no beneficial PMLU re-use are demolished and removed. c) All mine roads and access tracks with no beneficial PMLU are removed. d) All pipelines with no beneficial PMLU are drained, and removed. e) All waste removed from site. f) Mine water dams with no beneficial PMLU are decommissioned. g) All exploration drill holes have been rehabilitated in accordance with the eligibility criteria and standard conditions for exploration and mineral development projects – V2 (EHP, 2016).
RM2 | Identification and remediation of contaminated land | a) Contaminated land investigation completed by a suitability qualified person (SQP)1 in accordance with the Environmental Protection Act (1994) including: I. Contaminated and hazardous material either remediated in-situ or removed/transported to an approved landfill for disposal and waste tracking information recorded and submitted. II. Validation testing confirms that contaminated and hazardous materials have been removed or remediated successfully. III. Contaminated land assessment indicates that no contamination unsuitable for the post-mining land use remains or is occurring. IV. If required, a site investigation report including a site suitability statement must be prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act. V. A Site suitability statement from a SQP confirms the uses or activities for which the land is suitable, aligns to the approved PMLUs for the site. 1 Suitability qualified person (SQP): for performing a regulatory function under chapter 7, part 8 (Contaminated Land) of the EP Act or another function prescribed under a regulation, means a person who— (a) has qualifications and experience relevant to performing the function; and (b) if a regulation prescribes an organisation for this paragraph—is a member of the organisation
RM3 | Landform Establishment | All rehabilitation areas a) Engineering and design plans including drainage are developed by an AQP and finalised b) Bulk earthworks to achieve required landform and slopes are complete. c) Erosion and sediment control systems are designed by an AQP, installed, and fit for purpose. Cattle grazing (RA2, RA3, RA6) d) Landforms reshaped with maximum 15% slope e) Landforms design is assessed by an AQP as being geotechnically stable with a factor of safety ≥1.5 unless an alternative is justified by an AQP. f) Retained dams are safe for stock access and have vegetated bank Woodland Habitat PMLU (RA4, RA5, RA8) g) Landforms reshaped with maximum 25% slopes h) Areas >15% to be assessed by an AQP as being stable long term, with rock mulch applied as required i) Landforms design is assessed by an AQP as being geotechnically stable with a factor of safety ≥1.5 unless an alternative is justified by an AQP j) Rock mulch thickness placed as required based on final slope and iterative waste rock characterisation and erosion assessments Watercourse (RA9) k) Updated hydraulic flood modelling using drainage designs l)Hazard Assessment conducted to verify safety hazards are not significantly different to surrounding unmined landscapes subject to the same land use.
RM4 | Surface Preparation | a) Growth medium placed at a minimum depth of 100mm b) An assessment of growth media characteristics is completed by an AQP that identifies amelioration and other treatments required to achieve the following primary growth media quality targets^: c) Growth medium to meet the following suitability targets: - Cation exchange capacity of above 14 meq/100g for clays and 6 meq/100g for loams. -Major macronutrient concentrations in root zone (0–0.3m): ° Total nitrogen (N) above 1000 mg/kg. ° Available phosphorus (P) above 10 mg/kg. ° Potassium (K) above 160 mg/kg. °Total organic carbon (TOC) above 1%. - pHw range of soil is between 6.0–9.0 to at least 0.3m. - Primary growth media (0–0.3m) salinity (EC1:5) is less than 0.75dS/m. d) Rip along contour ^Primary growth media quality targets: criteria provided as a post-ameliorant target. Initial soil analysis values may be outside of these ranges; however they must be achieved where that is a requirement of this PRCP schedule.
RM5 | Revegetation | Cattle Grazing (RA2, RA3, RA6) a) Complete seeding in accordance with target species of 3P (perennial, palatable and productive) and rate as per the PRCP Schedule Appendix 1: Grazing species and seeding rate. b) Primary growth media quality targets listed in RM4(c) are achieved based on a number of representative samples as determined by AQP Woodland Habitat (RA4, RA5) c) Completed seeding using a selection of species outlined in PRCP Schedule Appendix 2: Recommended species to be established for woodland habitat at RA4 and RA5 d) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates for dominant tree species (5kg/ha), mid-storey species (5kg/ha), and groundcover species (5kg/ha). e) Primary growth media quality targets listed in RM4(c) are achieved based on a number of representative samples as determined by AQP Woodland Habitat (RA8) f) Complete seeding using a selection of species and sowing rates outlined in PRCP Schedule Appendix 3: Recommended species and sowing rates to be established for woodland habitat at RA8 g) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates as established in PRCP Schedule Appendix 3 h) Primary growth media quality targets listed in RM4(c) are achieved based on a number of representative samples as determined by AQP Watercourse (RA9) i) Completed seeding using a selection of species outlined in PRCP Schedule Appendix 4: Recommended species to be established for watercourse at RA9 j) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates for upper bank (5kg/ha), mid bank (5kg/ha), and lower bank (5kg/ha) k) Primary growth media quality targets listed in RM4(c) are achieved based on a number of representative samples as determined by AQP.
RM6 | Achievement of stable condition | a) Final landform for RA1, RA2, RA3, RA6 has achieved a geotechnically stable condition with minimum ≥ 1.5 factor of safety and slopes ≤15% b) Final landform for RA4, RA5, RA8 has achieved a geotechnically stable condition with minimum ≥ 1.5 factor of safety unless an alternative is justified by an AQP and slopes ≤25% c) Evidence that erosion for RA1, RA2, RA3, RA4, RA5, RA6 and RA8 is classified as ‘minor’ ‘moderate’ or ‘severe’ as defined by Appendix 7: Erosion classification framework. d) Assessment report completed by an AQP certifying that the diversion (RA7 and RA9) is operating in accordance with, DNRME Guideline: Works that interfere with water in a watercourse for a resource activity — watercourse diversions under the Water Act 2000 (OSW/2019/4599) criteria and is in a stable condition. e) Geomorphic index (IDC method) used to verify that Rehabilitation for RA7 and RA9 is erosionally stable with scores greater or equal to upstream or downstream values (IDC method) f) Receiving water quality must be monitored at the locations specified in the Appendix 8: Receiving Water Upstream Background Sites and Downstream Monitoring Points for a period of at least three (3) years. g) Surface water quality monitoring required by RM7(f) must be monitored for the following parameters. • pH • EC • turbidity • As • Mb • Se • total recoverable hydrocarbons (C6–C9) • total recoverable hydrocarbons (C10–C36) h) The downstream receiving water quality monitoring points (MP2 and MP3) must not be significantly higher (>15%) when compared to the upstream value at MP4 and MP5 for the water quality parameters specified in RM6(g) i) Groundwater bores specified in Table I2 in EPML00963013 must be monitored for quality and levels at the location specified in Appendix 9: Ground water monitoring points for a period of at least three years with monitoring intervals ≥ 4 weeks and ≤ 16 weeks. j) Ground water quality results for compliance bores must remain within the 95th percentile of the site-specific limits detailed in Table I2 of EPML00963013 for a minimum of 36 samples taken at intervals specified in RM6(i). k) Groundwater levels for compliance bores specified in Table I1 EPML00963013 must not exceed a drawdown ≥2m from the baseline RL level. l) Water quality in retained dams must not exceed the trigger values for livestock drinking water defined in ANZECC & ARMCANZ 2000
RM7 | Achievement of cattle grazing PMLU | a) Certification by an AQP that pasture meets pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per “Stocktake: Balancing Supply and Demand” (Developed by FutureBeef – futurebeef.com.au), as provided in Appendix 5: Pasture condition assessment, including: 1. Preferred pasture species (3P grasses^) diversity ≥2 species 2. Preferred pasture (3P) % DM yield ≥10% 3. Annual grass DM yield % <70% 4. Grasses other than 3P grasses and other weeds % DM yield <80% 5. Crown cover (3P grasses) – at worst, moderate to low density and some plants dead b) Leucaena stem density <250 stems >2m per ha (1 per 40m2) c) Certification from an AQP that rehabilitation is resilient to fire and grazing pressures. d) Land suitability class ≤3 or not different from pre-mining if ≥4^ ^Assessment completed in accordance with LSA Framework for Open-Cut Coal Mine Rehabilitation 2018 (A ruleset for land suitability assessment of sustainable beef cattle grazing on land rehabilitated after open-cut coal mining in the Bowen Basin Queensland) unless otherwise agreed in writing between the administering authority and the environmental authority holder.
RM8 | Achievement of Woodland habitat PMLU | a) A BioCondition assessment at RA4, RA5 and RA8 and is completed by an AQP using the methodology outlined in the latest version of the Queensland Herbarium’s BioCondition Assessment Manual. b) The BioCondition assessment required by RM8(a) at RA5 and RA6 demonstrates achievement of the PRCP Benchmark for each assessable attribute for the relevant regional ecosystem as per Appendix 6: Representative RE benchmark criteria for woodland habitat rehabilitation at RA4 and RA5 c) The BioCondition assessment required by RM8(a) at RA8 demonstrates achievement of the PRCP benchmark for each assessable attribute for the relevant regional ecosystem as per Appendix 6: Representative RE benchmark criteria for woodland habitat rehabilitation at RA8
RM9 | Achievement of Watercourse PMLU | a) Riparian vegetation condition is greater or equal to upstream or downstream values using Riparian Vegetation Index (IDC method)
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of structural stability | a) Rehabilitation is geotechnically stable and achieves a minimum factor of Safety of >1.25 as determined by an AQP
MM2 | Achievement of surface requirements | a) Safety bund is constructed, where required, at the geotechnical set-back distance b) Fencing erected around perimeter of safety bund, where required c) Warning signage placed along fence line, where required
MM3 | Achievement of sufficient improvement | a) Certification from an AQP that residual voids will not cause environmental harm to land, surface waters or any recognised groundwater aquifer b)Certification from an AQP that the residual voids are safe to humans and livestock
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## Appendix 3
Appendix 3: Recommended species to be established at the Woodland habitat at RA8

## Appendix 4
4

## Appendix 6
Appendix 6: Representative RE benchmark criteria for Woodland Habitat at RA5 and RA6
Appendix 6: Representative RE benchmark criteria for Woodland Habitat at RA8

## Appendix 8
Appendix 8: Receiving Water Upstream Background Sites and Downstream Monitoring Points

## Appendix 9
Appendix 9: Ground water Monitoring Points