## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 203.2
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2030 RM6
PMLU |  |  |  | Cattle Grazing
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10
Cumulative area available (ha) | 203.2 | 203.2 | 203.2
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM6 | 203.2 | 203.2
RM7 |  | 203.2
RM8 |  |  | 203.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Infrastructure for Decommissioning
Total rehabilitation area size (ha) |  |  |  | 248.2
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2040 RM1
PMLU |  |  |  | Cattle Grazing
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 248.2 | 248.2 | 248.2 | 248.2 | 248.2 | 248.2 | 248.2
Milestone completed by | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2045-12-10: Cumulative area achieved (ha)
RM1 | 2045-12-10: 248.2
RM2 | 2050-12-10: 24.8
RM3 | 2055-12-10: 248.2
RM4 | 2060-12-10: 248.2
RM5 | 2060-12-10: 248.2
RM6 | 2065-12-10: 248.2
RM7 | 2065-12-10: 248.2; 2070-12-10: 248.2
RM8 | 2075-12-10: 248.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Landform Embankment
Total rehabilitation area size (ha) |  |  |  | 35.5
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2025 RM6
PMLU |  |  |  | Woodland Habitat
Date area is available | 2025-12-10 | 2035-12-10 | 2040-12-10
Cumulative area available (ha) | 35.5 | 35.5 | 35.5
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM6 | 35.5
RM7 |  | 35.5
RM9 |  |  | 35.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Waste Rock Dumps and Topsoil Dumps (PMLU Woodland)
Total rehabilitation area size (ha) |  |  |  | 568
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2035 RM3
PMLU |  |  |  | Woodland Habitat
Date area is available | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 35 | 568 | 568 | 568 | 568 | 568 | 568 | 568
Milestone completed by | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2040-12-10: Cumulative area achieved (ha)
RM3 | 2040-12-10: 35; 2045-12-10: 568
RM4 | 2045-12-10: 35; 2050-12-10: 568
RM5 | 2045-12-10: 35; 2050-12-10: 568; 2055-12-10: 568
RM6 | 2055-12-10: 35; 2060-12-10: 568
RM7 | 2060-12-10: 35; 2065-12-10: 568; 2070-12-10: 568
RM9 | 2070-12-10: 35; 2075-12-10: 568
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Waste Rock Dumps and Topsoil Dumps (PMLU Cattle Grazing)
Total rehabilitation area size (ha) |  |  |  | 1023
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2030 RM3
PMLU |  |  |  | Cattle Grazing
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 304 | 790 | 890 | 1008 | 1023 | 1023 | 1023 | 1023 | 1023
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2035-12-10: Cumulative area achieved (ha)
RM3 | 2035-12-10: 304; 2040-12-10: 790; 2045-12-10: 890; 2050-12-10: 1008
RM4 | 2035-12-10: 7; 2040-12-10: 304; 2045-12-10: 790; 2050-12-10: 890; 2055-12-10: 1015
RM5 | 2035-12-10: 7; 2040-12-10: 304; 2045-12-10: 790; 2050-12-10: 890; 2055-12-10: 1015
RM6 | 8 | 15 | 304 | 790 | 890 | 1023
RM7 |  | 8 | 15 | 304 | 790 | 890 | 1023 | 1023
RM8 | 2055-12-10: 15; 2060-12-10: 304; 2065-12-10: 790; 2070-12-10: 890; 2075-12-10: 1023
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | New Chum Creek Diversion Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 44.7
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2030 RM6
PMLU |  |  |  | Watercourse
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10
Cumulative area available (ha) | 44.7 | 44.7 | 44.7
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM6 | 44.7 | 44.7
RM7 |  | 44.7
RM10 |  |  | 44.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Infrastructure for Decommissioning (Riparian Buffer)
Total rehabilitation area size (ha) |  |  |  | 51.5
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2025 RM1
PMLU |  |  |  | Woodland Habitat
Date area is available | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10
Cumulative area available (ha) | 7.5 | 9.8 | 34.2 | 51.5 | 51.5 | 51.5 | 51.5
Milestone completed by | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Milestone Reference | 2040-12-10: Cumulative area achieved (ha)
RM1 | 2040-12-10: 7.5
RM2 | 2045-12-10: 7.5
RM3 | 2045-12-10: 7.5
RM4 | 2045-12-10: 9.8; 2050-12-10: 17.3
RM5 | 2045-12-10: 9.8; 2050-12-10: 17.3
RM6 | 2050-12-10: 34.2; 2055-12-10: 51.5
RM7 | 2055-12-10: 34.2; 2060-12-10: 51.5; 2065-12-10: 51.5
RM9 | 2065-12-10: 34.2; 2070-12-10: 51.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
New Chum Creek Diversion Disturbance
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | New Chum Creek Diversion Disturbance
Total rehabilitation area size (ha) |  |  |  | 2.6
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2025 RM3
PMLU |  |  |  | Watercourse
Date area is available | 2025-12-10 | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10
Cumulative area available (ha) | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10
Milestone Reference | 2030-12-10: Cumulative area achieved (ha)
RM3 | 2030-12-10: 2.6
RM4 | 2035-12-10: 2.6
RM5 | 2035-12-10: 2.6; 2040-12-10: 2.6
RM6 | 2045-12-10: 2.6
RM7 | 2045-12-10: 2.6; 2050-12-10: 2.6
RM10 | 2055-12-10: 2.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final void being pit lake, low wall spoil, end wall, fence and bund and highwall
Total size (ha) |  |  |  | 316.2
Commencement of first milestone: <insert milestone reference> |  |  |  | 10/12/2040 MM1
NUMA |  |  |  | No use
Date area is available | 2040-12-10 | 2045-12-10 | 2050-12-10
Cumulative area available (ha) | 316.2 | 316.2 | 316.2
Milestone completed by | 2045-10-12 | 2050-12-10 | 2055-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 316.2
MM2 |  | 316.2
MM3 |  |  | 316.2
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) Services with no beneficial PMLU re-use are disconnected and decommissioned. b) All buildings with no beneficial PMLU re-use are demolished and removed. c) All mine roads and access tracks with no beneficial PMLU are removed. d) All pipelines with no beneficial PMLU are drained, and removed. e) All waste removed from site. f) Mine water dams with no beneficial PMLU are decommissioned. g) All exploration drill holes have been rehabilitated in accordance with the eligibility criteria and standard conditions for exploration and mineral development projects – V2 (EHP, 2016). h) Infrastructure required for the ongoing health and safety of operators, as defined by the Coal Mining Safety and Health Act 1999, is to be retained until deemed safe to remove.
RM2 | Identification and remediation of contaminated land | a) Contaminated land investigation completed by a suitability qualified person (SQP)1 in accordance with the Environmental Protection Act (1994) including: I. Contaminated and hazardous material either remediated in-situ or removed/transported to an approved landfill for disposal and waste tracking information recorded and submitted. II. Validation testing confirms that contaminated and hazardous materials have been removed or remediated successfully. III. Contaminated land assessment indicates that no contamination unsuitable for the post-mining land use remains or is occurring. IV. If required, a site investigation report including a site suitability statement must be prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act. V. A Site suitability statement from a SQP confirms the uses or activities for which the land is suitable, aligns to the approved PMLUs for the site. 1 Suitability qualified person (SQP): for performing a regulatory function under chapter 7, part 8 (Contaminated Land) of the EP Act or another function prescribed under a regulation, means a person who— (a) has qualifications and experience relevant to performing the function; and (b) if a regulation prescribes an organisation for this paragraph—is a member of the organisation
RM3 | Landform Establishment | All rehabilitation areas a) Engineering and design plans including drainage are developed by an AQP and finalised. b) All major earthworks completed, slopes and general reshaping and pushing/trimming completed to achieve final landform. c) Erosion and sediment control systems are installed, fit for purpose and verified by an AQP. d) Landforms are to be free draining. e) Where applicable, crests of rehabilitate landforms are to be bunded with designs informed by an AQP. Cattle grazing (RA1, RA2, RA5) f) Landforms reshaped to maximum 15% overall slope g) Landforms design is assessed by an AQP as being geotechnically stable with a factor of safety ≥1.5 unless an alternative is justified by an AQP. Woodland Habitat PMLU (RA3, RA4, RA7) h) Landforms reshaped with maximum 25% overall slope. i) Areas >15% overall to be assessed by an AQP as being stable long term, with rock mulch applied as required. j) Landforms design is assessed by an AQP as being geotechnically stable with a factor of safety ≥1.5 unless an alternative is justified by an AQP. k) Rock mulch thickness placed as required based on final slope and iterative waste rock characterisation and erosion assessments. Watercourse (RA6, RA8) l) Updated hydraulic flood modelling using drainage designs m) Hazard Assessment conducted to verify safety hazards are not significantly different to surrounding unmined landscapes subject to the same land use.
RM4 | Surface Preparation | a) Growth mediumdepth of at least 100mm placed on Grazing PMLU b) Growth mediumdepth of at least 100mm, mixed with fresh Permian overburden at a ration of 2-4 parts fresh Permian to 1 part topsoil placed on Woodland PMLU c) An assessment of growth media characteristics is completed by an AQP that identifies amelioration and other treatments required to achieve the following primary growth media quality targets, six months prior to progressive rehabilitation^ d) Growth medium to meet the following suitability targets: - Cation exchange capacity of above 14 meq/100g for clays and 6 meq/100g for loams. - Major macronutrient concentrations in root zone (0–0.3m): - Total nitrogen (N) above 1000 mg/kg. - Available phosphorus (P) above 10 mg/kg. - Potassium (K) above 160 mg/kg. - Total organic carbon (TOC) above 1%. - pH range of soil is between 6.0–9.0 to at least 0.3m. - Primary growth media (0–0.3m) salinity (EC1:5) is less than 0.75dS/m. e) Deep rip at least 500mm into soil/subsoil profile along contour of slopes. f) The surface and groundwater monitoring network, including, but not limited to, to those locations identified in Appendix 8 and Appendix 9, is installed and monitoring underway. ^Primary growth media quality targets: criteria provided as a post-ameliorant target. Initial soil analysis values may be outside of these ranges; however they must be achieved where that is a requirement of this PRCP schedule.
RM5 | Revegetation | Cattle Grazing (RA1, RA2, RA5) a) Complete seeding in accordance with target species of 3P (perennial, palatable and productive) and rate as per the PRCP Schedule Appendix 1: Recommended species to be established in Grazing PMLU. b) Primary growth media quality targets listed in RM4(e) are achieved based on a number of representative samples as determined by AQP. Woodland Habitat (RA3, RA4) c) Completed seeding using a selection of species outlined in Appendix 2: Recommended species to be established for woodland habitat at RA3 and RA4 d) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates for dominant tree species (5kg/ha), mid-storey species (5kg/ha), and groundcover species (5kg/ha). e) Primary growth media quality targets listed in RM4(e) are achieved based on a number of representative samples as determined by AQP Woodland Habitat (RA7) f) Complete seeding using a selection of species and sowing rates outlined in Appendix 3: Recommended species and sowing rates to be established for woodland habitat at RA7 g) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates as established in Appendix 3: Recommended species to be established at the Woodland habitat (RA7) h) Primary growth media quality targets listed in RM4(e) are achieved based on a number of representative samples as determined by AQP Watercourse (RA6 & RA8) i) Completed seeding using a selection of species outlined in Appendix 4: Recommended species to be established for watercourse PMLU at RA8 j) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates for upper bank (5kg/ha), mid bank (5kg/ha), and lower bank (5kg/ha) k) Primary growth media quality targets listed in RM4(e) are achieved based on a number of representative samples as determined by AQP.
RM6 | Achievement of surface requirements | All Rehabilitation Areas a) Presence of rocks, logs or other effective erosion control cover is limited to 30% of total vegetative groundcover. b) Weed presence is less than 10% of total vegetative groundcover confirmed by an AQP in annual monitoring. c) Evidence that erosion for grazing and woodland PMLU does not exceed the classification of 'moderate' or ‘severe’ as defined by Appendix 7: Erosion classification framework. d) Surface water runoff is non-polluting to receiving waters and complies with Appendix 10: Surface Water Quality Characteristics. Cattle Grazing (RA1, RA12, RA5) f) Final landform for grazing PMLU has achieved a geotechnically stable condition with minimum ≥ 1.5 factor of safety and slopes ≤15% g) Minimum 80% established and persistent vegetative groundcover for Grazing PMLU Woodland Habitat (RA3, RA4, RA7) g) Final landform for woodland PMLU has achieved a geotechnically stable condition with minimum ≥ 1.5 factor of safety unless an alternative is justified by an AQP and slopes ≤25% h) Minimum 50% established and persistent vegetative groundcover for Woodland PMLU (RA3) Embankment i) Minimum 50% established and persistent vegetative groundcover for Woodland PMLU (RA4 & RA7). k) Erosion monitoring of the embankment is to be undertaken pre and post wet season until minimum 50% vegetative cover is achieved Diversion & Watercourse (RA6, RA8) k) Geomorphic index (IDC method) used to verify that Rehabilitation for RA6 and RA8 is erosionally stable with scores greater or equal to upstream or downstream values (IDC method)
RM7 | Achievement of stable condition | All rehabilitation areas a) No evidence of erosion classified as moderate or severe as defined by Appendix 7: Erosion Classification framework b) Surface water runoff is non-polluting to receiving waters and complies with Appendix 10: Surface Water Quality Characteristics. c) Surface water quality results monitored within 48 hours of flow at, but not limited to location specified in Appendix 8: Receiving Water Upstream Background Sites and Downstream Monitoring Points, must not exceed the limits in Appendix 10: Surface Water Quality Characteristics, for a minimum of five (5) consecutive years. d) If the surface water quality exceeds RM7(e), the applicable upstream site must be compared to the downstream site result. e) Groundwater quality should be monitored quarterly at, but not limited to, monitoring bores listed in Appendix 9: Groundwater Monitoring Locations of the schedule, for quality characteristics listed in Appendix 11: Groundwater Quality Limits of the schedule and all results comply with limits of the schedule for a minimum of five (5) consecutive years. f) Upon completion of five (5) years of consecutive monitoring, a review of groundwater data is to be completed by an AQP to inform milestone criteria amendments. g) Groundwater levels for compliance bores specified in Appendix 11: Groundwater Quality Limits must not exceed a drawdown ≥2m from background excluding changes from pumping of licensed bores. h) Removal of any bunds used to initially control runoff from slopes, once target vegetation has been achieved and erosion levels are deemed acceptable by an AQP. Diversion & Watercourse (RA6, RA8) i) Assessment report completed by an AQP certifying that the diversion (RA6 and RA8) is operating in accordance with, DNRME Guideline: Works that interfere with water in a watercourse for a resource activity — watercourse diversions under the Water Act 2000 (OSW/2019/4599) criteria and is in a stable condition. j) Geomorphic index (IDC method) used to verify that Rehabilitation for RA6 and RA8 is erosionally stable with scores greater or equal to upstream or downstream values (IDC method)
RM8 | Achievement of cattle grazing PMLU | a) Certification by an AQP that pasture meets pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per “Stocktake: Balancing Supply and Demand” (Developed by FutureBeef – futurebeef.com.au), as provided in Appendix 5: Pasture condition assessment, including: - Preferred pasture species (3P grasses^) diversity ≥2 species - Preferred pasture (3P) % DM yield ≥10% - Annual grass DM yield % <70% - Grasses other than 3P grasses and other weeds % DM yield <80% - Crown cover (3P grasses) – at worst, moderate to low density and some plants dead b) Leucaena stem density <250 stems >2m per ha (1 per 40m2) c) Certification from an AQP that rehabilitation is resilient to fire and grazing pressures. d) Land suitability class ≤3 or not different from pre-mining if ≥4^ ^Assessment completed in accordance with LSA Framework for Open-Cut Coal Mine Rehabilitation 2018 (A ruleset for land suitability assessment of sustainable beef cattle grazing on land rehabilitated after open-cut coal mining in the Bowen Basin Queensland) unless otherwise agreed in writing between the administering authority and the environmental authority holder.
RM9 | Achievement of Woodland habitat PMLU | a) A BioCondition assessment at RA4, RA5 and RA8 and is completed by an AQP using the methodology outlined in the latest version of the Queensland Herbarium’s BioCondition Assessment Manual. b) The BioCondition assessment required by RM9(a) at RA3 and RA4 demonstrates achievement of the PRCP Benchmark for each assessable attribute for the relevant regional ecosystem as per Appendix 6: Representative RE benchmark criteria for woodland habitat rehabilitation at RA3 and RA4 c) The BioCondition assessment required by RM9(a) at RA8 demonstrates achievement of the PRCP benchmark for each assessable attribute for the relevant regional ecosystem as per Appendix 6: Representative RE benchmark criteria for woodland habitat rehabilitation at RA7
RM10 | Achievement of Watercourse PMLU | a) Riparian vegetation condition is greater or equal to upstream or downstream values using Riparian Vegetation Index (IDC method) b) Surface water runoff is non-polluting to receiving waters and complies with Appendix 10: Surface Water Quality Characteristics.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria2 | Column1
MM1 | Achievement of structural stability | a) Certification by an AQP, that final voids are stable, including: i) Certification that the highwall and end wall (where not backfilled) have: - overall slope angle 65° void highwall and end wall in competent (unweathered) rock; - overall slope angle 45° highwall and end wall in less competent (weathered) rock; and ii) Geotechnically stable for the foreseeable future.
MM2 | Achievement of surface requirements | a) Safety bund setback distance is in accordance with a calculated geotechnical FoS of ≥1.5 but a minimum of 15m and maximum of 40m. b) The safety bund is constructed in accordance with engineering requirements including: - constructed from non-weathered dumped rockfill; - a minimum 2 m in height; - a minimum of 7 m base width; and - 1 in 1.5 batters. c) Bunding confirmed to be geotechnically stable by an AQP. d) Appropriate signage placed every 100m of the perimeter of the void to clearly identify and convey the purpose (e.g. EP Act 1994 Non- Use Management Area No Entry). e) Installation of fencing completed for the residual void management areas to limit human and livestock access.
MM3 | Achievement of sufficient improvement | a) Certification by an AQP, that final void is stable, including: i) certification that the highwall and end wall (where not backfilled) have: - Overall slope angle 65° for void highwall and end wall in competent (unweathered) rock; - Overall slope angle 45° for highwall and end wall in less competent (weathered) rock; ii) geotechnically stable for the foreseeable future; iii) Evidence that erosion does not exceed the classification of 'moderate' or ‘severe’ as defined by Appendix 7: Erosion classification framework and will not cause instability; iv) Monitoring and mitigation must occur following rainfall events greater than 0.1% AEP v) drainage measures and structures have been appropriately established and are directing overland flow away from the highwall edge; and vi) erosion and sediment control measures have been installed and are operating as per design. b) Certification by an AQP that the residual void is: i) a single residual void area of 316 ha; and ii) a maximum depth of 145 m c) Certification from an AQP, that the safety bund and fencing are present and functional. d) Groundwater quality should be monitored quarterly at, but not limited to, monitoring bores listed in Appendix 9: Groundwater Monitoring Locations of the schedule, for quality characteristics listed in Appendix 11: Groundwater Quality Limits of the schedule and all results comply with limits of the schedule for a minimum of five (5) consecutive years. e) Upon completion of five (5) years of consecutive monitoring, a review of groundwater data is to be completed by an AQP to inform milestone criteria amendments. f) Groundwater levels for compliance bores specified in Appendix 11: Groundwater Quality Limits must not exceed a drawdown ≥2m from the background excluding changes from pumping of licenced bores. g) Final void walls confirmed to drain internally to the final void. h) Certification from an AQP that water level in each residual void will not cause environmental harm to the surrounding environment, and the voids act as groundwater sinks to the receiving groundwater environment. i) Certification from an AQP that evidence, based on up-to-date groundwater modelling, that the final void lake will not overflow nor potentially contaminate any other surface water bodies. j) Risks from the void is ALARP in accordance with the latest version of AS/NZS ISO 31000:2009 Risk Management and certified by an AQP.
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## Appendix 4
4

## Appendix 3
Appendix 3: Recommended species to be established at the Woodland habitat at RA7

## Appendix 6
Appendix 6: Representative RE benchmark criteria for Woodland Habitat at RA3 and RA4
Appendix 6: Representative RE benchmark criteria for Woodland Habitat at RA7

## Appendix 8
Appendix 8: Receiving Water Upstream Background Sites and Downstream Monitoring Points
Monitoring Point (MP) | Receiving Water Location Description | Latitude (DD GDA2020) | Latitude (DD GDA2020)
Upstream Background Monitroing Points
MP4 | New Chum Creek – upstream of the diversion | -22.0526 | 148.2678
MP5 | Isaac River – 4760m upstream of the confluence of New Chum Creek and Isaac River | -22.0926 | 148.2392
Downstream Monitoring Points
MP2 | New Chum Creek – downstream of the diversion | -22.1061 | 148.2711
MP3 | Isaac River – 3000m downstream of the confluence of New Chum Creek and Isaac River | -22.1246 | 148.2963
Creek DiversionMonitoring
NCC - DIV1 | Diversion offtake | -22.0667 | 148.2647
NCC-DIV2 | Diversion offtake | -22.0727 | 148.2693
NCC-DIV3 | Diversion offtake | -22.0808 | 148.2685
NCC-DIV4 | Diversion offtake | -22.0855 | 148.2671
NCC-D1 | Downstream monitroing point | -22.095 | 148.2627
NCC-D2 | Downstream monitroing point | -22.0962 | 148.2642
NCC-D3 | Downstream monitroing point | -22.0969 | 148.2658
NCC-D4 | Downstream monitroing point | -22.0984 | 148.266
NCC-U1 | Upstream monitoring point | -22.0553 | 148.2661
NCC-U2 | Upstream monitoring point | -22.0564 | 148.2655
NCC-U3 | Upstream monitoring point | -22.0577 | 148.2651
NCC-U4 | Upstream monitoring point | -22.059 | 148.2637

## Appendix 9
Appendix 9: Ground water Monitoring Points
Monitoring Bore | Hydrogeological unit | Surface RL (mAHD) | Location (GDA2020)
|  |  | Easting | Northing
Interpretation Bores
OBS4 (MP11) | Rewan Group | 229.3 | -22.0396 | 148.2287
Compliance Bores
OBS1 (MP7) | RCM Interburden | 193.18 | -22.1068 | 148.2625
OBS2 (MP8) | RCM Interburden | 215.7 | -22.0805 | 148.2748
OBS5 (MP12) | Alluvium | 194.4 | -22.0839 | 148.2229
OBS8 | Tertiary Unconsolidated Sand | 192.94 | -22.1171 | 148.2785
OBS10 | Leichart | 194.36 | -22.0925 | 148.2398
OBS15 | Alluvium/Tertiary | 199.7 | -22.091 | 148.2387
OBS16 | Permian Coal Measures (Leichardt Seam) | 199.77 | -22.0917 | 148.2398
OBS17 | Alluvium/Tertiary | 193.53 | -22.0992 | 148.2491
OBS18 | Permian Coal Measures (Vermont Seam) | 193.93 | -22.099 | 148.2489
OBS19 | Base of Alluvium/Tertiary sediments | 194.14 | -22.1069 | 148.2604

## Appendix 10
Appendix 10: Surface Water Quality Parameters
Quality Characteristics (units) | Limit | Comment on Limit
pH | 6.5-8.5 | WQO for Upper Isaac River catchment waters applied
Electrical Conductivity | 720 | WQO for Upper Isaac River catchment waters applied
Turbidity (NTU) | 50 | WQO for Upper Isaac River catchment waters applied
Sulphate (mg/L) | 25 | WQO for Upper Isaac River catchment waters applied
Aluminium - dissolved (µg/L) | 55 | ANZG 2018
Arsenic - dissolved (µg/L) | 13 | ANZG 2018
Cadmium - dissolved (µg/L) | 0.2 | ANZG 2018
Chromium - dissolved (µg/L) | 1 | ANZG 2018
Copper - dissolved (µg/L) | 2 | ANZG 2018 | ANZG 2018 value is 1.4
Iron - dissolved (µg/L) | 300 | ANZG 2018
Lead - dissolved (µg/L) | 4 | ANZG 2018
Mercury - dissolved (µg/L) | 0.2 | ANZG 2018
Nickel - dissolved (µg/L) | 11 | ANZG 2018
Zinc - dissolved (µg/L) | 8 | ANZG 2018
Boron - dissolved (µg/L) | 370 | ANZG 2018
Cobalt - dissolved (µg/L) | 90 | ANZG 2018 | ANZG 2018 value is 1.4
Manganese - dissolved (µg/L) | 1900 | ANZG 2018
Molybdenum - dissolved (µg/L) | 34 | ANZG 2018
Selenium - dissolved (µg/L) | 10 | ANZG 2018 | Should be 5 - ANZG 2018 recommends that the 99% species protection level DGV is used for slightly to moderately disturbed systems
Silver - dissolved (µg/L) | 1 | ANZG 2018
Uranium - dissolved (µg/L) | 1 | ANZG 2018
Vanadium - dissolved (µg/L) | 10 | ANZG 2018
Ammonia - dissolved (µg/L) | 900 | No data, therefore, ANZG 2018 applies.
Nitrate - dissolved (µg/L) | 1100
Petroleum hydrocarbons (C6-C9) | 20 | Limit of reporting (LoR)
Petroleum hydrocarbons (C10-C36) | 100 | Limit of reporting (LoR)
Fluoride (total) (µg/L) | 2000 | WQO for Stock Protection applied
Major ions (mg/L) Calcium, chloride, potassium, magnesium, sodium, bicarbonate, carbonate | For interpretation purposes only
Hardness (mg/L) | For interpretation purposes only
Notes: - All metals and metalloids must be measured as ‘dissolved’ (from analysis of a field filtered sample) and total (unfiltered). - Limits for metals and metalloids apply to dissolved results. - LOR – typical reporting for method stated. ICPMS/CV FIMS – analytical method required to achieve LOR. - ANZG (2018) Aquatic ecosystem protection for moderately disturbed system (95% protection)

## Appendix 11
Appendix 11: Groundwater Quality Limits
Quality Characterisitic | Units | Trigger Levels |  |  |  |  | Comment on Limit
|  | OBS4 (MP11) | OBS1 (MP7) | OBS2 (MP8) | OBS5 (MP12) | OBS10
Water Level | RL | Monitored for interpretative reasons only – no triggers apply | Greater than 2m from background excluding changes from pumping of licenced bores
pH | pH units |  | 6.5-8.5 | 6.5-8.5 | 6.5-8.5 | 6.5-8.7 | Adopted from site specific trigger level from LOD, excluding OBS10 which is site specific trigger
Eletrical Conductivity | µS/cm |  | 16000 | 16000 | 34350 | 16000 | Adopted from site specific trigger level from LOD
Sulfate | mg/L |  | 398 | 398 | 1860 | 398 | Adopted from site specific trigger level from LOD
Dissolved Aluminium | mg/L |  | 0.055 | 0.055 | 0.07 | 0.066 | Adopted from site specific trigger level from LOD
Dissolved Antimony | mg/L |  | 0.009 | 0.009 | 0.009 | 0.009 | ANZG 2018
Dissolved Arsenic | mg/L |  | 0.013 | 0.013 | 0.013 | 0.013 | ANZG 2018
Dissolved Iron | mg/L |  | 1.3 | 2 | 1.4 | 0.7 | Adopted from site specific trigger level from LOD
Dissolved Mercury | mg/L |  | 0.0006 | 0.006 | 0.006 | 0.006 | ANZG 2018
Dissolved Molybdenum | mg/L |  | 0.034 | 0.034 | 0.034 | 0.034 | ANZG 2018
Dissovled Selenium | mg/L |  | 0.011 | 0.011 | 0.011 | 0.011 | Adopted from site specific trigger level from LOD
Dissolved Silver | mg/L |  | 0.001 | 0.001 | 0.001 | 0.001 | ANZG 2018
TPH C6-C10 | µg/L |  | 20 | 26 | 26 | 20 | ANZG 2018, excluding OBS2 and OBS5 which are site specific triggers
TPH >C10-C40 | µg/L |  | 100 | 100 | 226 | 100 | ANZG 2018, excluding OBS5 which are site specific trigger
Notes: - All metals and metalloids must be measured as ‘dissolved’ (from analysis of a field filtered sample) and total (unfiltered). - Limits for metals and metalloids apply to dissolved results. - LOR – typical reporting for method stated. ICPMS/CV FIMS – analytical method required to achieve LOR. - ANZG (2018) Aquatic ecosystem protection for moderately disturbed system (95% protection)