## Instructions
ABN 46 640 294 485
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form or ESR/2025/7103 (Word template) must be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.02 • Effective: 3 Dec 2025

## Callide RA1
Callide
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA1
Relevant activities |  |  | Existing Rehabililitation - Pre 1998 at: Dunn Creek (42ha) Trap Gully (28ha) The Hut (31ha) Boundary Hill (115ha)
Total rehabilitation area size (ha) |  |  | 216
Commencement of first milestone: RM6 |  |  | 2026-05-08
PMLU |  |  | Bushland
Date area is available | 2026-05-08 | 2026-12-10
Cumulative area available (ha) | 216 | 216
Milestone completed by | 2026-12-10 | 2030-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 6 - Achievement of surface requirements (Bushland) | 216
RM 9 - Achievement of Bushland PMLU to a stable condition |  | 216
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Callide RA2
Callide Mine
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Bushland - Existing Rehabililitation - Post 1998 Dunn Creek (127+68ha) The Hut (79+84ha) Boundary Hill (126+124ha)
Total rehabilitation area size (ha) |  |  |  | 608
Commencement of first milestone: RM6 |  |  |  | 2026-05-08
PMLU |  |  |  | Bushland
Date area is available | 2026-05-08 | 2030-12-10 | 2035-12-10
Cumulative area available (ha) | 332 | 608 | 608
Milestone completed by | 2030-12-10 | 2035-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 6 - Achievement of surface requirements (Bushland) | 332 | 608
RM 9 - Achievement of Bushland PMLU to a stable condition |  | 332 | 608
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Dunn Creek RA2
Dunn Creek
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Bushland - Existing Rehabililitation - Post 1998
Total rehabilitation area size (ha) |  |  |  | 195
Commencement of first milestone: RM6 |  |  |  | 2026-05-08
PMLU |  |  |  | Bushland
Date area is available | 2026-05-08 | 2030-12-10 | 2035-12-10
Cumulative area available (ha) | 127 | 195 | 195
Milestone completed by | 2030-12-10 | 2035-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 6 - Achievement of surface requirements (Bushland) | 127 | 68
RM 9 - Achievement of Bushland PMLU to a stable condition |  | 127 | 195
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## The Hut RA2
The Hut
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Bushland - Existing Rehabililitation - Post 1998
Total rehabilitation area size (ha) |  |  |  | 163
Commencement of first milestone: RM6 |  |  |  | 2026-05-08
PMLU |  |  |  | Bushland
Date area is available | 2026-05-08 | 2030-12-10 | 2035-12-10
Cumulative area available (ha) | 79 | 163 | 163
Milestone completed by | 2030-12-10 | 2035-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 6 - Achievement of surface requirements (Bushland) | 79 | 84
RM 9 - Achievement of Bushland PMLU to a stable condition |  | 79 | 163
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Boundary Hill RA2
Boundary Hill
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Bushland - Existing Rehabililitation - Post 1998
Total rehabilitation area size (ha) |  |  |  | 250
Commencement of first milestone: RM6 |  |  |  | 2026-05-08
PMLU |  |  |  | Bushland
Date area is available | 2026-05-08 | 2030-12-10 | 2035-12-10
Cumulative area available (ha) | 126 | 250 | 250
Milestone completed by | 2030-12-10 | 2035-12-10 | 2045-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 6 - Achievement of surface requirements (Bushland) | 126 | 124
RM 9 - Achievement of Bushland PMLU to a stable condition |  | 126 | 250
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Dunn Creek RA3
Dunn Creek
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Overburden Emplacement Areas
Total rehabilitation area size (ha) |  |  |  | 530
Commencement of first milestone: RM1 |  |  |  | 2030-12-10
PMLU |  |  |  | Bushland
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 150 | 339 | 339 | 509 | 530 | 530 | 530 | 530 | 530
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2035-12-10: Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 2035-12-10: 150; 2040-12-10: 339; 2050-12-10: 509; 2055-12-10: 530
RM 2 - Identification, remediation and removal of contaminated land | 2035-12-10: 150; 2040-12-10: 339; 2050-12-10: 509; 2055-12-10: 530
RM 3 - Landform development and reshaping/reprofiling | 2035-12-10: 150; 2040-12-10: 339; 2050-12-10: 509; 2055-12-10: 530
RM 4 - Surface Preparation | 2035-12-10: 150; 2040-12-10: 339; 2050-12-10: 509; 2055-12-10: 530
RM 5 - Revegatation | 150 | 339 | 339 | 509 | 530 | 530 | 530
RM 6 - Achievement of surface requirements (Bushland) | 2045-12-10: 150; 2050-12-10: 339; 2055-12-10: 339; 2060-12-10: 509; 2065-12-10: 530
RM 9 - Achievement of Bushland PMLU to a stable condition | 2055-12-10: 150; 2060-12-10: 339; 2065-12-10: 339; 2070-12-10: 509; 2075-12-10: 530
RM 12 - Retained Infrastructure | 2055-12-10: 150; 2060-12-10: 339; 2065-12-10: 339; 2070-12-10: 509; 2075-12-10: 530
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Trap Gully RA3
Trap Gully
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Overburden Emplacement Areas
Total rehabilitation area size (ha) |  |  |  | 982
Commencement of first milestone: RM1 |  |  |  | 2045-12-10
PMLU |  |  |  | Bushland
Date area is available | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Cumulative area available (ha) | 99 | 396 | 982 | 982 | 982 | 982 | 982
Milestone completed by | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10 | 2080-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 99 | 396 | 982
RM 2 - Identification, remediation and removal of contaminated land | 99 | 396 | 982
RM 3 - Landform development and reshaping/reprofiling | 99 | 396 | 982
RM 4 - Surface Preparation | 99 | 396 | 982
RM 5 - Revegatation | 99 | 396 | 982 | 982
RM 6 - Achievement of surface requirements (Bushland) |  |  | 99 | 396 | 982 | 982
RM 9 - Achievement of Bushland PMLU to a stable condition |  |  |  |  | 99 | 396 | 982
RM 12 - Retained Infrastructure |  |  |  |  | 99 | 396 | 982
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## The Hut RA3
The Hut
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Overburden Emplacement Areas
Total rehabilitation area size (ha) |  |  |  | 214
Commencement of first milestone: RM1 |  |  |  | 2026-12-10
PMLU |  |  |  | Bushland
Date area is available | 2026-12-10 | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10
Cumulative area available (ha) | 48 | 57 | 57 | 164 | 214 | 214 | 214 | 214 | 214
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Milestone Reference | 2030-12-10: Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 2030-12-10: 48; 2035-12-10: 57; 2045-12-10: 164; 2050-12-10: 214
RM 2 - Identification, remediation and removal of contaminated land | 2030-12-10: 48; 2035-12-10: 57; 2045-12-10: 164; 2050-12-10: 214
RM 3 - Landform development and reshaping/reprofiling | 2030-12-10: 48; 2035-12-10: 57; 2045-12-10: 164; 2050-12-10: 214
RM 4 - Surface Preparation | 2030-12-10: 48; 2035-12-10: 57; 2045-12-10: 164; 2050-12-10: 214
RM 5 - Revegatation | 48 | 57 | 57 | 164 | 214 | 214
RM 6 - Achievement of surface requirements (Bushland) |  |  | 48 | 57 | 57 | 164 | 214 | 214
RM 9 - Achievement of Bushland PMLU to a stable condition | 2050-12-10: 48; 2055-12-10: 57; 2060-12-10: 57; 2065-12-10: 164; 2070-12-10: 214
RM 12 - Retained Infrastructure | 2050-12-10: 48; 2055-12-10: 57; 2060-12-10: 164; 2065-12-10: 164; 2070-12-10: 214
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Boundary Hill RA3
Boundary Hill
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Overburden Emplacement Areas
Total rehabilitation area size (ha) |  |  |  | 501
Commencement of first milestone: RM1 |  |  |  | 2030-12-10
PMLU |  |  |  | Bushland
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Cumulative area available (ha) | 40 | 207 | 424 | 424 | 501 | 501 | 501 | 501 | 501
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2035-12-10: Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 2035-12-10: 40; 2040-12-10: 207; 2050-12-10: 424; 2055-12-10: 501
RM 2 - Identification, remediation and removal of contaminated land | 2035-12-10: 40; 2040-12-10: 207; 2050-12-10: 424; 2055-12-10: 501
RM 3 - Landform development and reshaping/reprofiling | 2035-12-10: 40; 2040-12-10: 207; 2050-12-10: 424; 2055-12-10: 501
RM 4 - Surface Preparation | 2035-12-10: 40; 2040-12-10: 207; 2050-12-10: 424; 2055-12-10: 501
RM 5 - Revegatation | 40 | 207 | 207 | 424 | 501 | 501
RM 6 - Achievement of surface requirements (Bushland) | 2045-12-10: 40; 2050-12-10: 207; 2055-12-10: 207; 2060-12-10: 424; 2065-12-10: 501
RM 9 - Achievement of Bushland PMLU to a stable condition | 2055-12-10: 40; 2060-12-10: 207; 2065-12-10: 424; 2070-12-10: 501; 2075-12-10: 501
RM 12 - Retained Infrastructure | 2055-12-10: 40; 2060-12-10: 207; 2065-12-10: 424; 2070-12-10: 424; 2075-12-10: 501
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Dunn Creek RA4
Dunn Creek
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 130
Commencement of first milestone: RM1 |  |  |  | 2050-12-10
PMLU |  |  |  | Bushland
Date area is available | 2050-12-10 | 2055-12-10 | 2065-12-10
Cumulative area available (ha) | 130 | 130 | 130
Milestone completed by | 2055-12-10 | 2065-12-10 | 2075-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 130
RM 2 - Identification, remediation and removal of contaminated land | 130
RM 3 - Landform development and reshaping/reprofiling | 130
RM 4 - Surface Preparation | 130
RM 5 - Revegatation | 130
RM 6 - Achievement of surface requirements (Bushland) |  | 130
RM 9 - Achievement of Bushland PMLU to a stable condition |  |  | 130
RM 12 - Retained Infrastructure |  |  | 130
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Trap Gully RA4
Trap Gully
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 68
Commencement of first milestone: RM1 |  |  |  | 2050-12-10
PMLU |  |  |  | Bushland
Date area is available | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2075-12-10 | 2080-12-10
Cumulative area available (ha) | 17 | 68 | 68 | 68 | 68 | 68
Milestone completed by | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2075-12-10 | 2080-12-10 | 2085-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 17 | 68
RM 2 - Identification, remediation and removal of contaminated land | 17 | 68
RM 3 - Landform development and reshaping/reprofiling | 17 | 68
RM 4 - Surface Preparation | 17 | 68
RM 5 - Revegatation | 17 | 68 | 68
RM 6 - Achievement of surface requirements (Bushland) |  |  | 17 | 68 | 68
RM 9 - Achievement of Bushland PMLU to a stable condition |  |  |  |  | 17 | 68
RM 12 - Retained Infrastructure |  |  |  |  | 17 | 68
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## The Hut RA4
The Hut
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 120
Commencement of first milestone: RM1 |  |  |  | 2030-12-10
PMLU |  |  |  | Bushland
Date area is available | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10
Cumulative area available (ha)
Milestone completed by | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | 2070-12-10
Milestone Reference | 2035-12-10: Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 2035-12-10: 34; 2045-12-10: 38; 2050-12-10: 120
RM 2 - Identification, remediation and removal of contaminated land | 2035-12-10: 34; 2045-12-10: 38; 2050-12-10: 120
RM 3 - Landform development and reshaping/reprofiling | 2035-12-10: 34; 2045-12-10: 38; 2050-12-10: 120
RM 4 - Surface Preparation | 2035-12-10: 34; 2045-12-10: 38; 2050-12-10: 120
RM 5 - Revegatation | 34 | 34 | 38 | 120 | 120
RM 6 - Achievement of surface requirements (Bushland) |  |  | 34 | 34 | 38 | 120 | 120
RM 9 - Achievement of Bushland PMLU to a stable condition | 2055-12-10: 34; 2060-12-10: 34; 2065-12-10: 38; 2070-12-10: 120
RM 12 - Retained Infrastructure | 2055-12-10: 34; 2060-12-10: 34; 2065-12-10: 38; 2070-12-10: 120
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Boundary Hill RA4
Boundary Hill
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 106
Commencement of first milestone: RM1 |  |  |  | 2045-12-10
PMLU |  |  |  | Bushland
Date area is available | 2045-12-10 | 2050-12-10 | 2060-12-10
Cumulative area available (ha) | 106 | 106 | 106
Milestone completed by | 2050-12-10 | 2060-12-10 | 2070-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 106
RM 2 - Identification, remediation and removal of contaminated land | 106
RM 3 - Landform development and reshaping/reprofiling | 106
RM 4 - Surface Preparation | 106
RM 5 - Revegatation | 106
RM 6 - Achievement of surface requirements (Bushland) |  | 106
RM 9 - Achievement of Bushland PMLU to a stable condition |  |  | 106
RM 12 - Retained Infrastructure |  |  | 106
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## The Hut RA5
The Hut
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 3
Commencement of first milestone: RM1 |  |  |  | 2040-12-10
PMLU |  |  |  | Grazing
Date area is available | 2040-12-10 | 2045-12-10 | 2055-12-10
Cumulative area available (ha) | 3 | 3 | 3
Milestone completed by | 2045-12-10 | 2055-12-10 | 2060-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 3
RM 2 - Identification, remediation and removal of contaminated land | 3
RM 3 - Landform development and reshaping/reprofiling | 3
RM 4 - Surface Preparation | 3
RM 5 - Revegatation | 3
RM 7 - Achievement of surface requirements (Grazing) |  | 3
RM 10 - Achievement of Grazing PMLU to a stable condition |  |  | 3
RM 12 - Retained Infrastructure |  |  | 3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Boundary Hill RA5
Boundary Hill
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Mine Infrastructure Area, Roads, Laydown areas, General infrastructure and disturbance
Total rehabilitation area size (ha) |  |  |  | 82
Commencement of first milestone: RM1 |  |  |  | 2045-12-10
PMLU |  |  |  | Grazing
Date area is available | 2045-12-10 | 2050-12-10 | 2065-12-10
Cumulative area available (ha) | 82 | 82 | 82
Milestone completed by | 2050-12-10 | 2060-12-10 | 2070-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 1 - Infrastructure decommissioning and removal | 82
RM 2 - Identification, remediation and removal of contaminated land | 82
RM 3 - Landform development and reshaping/reprofiling | 82
RM 4 - Surface Preparation | 82
RM 5 - Revegatation | 82
RM 7 - Achievement of surface requirements (Grazing) |  | 82
RM 10 - Achievement of Grazing PMLU to a stable condition |  |  | 82
RM 12 - Retained Infrastructure |  |  | 82
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Trap Gully RA6
Trap Gully
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6
Relevant activities |  |  | Creek Diversion
Total rehabilitation area size (ha) |  |  | 3
Commencement of first milestone: RM8 |  |  | 2035-12-10
PMLU |  |  | Watercourse (Engineered Diversion)
Date area is available | 2035-12-10 | 2045-12-10
Cumulative area available (ha) | 3
Milestone completed by | 2045-12-10 | 1955-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 8 - Achievement of surface requirements (Watercourse) | 3
RM 11 - Achievement of Watercourse PMLU to a stable condition |  | 3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## The Hut RA6
Trap Gully
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6
Relevant activities |  |  | Creek Diversion
Total rehabilitation area size (ha) |  |  | 10
Commencement of first milestone: RM8 |  |  | 2045-12-10
PMLU |  |  | Watercourse (Engineered Diversion)
Date area is available | 2035-12-10 | 2045-12-10
Cumulative area available (ha) | 10 | 10
Milestone completed by | 2045-12-10 | 1955-12-10
Milestone Reference | Cumulative area achieved (ha)
RM 8 - Achievement of surface requirements (Watercourse) | 10
RM 11 - Achievement of Watercourse PMLU to a stable condition |  | 10
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Dunn Creek IA1
Dunn Creek
Non-use management area (NUMA)
Improvement area |  |  | IA1
Relevant activities |  |  | Final Voids and Ramps D-Cut Void (206.7ha) The Bluff (164.6ha)
Total size (ha) |  |  | 371
Commencement of first milestone: MM1 |  |  | 2055-12-10
NUMA |  |  | Final Void
Date area is available | 2055-12-10 | 2060-12-10
Cumulative area available (ha) | 371 | 371
Milestone completed by | 2060-12-10 | 2075-12-10
Milestone Reference | Cumulative area achieved (ha)
MM 1 - Achievement of final landform design | 371
MM 2 - Achievement of safety requirements | 371
MM 3 - Achievement of sufficient improvement |  | 371
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Trap Gully IA1
Trap Gully
Non-use management area (NUMA)
Improvement area |  |  | IA1
Relevant activities |  |  | Final Voids and Ramps
Total size (ha) |  |  | 203
Commencement of first milestone: MM1 |  |  | 2060-12-10
NUMA |  |  | Final Void
Date area is available | 2060-12-10 | 2065-12-10
Cumulative area available (ha) | 203 | 203
Milestone completed by | 2065-12-10 | 2080-12-10
Milestone Reference | Cumulative area achieved (ha)
MM 1 - Achievement of final landform design | 203
MM 2 - Achievement of safety requirements | 203
MM 3 - Achievement of sufficient improvement |  | 203
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## The Hut IA1
The Hut
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final Voids and Ramps CVN (90.5ha) CVS (60.3ha) EH (63.0ha)
Total size (ha) |  |  |  | 213
Commencement of first milestone: MM1 |  |  |  | 2030-12-10
NUMA |  |  |  | Final Void
Date area is available | 2030-12-10 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2060-12-10 | 2065-12-10
Cumulative area available (ha) | 90 | 153 | 213 | 213 | 213 | 213
Milestone completed by | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2065-12-10 | 2070-12-10
Milestone Reference | Cumulative area achieved (ha)
MM 1 - Achievement of final landform design | 90 | 153 | 213
MM 2 - Achievement of safety requirements | 90 | 153 | 213
MM 3 - Achievement of sufficient improvement |  |  |  | 90 | 153 | 213
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Boundary Hill IA1
Boundary Hill
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final Voids and Ramps BH (258.6ha) BHE (32.4ha) BHS (156.0ha)
Total size (ha) |  |  |  | 447
Commencement of first milestone: MM1 |  |  |  | 2050-12-10
NUMA |  |  |  | Final Void
Date area is available | 2050-12-10 | 2055-12-10 | 2060-12-10
Cumulative area available (ha) | 291 | 447 | 447
Milestone completed by | 2055-12-10 | 2060-12-10 | 2075-12-10
Milestone Reference | Cumulative area achieved (ha)
MM 1 - Achievement of final landform design | 291 | 447
MM 2 - Achievement of safety requirements | 291 | 447
MM 3 - Achievement of sufficient improvement |  |  | 447
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | 1.1 With the exception of any infrastructure to remain as part of the post-mining land use (PMLU), where agreed to be retained by the landholder as evidenced by a signed landholder agreement, (and subject to the exclusions in 1.2), or infrastructure required for rehabilitation activities the following are complete:
a) All known services disconnected and removed.
b) All buildings and associated infrastructure dismantled and removed offsite.
c) All hardstand, concrete areas and roads (bitumen, blue metal, aggregate etc.) removed.
d) All fencing and associated foundations removed.
e) All known pipelines drained and removed.
f) All waste not authorised to be disposed of on-site under Environmental Authority EPML00720413 removed.
g) All surface water drainage infrastructure that does not form part of a non-use management area (NUMA) is removed.
h) All drillholes, bores and associated sediment ponds and sumps decommissioned.
i) All machinery and equipment removed.
j) All dams dewatered and desilted.
k) Watercourse crossings and culverts removed.
1.2 Below-ground infrastructure, services and waste (as per the Environmental Authority EPML00720413 – Schedule H waste) deeper than 0.5 m in relation to the final landform surface can be retained provided:
a) All pipelines have been drained; and
b) All below-ground infrastructure (installed after the approval date of this PRCP) to be retained must be mapped; and
c) The intended PMLU is not compromised; and
d) There is no ongoing risk of environmental harm
1.3 An independent AQP has certified the achievement of RM1.1.
RM2 | Identification, remediation and removal of contaminated land | 2.1 For any part of the mining leases that has been used for a notifiable activity, or which the holder is aware is likely to be contaminated land, a contaminated Land Investigation Document completed in accordance with the Environmental Protection Act 1994, including a site investigation report, and, where required, a Validation Report and/or a draft Site Management Plan.
2.2 Contaminated water and sediment removed from dams.
2.3 Contaminated and hazardous material either remediated in situ or removed/transported to a facility lawfully able to accept the material.
2.4 A Suitably Qualified person certifies that no contamination unsuitable for the PMLU achievement remains or is occurring.
RM3 | Landform development (reshaping/reprofiling) | 3.1 All major earthworks (including reshaping, pushing/trimming) are completed in accordance with the design specification provided by an AQP, developed in accordance with EA Tables F2 and F3.
3.2 The constructed landform has been assessed by an appropriately qualified person and certified as geotechnically safe and stable for the intended post-mining land use, consistent with the methodology and principles outlined in Project C34028 — Guidelines for Assessment of Geotechnically Safe and Stable Post-Mining Landforms (ACARP).
3.3 Landforms (except for Dunn Creek A & S Cut spoil) reshaped with maximum outer slopes of ≤15% with graded banks at 10m vertical intervals (60 m along the slope).
3.4 Landform of Dunn Creek A & S Cut spoil reshaped with maximum outer slopes of ≤25% with 120m slope length and berms or graded banks at 120m along the slope and basalt mulch cladding.
ESC Facilities
3.5 Existing and proposed Erosion and Sediment Control (ESC) and drainage structures on site have been reviewed and endorsed by an independent AQP as appropriate to the landform, materials and PMLU, with consideration given to long-term performance and stability in a post-closure context.
3.6 ESC facilities decommissioned and left free draining.
3.7 Independent AQP has certified achievement of RM 3.1-3.4.
RM4 | Surface preparation (Bushland and Grazing) | 4.1 Assessment of growth media characteristics and the development of an amelioration and physical treatment plan is completed prior to the application of the growth media to the surface.
4.2 Ameliorant and physical treatments such as fertiliser, lime, gypsum and/or organic matter are applied as identified in criteria 4.1.
4.3 Deep ripping of compacted surfaces, at least 300 mm at 1 metre spacing into soil/subsoil profile along contour of slopes, where possible.
4.4 Application of rock mulch on steeper slopes as directed by the LODs.
4.5 Topsoil/growth media placement of a minimum of 0.15 m in areas where topsoil has previously been removed.
4.6 Following amelioration as per criteria 4.1 and 4.2, representative soil testing of growth media confirms:
a) pH in the range of 5.0 - 8.5.
b) Electrical Conductivity (saturated extract) (dS/m) ≤0.6 (600 µS/cm).
c) Exchangeable sodium percentage (ESP) (%) < 15.
4.7 Independent AQP has certified the amelioration and treatment plan in RM 4.1 and achievement of RM 4.2-4.6.
RM5 | Revegetation (Bushland, Grazing and Watercourse) | 5.1 Seeding completed using seed mix and sowing rates described in Section F Appendix 1: Seed mixes and seeding rates, or as amended for additional native endemic species as recommended by an AQP and certified as suitable to achieve a stable condition.
5.2 Stock exclusion fencing has been established where required to prevent stock from grazing newly seeded areas.
5.3 Appropriate erosion controls installed/placed and functioning as designed (as per AQP certified report) to ensure erosive events do not significantly impact plant establishment.
Bushland PMLU (RA3 and RA4)
5.4 Non-native seed must not be used for the revegetation of Bushland PMLU (except when sterile cover crops are used).
5.5 Completed seeding with a selection of native vegetation species and seeding rates in Section F Appendix 1 Table 1 – Species list and seeding rates for bushland PMLU.
5.6 Species chosen must reflect REs 11.10.13 or 11.10.1
5.7 Minimum seeding rates of 6kg/ha of tree species, 4kg/ha of woody understory species and 10kg/ha of grasses used.
Grazing PMLU (RA5)
5.8 Completed seeding with a selection of species and seeding rates listed in Section F Appendix 1 Table 2 - Species list and seeding rates for grazing PMLU.
5.9 At least four species of 3P pasture species and two legume species established, from Section F Appendix 1 Table 2 - Species list and seeding rates for grazing PMLU are applied per application area.
5.10 Minimum seeding rates of 16kg/ha of pasture seed and 4kg/ha of legume seed are used.
Watercourse PMLU (RA6)
5.11 Completed seeding with a selection of relevant watercourse species and seeding rates in Section F Appendix 1 Table 3A: Recommended species to be established for the Watercourse PMLU – upper and mid banks and Table 3B: Recommended species to be established for the Watercourse PMLU – lower banks
5.12 Species chosen should reflect RE11.3.25.
5.13 Minimum seeding rates of:
(a) For the upper and mid banks – 6kg/ha trees species, 4kg/ha woody understorey species and 10kg/ha grasses and other groundcover species.
(b) For the lower banks – 5kg/ha tree species and 10kg/ha of grasses and other groundcover species.
RM6 | Achievement of surface requirements (Bushland) | 6.1 Species used in revegetation remain present and show evidence of natural recruitment. Evidence of flora recruitment from rehabilitation monitoring data.
6.2 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover.
6.3 Restricted invasive plants are appropriately managed.
6.4 Achievement of bare ground <25%
6.5 With respect to erosion, an AQP certifies that:
a) No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Section F Appendix 1 Table 4 – Erosion Classification Framework
b) Any erosion present will not compromise the achievement of the PMLU to a stable condition.
c) Erosion requiring intervention has been remediated and does not impact achieving the PMLU.
d) Any and all gully erosion:
(i) Is isolated, linear, discontinuous, and restricted to primary or minor drainage lines
(ii) Does not exceed 1 metre in depth at any point
(iii) Does not expose or risk exposing environmentally problematic materials
(iv) The cause is known and has been resolved
(v) Is in a stabilised state, demonstrated by monitoring data over a 5-year period
(vi) Does not provide a safety hazard within the context of the PMLU; and
(vii) Does not impact the stability or performance of engineered drainage features
6.6 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur, and it is safe to do so and complies with Table 7 – Surface water quality limits for pH, EC and total suspended solids.
ESC Facilities
6.7 No evidence of scouring, overtopping, sedimentation or destabilisation in (or associated with) erosion and sediment control and engineering drainage structures.
6.8 Any ESC and drainage structures to be retained as a permanent features are certified by an AQP to remain stable in perpetuity with no increased risk of gully erosion at surrender.
Bushland PMLU – Planned rehabilitation (RA3 and RA4)
6.9 Achievement of bare ground <25%
6.10 Monitoring completed by an AQP using Batchfire’s PRCP Section 9 methodology
6.11 The assessment completed under RM6.10 complies with the PRCP RM6 Benchmark, as per Table 5 – BioCondition Benchmark Criteria
RM7 | Achievement of surface requirements (Grazing) | 7.1 Species used in revegetation remain present and show evidence of natural recruitment. Evidence of flora recruitment from rehabilitation monitoring data.
7.2 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover.
7.3 Restricted invasive plants are appropriately managed.
7.4 >50% established and self-sustaining vegetative groundcover of species listed in Section F Appendix 1 Table 2 - Species list and seeding rates for grazing PMLU.
7.5 Minimum vegetation composition (per hectare (averaged)) of:
a) four species of 3P pasture species, and
b) two legumes
7.6 Land Suitability class is 3 or below.
7.7 With respect to erosion, an AQP certifies that:
a) No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Section F Appendix 1 Table 4 – Erosion Classification Framework
b) Any erosion present will not compromise the achievement of the PMLU to a stable condition.
c) Erosion requiring intervention has been remediated and does not impact achieving the PMLU.
d) Any and all gully erosion:
(i) Is isolated, linear, discontinuous and restricted to primary or minor drainage lines
(ii) Does not exceed 1 m in depth at any point
(iii) Does not expose or risk exposing environmentally problematic materials
(iv) Cause is known and has been resolved
(v) Is in a stabilised state, demonstrated by monitoring data over a 5 year period
(vi) Does not provide a safety hazard within the context of the PMLU; and
(vii) Does not impact the stability or performance of engineered drainage features
7.8 Surface water runoff has been collected (when safe to do so) across representative areas of rehabilitation when surface flows occur, and results comply with Table 7 – Surface water quality limits for pH, EC and total suspended solids .
RM8 | Achievement of surface requirements (Watercourse) | 8.1 Species used in revegetation remain present and show evidence of natural recruitment. Evidence of flora recruitment from rehabilitation monitoring data.
8.2 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover.
8.3 Restricted invasive plants are appropriately managed.
8.4 Groundcover: <25% bare ground.
8.5 Watercourse vegetation meets the following:
a) Species richness:
(i) ≥2 native trees,
(ii) ≥2 native shrubs;
(iii) ≥2 grass species;
b) Tree canopy cover ≥ 13%.
8.6 With respect to erosion, an AQP certifies that:
a) No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Section F Appendix 1 Table 4 – Erosion Classification Framework
b) Any erosion present will not compromise the achievement of the PMLU to a stable condition.
c) Erosion requiring intervention has been remediated and does not impact achieving the PMLU.
d) Any and all gully erosion:
(i) Is isolated, linear, discontinuous and restricted to primary or minor drainage lines
(ii) Does not exceed 1 m in depth at any point
(iii) Does not expose or risk exposing environmentally problematic materials
(iv) Cause is known and has been resolved
(v) Is in a stabilised state, demonstrated by monitoring data over a 5-year period
(vi) Does not provide a safety hazard within the context of the PMLU; and
(vii) Does not impact the stability or performance of engineered drainage features
8.7 Surface water runoff has been collected (when safe to do so) across representative areas of rehabilitation when surface flows occur, and results comply with Table 7 – Surface water quality limits for pH, EC and total suspended solids.
RM9 | Achievement of Bushland post-mining land use to a stable condition | 9.1 Safety hazards in the rehabilitation area are not significantly different to surrounding unmined landscapes subject to the same land use.
9.2 Any remaining infrastructure has been rehabilitated in accordance with RM1.1
9.3 The land is structurally and erosionally stable.
Bushland PMLU – Existing rehabilitation pre-1998 (RA1)
9.4 At least three native species are present, including one or more Eucalyptus, Acacia, or Corymbia
9.5 50% of the trees present are healthy and growing.
9.6 Trees >1.6m tall have a density >50 stems/ha
Bushland PMLU – Existing rehabilitation post-1998 (RA2)
9.7 At least four native species present, including one or more Eucalyptus, Acacia, or Corymbia
9.8 80% of trees (excluding short-lived acacias) are healthy and growing
9.9 Trees >1.6m tall and >100 stems/ha
Bushland PMLU – Planned rehabilitation (RA3 and RA4)
9.10 Achievement of bare ground <25%
9.11 Monitoring completed by an AQP using Batchfire’s PRCP Section 9 methodology
9.12 The assessment completed under RM9.11 complies with the PRCP RM9 Benchmark, as per Table 5 – BioCondition Benchmark Criteria
9.13 Surface water runoff has been collected (when safe to do so) across representative areas of rehabilitation when surface flows occur, and results comply with Table 7 – Surface water quality limits for pH, EC and total suspended solids.
Contaminated Land
9.14 Verification by a suitably qualified person to confirm:
a) Requirements of any site management plan have been met
b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the nominated PMLU
c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2.
Drainage Structures
9.15 Where engineered drainage structures are to be retained as permanent features (e.g. contour banks, bench drains, rock drains), it must be certified by an AQP that the structures are stable and can be expected to remain stable and functional in the long term.
Retained Infrastructure/Water Storage
9.16 Infrastructure to be transitioned to a future landholder is deemed fit for purpose, safe and stable by AQP and accepted, by signed agreement with the future landholder
9.17 Retained dams are safe for native animals and stock access and have vegetated banks.
9.18 Water storage water quality monitored quarterly must meet the ANZECC 2000 livestock drinking water limits, for a minimum of 5 consecutive years, including the 5-year period immediately prior to surrender.
RM10 | Achievement of Grazing post-mining land use to a stable condition | 10.1 Safety hazards in the rehabilitation area are not significantly different to surrounding unmined landscapes subject to the same land use.
10.2 Any remaining infrastructure has been rehabilitated in accordance with RM1.1.
10.3 The land is structurally and erosionally stable.
10.4 Total groundcover ≥70%, of which ≥50% is vegetative cover consisting of 3P pasture species as listed in Section F Appendix 1 Table 2 Recommended species list and seeding rates for the Grazing PMLU
10.5 Surface water runoff has been collected (when safe to do so) across representative areas of rehabilitation when surface flows occur, and results comply with Table 7 – Surface water quality limits for pH, EC and total suspended solids.
Contaminated Land
10.6 Verification by a suitably qualified person to confirm:
a) Requirements of any site management plan have been met
b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for nominated PMLU
c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2.
Drainage Structures
10.7 Where engineered drainage structures are to be retained as permanent features (e.g. contour banks, bench drains, rock drains), it must be certified by an AQP that the structures are stable and can be expected to remain stable and functional in the long term.
Retained Infrastructure/Water Storage
10.8 Infrastructure to be transitioned to a future landholder is deemed fit for purpose, safe and stable by AQP and accepted, by signed agreement with the future landholder.
10.9 Retained dams are safe for native animals and stock access and have vegetated banks.
10.10 Water storages water quality monitored quarterly must meet the ANZECC 200 livestock drinking water limit, for a minimum of 5 consecutive years, including the 5-year period immediately prior to surrender.
RM11 | Achievement of Watercourse post-mining land use to a stable condition | 11.1 Safety hazards in the rehabilitation area are not significantly different to surrounding unmined landscapes subject to the same land use.
Oaky Creek Diversion
11.2 The watercourse/diversion achieves compliance with all relevant conditions of Water Licence 105184 and approvals issued under the Water Act 2000 (Qld), which includes:
a) Ongoing monitoring is undertaken
b) Completion of any maintenance/repairs
c) Satisfying completion criteria specified in the Water Licence design criteria
d) Submission of a water licence relinquishment application, supported by a Final Monitoring and Evaluation Report that is certified by an RPEQ
e) QLD government relinquishment of Water Licence 105184
Trap Gully Diversion
11.3 A remediation and monitoring plan to be developed by AQP
11.4 Diversion remediation work undertaken in accordance with the plan developed in 11.3.
11.5 Monitoring program implemented
11.6 Certification by AQP that diversion is stable
RM12 | Retained Infrastructure | 12.1 Infrastructure to be transitioned to a future landholder is deemed fit for purpose (verified by an AQP) and accepted, by signed agreement, with the future landholder.
12.2 An AQP certifies that all infrastructure to be retained onsite is safe, stable and will not cause environmental harm.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of final landform design | 1.1 The residual void NUMA areas include the residual voids, geotechnical stability set backs from the void wall crests and the highwall safety bunds/fences. The residual voids have a maximum area including the high walls, low walls, end walls, ramps and ramp slopes, and void water bodies as follows:
(a) Boundary Hill: 275.4ha
(b) Boundary Hill South: 147.4 ha
(c) Dunn Creek: 329.5.2ha
(d) Trap Gully: 190.5ha
(e) The Hut: 167.8ha
The additional residual void NUMA areas, required for the geotechnical stability set backs and safety bunds/fences, will be determined by an AQP within 3 years of mine closure. Interim total residual void NUMA areas, including allowances of up to 100m for geotechnical stability set backs and safety bunds/fences, are as follows:
(a) Boundary Hill: 291ha
(b) Boundary Hill South: 156 ha
(c) Dunn Creek: 371.3ha
(d) Trap Gully: 203.1ha
(e) The Hut: 213.8ha.
1.2 Highwall landforms must:
(a) Where appropriate and practical, a diversion drain will be constructed on the crest of the highwall to divert runoff away from the residual void
(b) have 75-degree slopes and;
(i) if determined to be stable by an AQP, the highwall will be left as is;
(ii) if not deemed stable by an AQP, then alternative treatments will be undertaken to ensure geotechnical stability as determined by the AQP.
(c) Have pre-strip benches shaped to shed runoff over the high wall at several locations to limit erosion.
1.3 The final design for highwall landform must be completed by an AQP based on the latest flood modelling and materials data prior to construction.
1.4 Low walls and ramps slope generally at angle of repose.
1.5 The location of the voids and associated safety bunds does not cause instability or degradation to the land outside the NUMA.
1.6 Based on the water level and any water quality post closure prediction results from the groundwater model and final void lake balance models, an AQP assesses that the final void lake will not adversely impact groundwater quality at sensitive groundwater-dependent features
1.7 Based on the post closure groundwater model and final void water balance models the final void lake will not overflow to the ground surface
MM2 | Achievement of safety requirements | 2.1 Competent safety bund or equivalent landform in place to prevent access to the residual void NUMA, at the geotechnical stability set-back distance determined in accordance with 1.1.
2.2 The safety bund is accordance with engineering requirements including:
(i) Constructed from non-weathered, non-dispersive dumped rockfill;
(ii) a minimum 2m in height; and
(iii) a minimum of 4 m base width
2.3 Fencing erected, where required to prevent access to the residual void, around the perimeter of the safety bund.
2.4 Safety signage (design in accordance with Australian standard) is erected at 100m intervals along the fence.
MM3 | Achievement of sufficient improvement | 3.1 The highwall stability has been assessed and geotechnical stability set back distance has been determined by an AQP.
3.2 Appropriate safety infrastructure (as per MM2) at the geotechnical set-back distance has been installed to prevent access to the residual void NUMA.
3.3 The residual void is safe to humans and livestock.
3.4 The final void water level and quality does not, and will not, cause environmental harm to the receiving environment, as demonstrated by groundwater and final void lake level and quality monitoring.
3.5 Erosion of the landform within the residual void NUMA area will not negatively impact on the stability of any adjacent rehabilitation areas, or their ability to sustain their PMLU.
3.6 Monitoring and maintenance of exclusion fences and bunds to be carried out to ensure they remain effective.
3.7 Independent AQP certifies achievement of MM3.1 – MM3.6
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones