## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Exploration
Total rehabilitation area size (ha) |  |  |  | 4.1
Commencement of first milestone: RM3 |  |  |  | 10/12/2024
PMLU |  |  |  | Grazing
Date area is available | 2024-12-10 | 2025-12-10 | 2028-12-10 | 2034-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10
Cumulative area available (ha) | 2.3335 | 2.3335 | 2.3335 | 4.0959 | 4.0959 | 4.0959 | 4.0959 | 4.0959
Milestone completed by | 2025-12-10 | 2028-12-10 | 2034-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10
Milestone Reference | 2025-12-10: Cumulative area achieved (ha)
RM3 | 2025-12-10: 2.3335; 2038-12-10: 4.0959
RM4 | 2025-12-10: 2.3335; 2038-12-10: 4.0959
RM5 | 2025-12-10: 2.3335; 2038-12-10: 4.0959; 2040-12-10: 4.0959
RM6 | 2028-12-10: 2.3335; 2042-12-10: 4.0959; 2044-12-10: 4.0959
RM7 |  |  | 2.3335 | 2.3335 | 2.3335 | 2.3335 | 2.3335 | 4.0959
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Overburden dumps and topsoil stockpiles
Total rehabilitation area size (ha) |  |  |  | 468.5
Commencement of first milestone: RM2 |  |  |  | 10/12/2025
PMLU |  |  |  | Grazing
Date area is available | 2023-06-30 | 2023-12-10 | 2024-12-10 | 2025-12-10 | 2026-12-10 | 2027-12-10 | 2028-12-10 | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10
Cumulative area available (ha) | 0 | 0 | 0 | 40.5921 | 81.2753 | 104.7954 | 135.9014 | 188.7588 | 242.4877 | 285.9949 | 368.9991 | 468.5 | 468.5 | 468.5 | 468.5 | 468.5 | 468.5
Milestone completed by | 2023-12-10 | 2024-12-10 | 2025-12-10 | 2026-12-10 | 2027-12-10 | 2028-12-10 | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10
Milestone Reference | 2023-12-10: Cumulative area achieved (ha)
RM2 | 2026-12-10: 40.5921; 2027-12-10: 81.2753; 2028-12-10: 104.7954; 2029-12-10: 135.9014; 2030-12-10: 188.7588; 2031-12-10: 242.4877; 2032-12-10: 285.9949; 2034-12-10: 368.9991; 2036-12-10: 468.5
RM3 | 2026-12-10: 40.5921; 2027-12-10: 81.2753; 2028-12-10: 104.7954; 2029-12-10: 135.9014; 2030-12-10: 188.7588; 2031-12-10: 242.4877; 2032-12-10: 285.9949; 2034-12-10: 368.9991; 2036-12-10: 468.5
RM4 | 2026-12-10: 0; 2027-12-10: 40.5921; 2028-12-10: 81.2753; 2029-12-10: 104.7954; 2030-12-10: 135.9014; 2031-12-10: 188.7588; 2032-12-10: 242.4877; 2034-12-10: 319.9207; 2036-12-10: 406.3733; 2038-12-10: 468.5
RM5 | 2027-12-10: 40.5921; 2028-12-10: 81.2753; 2029-12-10: 104.7954; 2030-12-10: 135.9014; 2031-12-10: 188.7588; 2032-12-10: 242.4877; 2034-12-10: 319.9207; 2036-12-10: 406.3733; 2038-12-10: 468.5
RM6 | 2030-12-10: 40.5921; 2031-12-10: 81.2753; 2032-12-10: 104.7954; 2034-12-10: 188.7588; 2036-12-10: 285.9949; 2038-12-10: 368.9991; 2040-12-10: 468.5
RM7 | 2036-12-10: 81.2753; 2038-12-10: 135.9014; 2040-12-10: 242.4877; 2042-12-10: 319.9207; 2044-12-10: 406.3733; 2046-12-10: 468.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2023-12-10 to 2032-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2023-12-10 to 2032-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2023-12-10 to 2032-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2023-12-10 to 2032-12-10

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Landholder retained infrastructure (Roads and Dams)
Total rehabilitation area size (ha) |  |  |  | 72.9
Commencement of first milestone: RM1 |  |  |  | 10/12/2040
PMLU |  |  |  | Retained infrastructure supporting grazing
Date area is available | 2040-12-10 | 2042-12-10 | 2044-12-10
Cumulative area available (ha) | 72.9 | 72.9 | 72.9
Milestone completed by | 2042-12-10 | 2044-12-10 | 2046-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 72.9
RM2 | 72.9
RM3 |  | 72.9
RM7 |  |  | 72.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure areas not subject to landholder agreement
Total rehabilitation area size (ha) |  |  |  | 119
Commencement of first milestone: RM1 |  |  |  | 10/12/2036
PMLU |  |  |  | Grazing
Date area is available | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10
Cumulative area available (ha) | 15.0657 | 16.0559 | 119 | 119 | 119 | 119 | 119
Milestone completed by | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10
Milestone Reference | 2038-12-10: Cumulative area achieved (ha)
RM1 | 2038-12-10: 15.0657; 2040-12-10: 16.0559; 2042-12-10: 119
RM2 | 2038-12-10: 15.0657; 2040-12-10: 16.0559; 2042-12-10: 119
RM3 | 2038-12-10: 15.0657; 2040-12-10: 16.0559; 2042-12-10: 119
RM4 | 2038-12-10: 5.3018; 2040-12-10: 16.0559; 2042-12-10: 119
RM5 | 2038-12-10: 5.3018; 2040-12-10: 16.0559; 2042-12-10: 119; 2044-12-10: 119
RM6 | 2042-12-10: 15.0657; 2044-12-10: 16.0559; 2046-12-10: 119; 2048-12-10: 119
RM7 | 2046-12-10: 5.3018; 2048-12-10: 16.0559; 2050-12-10: 119
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 89.89
Commencement of first milestone: RM3 |  |  |  | 10/12/2024
PMLU |  |  |  | Grazing
Date area is available | 2023-12-10 | 2024-12-10 | 2026-12-10 | 2028-12-10 | 2030-12-10 | 2032-12-10 | 2034-12-10
Cumulative area available (ha) | 89.8929 | 89.8929 | 89.8929 | 89.8929 | 89.8929 | 89.8929 | 89.8929
Milestone completed by | 2024-12-10 | 2026-12-10 | 2028-12-10 | 2030-12-10 | 2032-12-10 | 2034-12-10 | 2036-12-10
Milestone Reference | 2024-12-10: Cumulative area achieved (ha)
RM3 | 2024-12-10: 89.8929
RM4 | 2024-12-10: 89.9
RM5 | 2024-12-10: 89.8929; 2026-12-10: 89.8929; 2028-12-10: 89.8929
RM6 | 2028-12-10: 45; 2030-12-10: 89.8929; 2032-12-10: 89.8929; 2034-12-10: 89.8929
RM7 | 2032-12-10: 45; 2034-12-10: 45; 2036-12-10: 89.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Low Wall
Total rehabilitation area size (ha) |  |  |  | 135.2
Commencement of first milestone: RM3 |  |  |  | 10/12/2032
PMLU |  |  |  | Woodland Habitat
Date area is available | 2032-12-10 | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10
Cumulative area available (ha) | 46 | 92 | 135.2 | 135.2 | 135.2 | 135.2 | 135.2 | 135.2 | 135.2
Milestone completed by | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10
Milestone Reference | 2034-12-10: Cumulative area achieved (ha)
RM3 | 2034-12-10: 46; 2036-12-10: 92; 2038-12-10: 135.2
RM4 | 2036-12-10: 46; 2038-12-10: 92; 2040-12-10: 135.2
RM5 | 2036-12-10: 46; 2038-12-10: 92; 2040-12-10: 135.2; 2042-12-10: 135.2; 2044-12-10: 135.2
RM6 | 2040-12-10: 46; 2042-12-10: 92; 2044-12-10: 92; 2046-12-10: 135.2; 2048-12-10: 135.2
RM7 | 2044-12-10: 46; 2046-12-10: 92; 2048-12-10: 92; 2050-12-10: 135.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Isaac River Riparian Buffer
Total rehabilitation area size (ha) |  |  |  | 51.1
Commencement of first milestone: RM3 |  |  |  | 10/12/2036
PMLU |  |  |  | Riparian Woodland Habitat
Date area is available | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10
Cumulative area available (ha) | 10 | 26 | 51.1 | 51.1 | 51.1 | 51.1 | 51.1
Milestone completed by | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10
Milestone Reference | 2038-12-10: Cumulative area achieved (ha)
RM3 | 2038-12-10: 10; 2040-12-10: 26; 2042-12-10: 51.1
RM4 | 2038-12-10: 5; 2040-12-10: 10; 2042-12-10: 26; 2044-12-10: 51.1
RM5 | 2038-12-10: 5; 2040-12-10: 10; 2042-12-10: 26; 2044-12-10: 51.1
RM6 | 2042-12-10: 10; 2044-12-10: 26; 2046-12-10: 51.1; 2048-12-10: 51.1
RM7 | 2046-12-10: 10; 2048-12-10: 26; 2050-12-10: 51.1
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final void, end wall and highwall
Total size (ha) |  |  |  | 75
Commencement of first milestone: <insert milestone reference> |  |  |  | 30/6/2039 MM1
NUMA |  |  |  | NUMA
Date area is available | 2039-06-30 | 2039-06-30 | 2039-06-30 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 75 | 75 | 75
Milestone completed by | 2039-12-10 | 1940-12-10 | 1941-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
MM1 | 75
MM2 |  | 75
MM3 |  |  | 75
MM
MM
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Raw Data
OID_ | AREA | LAYER | REHAB_AREA | AVAILABLE | PMLU | FEATURE | AREA_HA | RA_PMLU | RM1 | RM2 | RM3 | RM4 | RM5 | RM6 | RM7 | SORT_COL | MAX_FINAL | END
0 | 2.4076 | Cleared | RA5 | 30/6/2023 |  |  | 2.4076 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 1 | 2031-12-10 | 2050-12-10 | Row Labels | Sum of AREA
1 | 0.277 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.277 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 2 | 2050-12-10 |  | IA1 | 75.0798
2 | 0.14516 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.14516 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 3 | 2050-12-10 |  | RA1 | 4.0959
3 | 0.016408 | Cleared | RA4 | 2040-06-30 |  |  | 0.016408 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 4 | 2050-12-10 |  | RA2 | 625.1378
4 | 0.10587 | MIA Dirty Water Drain | RA5 | 30/6/2023 |  |  | 0.10587 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 5 | 2031-12-10 |  | RA3 | 72.8706
5 | 0.16731 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.16731 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 6 | 2050-12-10 |  | RA4 | 148.6438
6 | 0.6392 | Cleared | RA5 | 30/6/2023 |  |  | 0.6392 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 7 | 2031-12-10 |  | RA5 | 89.8929
7 | 0.16651 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.16651 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 8 | 2050-12-10 |  | Grand Total | 1015.7208
8 | 9.1683 | Main Site Access and Haul Road | RA3 | 2040-06-30 |  |  | 9.1683 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 9 | 2050-12-10
9 | 0.0027235 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.0027235 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 10 | 2031-12-10
10 | 0.016986 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.016986 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 11 | 2031-12-10
11 | 0.27244 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.27244 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 12 | 2031-12-10
12 | 0.12906 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.12906 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 13 | 2031-12-10
13 | 0.0038569 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0038569 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 14 | 2050-12-10
14 | 0.0034214 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0034214 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 15 | 2050-12-10 |  | IA1 | 1 | 75.0798
15 | 0.0037646 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0037646 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 16 | 2050-12-10 |  | RA1 | 49 | 4.0959
16 | 0.0017483 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0017483 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 17 | 2050-12-10 |  | RA2 | 16 | 468.5524
17 | 0.0015627 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0015627 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 18 | 2050-12-10 |  | RA3 | 64 | 72.8706
18 | 0.0014753 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0014753 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 19 | 2050-12-10 |  | RA4 | 148 | 119.0005
19 | 0.0037233 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0037233 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 20 | 2050-12-10 |  | RA5 | 67 | 89.8929
20 | 0.0033669 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0033669 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 21 | 2050-12-10 |  | RA6 | 2 | 135.1591
21 | 0.0038535 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0038535 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 22 | 2050-12-10 |  | RA7 | 14 | 51.0696
22 | 0.0005643 | Tank 3m Diametre | RA4 | 2040-06-30 |  |  | 0.0005643 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 23 | 2050-12-10 |  | Sensitive Receptor | 17 | 49.7475
23 | 9.6235 | Hardstand Gravel Base | RA3 | 2040-06-30 |  |  | 9.6235 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 24 | 2050-12-10 |  | Maximum Disturbance | 1 | 1866.9789
24 | 0.25977 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.25977 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 25 | 2050-12-10
25 | 0.03592 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.03592 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 26 | 2050-12-10
26 | 0.049104 | Cleared | RA4 | 2040-06-30 |  |  | 0.049104 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 27 | 2050-12-10
27 | 0.17228 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.17228 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 28 | 2050-12-10
28 | 0.053529 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.053529 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 29 | 2050-12-10
29 | 0.018398 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.018398 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 30 | 2050-12-10
30 | 0.55429 | Existing Farm Track | RA4 | 2040-06-30 |  |  | 0.55429 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 31 | 2050-12-10
31 | 0.049937 | Cleared | RA4 | 2040-06-30 |  |  | 0.049937 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 32 | 2050-12-10
32 | 0.014391 | Switchyard | RA4 | 2040-06-30 |  |  | 0.014391 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 33 | 2050-12-10
33 | 0.21535 | Existing Farm Track | RA1 | 30/6/2037 |  |  | 0.21535 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 34 | 2046-12-10
34 | 0.046949 | Access Track | RA1 | 30/6/2037 |  |  | 0.046949 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 35 | 2046-12-10
35 | 0.10932 | Access Track | RA1 | 30/6/2037 |  |  | 0.10932 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 36 | 2046-12-10
36 | 0.084417 | Access Track | RA1 | 30/6/2037 |  |  | 0.084417 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 37 | 2046-12-10
37 | 0.14692 | Access Track | RA1 | 30/6/2037 |  |  | 0.14692 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 38 | 2046-12-10
38 | 0.033641 | Access Track | RA1 | 30/6/2037 |  |  | 0.033641 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 39 | 2046-12-10
39 | 0.11634 | Access Track | RA1 | 30/6/2037 |  |  | 0.11634 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 40 | 2046-12-10
40 | 0.12137 | Access Track | RA1 | 30/6/2037 |  |  | 0.12137 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 41 | 2046-12-10
41 | 0.035086 | Access Track | RA1 | 30/6/2037 |  |  | 0.035086 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 42 | 2046-12-10
42 | 0.0099323 | Access Track | RA1 | 30/6/2037 |  |  | 0.0099323 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 43 | 2046-12-10
43 | 0.012828 | Switchyard | RA4 | 2040-06-30 |  |  | 0.012828 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 44 | 2050-12-10
44 | 0.11683 | Cleared | RA4 | 2040-06-30 |  |  | 0.11683 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 45 | 2050-12-10
45 | 0.077421 | Rock Lined Drain | RA5 | 30/6/2023 |  |  | 0.077421 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 46 | 2031-12-10
46 | 0.50631 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.50631 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 47 | 2050-12-10
47 | 0.39975 | Drain | RA4 | 2040-06-30 |  |  | 0.39975 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 48 | 2050-12-10
48 | 2.2641 | Dam Wall | RA3 | 2040-06-30 |  |  | 2.2641 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 49 | 2050-12-10
49 | 0.012197 | Switchyard | RA4 | 2040-06-30 |  |  | 0.012197 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 50 | 2050-12-10
50 | 0.095292 | Cleared | RA5 | 30/6/2023 |  |  | 0.095292 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 51 | 2031-12-10
51 | 0.49178 | Topsoil Stockpile | RA5 | 30/6/2023 |  |  | 0.49178 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 52 | 2031-12-10
52 | 0.79326 | Cleared | RA5 | 30/6/2023 |  |  | 0.79326 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 53 | 2031-12-10
53 | 0.013282 | Switchyard | RA4 | 2040-06-30 |  |  | 0.013282 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 54 | 2050-12-10
54 | 0.052643 | Cleared | RA4 | 2040-06-30 |  |  | 0.052643 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 55 | 2050-12-10
55 | 1.0339 | Dam Wall | RA3 | 2040-06-30 |  |  | 1.0339 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 56 | 2050-12-10
56 | 0.030265 | Cleared | RA4 | 2040-06-30 |  |  | 0.030265 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 57 | 2050-12-10
57 | 0.18407 | Haul Road Drain | RA4 | 2040-06-30 |  |  | 0.18407 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 58 | 2050-12-10
58 | 0.22058 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.22058 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 59 | 2031-12-10
59 | 0.072525 | Cleared | RA4 | 2040-06-30 |  |  | 0.072525 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 60 | 2050-12-10
60 | 0.047686 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.047686 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 61 | 2050-12-10
61 | 0.037648 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.037648 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 62 | 2050-12-10
62 | 0.10761 | Access Track | RA4 | 2040-06-30 |  |  | 0.10761 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 63 | 2050-12-10
63 | 0.52944 | Cleared | RA5 | 30/6/2023 |  |  | 0.52944 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 64 | 2031-12-10
64 | 1.2353 | Cleared Not Topsoil Stripped | RA5 | 30/6/2023 |  |  | 1.2353 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 65 | 2031-12-10
65 | 0.29976 | Cleared | RA4 | 2040-06-30 |  |  | 0.29976 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 66 | 2050-12-10
66 | 6.2584 | Cleared | RA5 | 30/6/2023 |  |  | 6.2584 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 67 | 2031-12-10
67 | 0.05617 | Cleared | RA5 | 30/6/2023 |  |  | 0.05617 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 68 | 2031-12-10
68 | 8.5742 | Cleared | RA5 | 30/6/2023 |  |  | 8.5742 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 69 | 2031-12-10
69 | 0.29747 | Access Track | RA5 | 30/6/2023 |  |  | 0.29747 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 70 | 2031-12-10
70 | 0.62093 | Cleared | RA5 | 30/6/2023 |  |  | 0.62093 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 71 | 2031-12-10
71 | 0.16576 | Cleared | RA4 | 2040-06-30 |  |  | 0.16576 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 72 | 2050-12-10
72 | 3.2473 | Cleared Not Topsoil Stripped | RA4 | 2040-06-30 |  |  | 3.2473 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 73 | 2050-12-10
73 | 0.080121 | Pöwerline Corridor | RA4 | 2040-06-30 |  |  | 0.080121 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 74 | 2050-12-10
74 | 2.1862 | Pöwerline Corridor | RA4 | 2040-06-30 |  |  | 2.1862 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 75 | 2050-12-10
75 | 1.2134 | Pöwerline Corridor | RA4 | 2040-06-30 |  |  | 1.2134 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 76 | 2050-12-10
76 | 0.32578 | Access Track | RA4 | 2040-06-30 |  |  | 0.32578 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 77 | 2050-12-10
77 | 0.19533 | Access Track | RA4 | 2040-06-30 |  |  | 0.19533 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 78 | 2050-12-10
78 | 0.24442 | Pöwerline Corridor | RA4 | 2040-06-30 |  |  | 0.24442 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 79 | 2050-12-10
79 | 0.11212 | Access Track | RA4 | 2040-06-30 |  |  | 0.11212 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 80 | 2050-12-10
80 | 18.1363 | Cleared Not Topsoil Stripped | RA5 | 30/6/2023 |  |  | 18.1363 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 81 | 2031-12-10
81 | 3.3875 | Isaac Plains Mine Access Road | RA3 | 2040-06-30 |  |  | 3.3875 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 82 | 2050-12-10
82 | 11.1268 | Cleared Not Topsoil Stripped | RA5 | 30/6/2023 |  |  | 11.1268 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 83 | 2031-12-10
83 | 2.9931 | Cleared | RA4 | 2040-06-30 |  |  | 2.9931 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 84 | 2050-12-10
84 | 1.631 | Cleared | RA4 | 2040-06-30 |  |  | 1.631 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 85 | 2050-12-10
85 | 5.0087 | Cleared | RA4 | 2040-06-30 |  |  | 5.0087 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 86 | 2050-12-10
86 | 3.046 | ROM Haul Road to Isaac Plains | RA3 | 2040-06-30 |  |  | 3.046 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 87 | 2050-12-10
87 | 0.036961 | Laydown Yard | RA4 | 2040-06-30 |  |  | 0.036961 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 88 | 2050-12-10
88 | 0.79477 | Cleared | RA5 | 30/6/2023 |  |  | 0.79477 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 89 | 2031-12-10
89 | 1.4023 | Cleared | RA5 | 30/6/2023 |  |  | 1.4023 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 90 | 2031-12-10
90 | 3.7109 | Cleared | RA4 | 2040-06-30 |  |  | 3.7109 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 91 | 2050-12-10
91 | 0.14011 | Cleared | RA4 | 2040-06-30 |  |  | 0.14011 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 92 | 2050-12-10
92 | 1.327 | Cleared | RA5 | 30/6/2023 |  |  | 1.327 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 93 | 2031-12-10
93 | 0.5391 | Cleared | RA5 | 30/6/2023 |  |  | 0.5391 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 94 | 2031-12-10
94 | 0.013936 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.013936 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 95 | 2050-12-10
95 | 0.031216 | HV Workshop Hardstand | RA4 | 2040-06-30 |  |  | 0.031216 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 96 | 2050-12-10
96 | 11.3012 | ROM Coal Pad | RA3 | 2040-06-30 |  |  | 11.3012 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 97 | 2050-12-10
97 | 0.10001 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.10001 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 98 | 2050-12-10
98 | 0.14476 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.14476 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 99 | 2050-12-10
99 | 0.27706 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.27706 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 100 | 2050-12-10
100 | 0.2961 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.2961 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 101 | 2050-12-10
101 | 0.32734 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.32734 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 102 | 2050-12-10
102 | 0.078254 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.078254 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 103 | 2050-12-10
103 | 2.369 | Cleared | RA4 | 2040-06-30 |  |  | 2.369 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 104 | 2050-12-10
104 | 0.15026 | Cleared | RA4 | 2040-06-30 |  |  | 0.15026 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 105 | 2050-12-10
105 | 0.90259 | Cleared | RA4 | 2040-06-30 |  |  | 0.90259 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 106 | 2050-12-10
106 | 0.76644 | Cleared | RA4 | 2040-06-30 |  |  | 0.76644 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 107 | 2050-12-10
107 | 1.1723 | Clean Water Diversion Drain | RA5 | 30/6/2023 |  |  | 1.1723 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 108 | 2031-12-10
108 | 2.317 | Clean Water Diversion Drain | RA5 | 30/6/2023 |  |  | 2.317 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 109 | 2031-12-10
109 | 0.12561 | Cleared | RA5 | 30/6/2023 |  |  | 0.12561 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 110 | 2031-12-10
110 | 0.032808 | Access Track | RA1 | 30/6/2037 |  |  | 0.032808 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 111 | 2046-12-10
111 | 0.19877 | Cleared | RA4 | 2040-06-30 |  |  | 0.19877 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 112 | 2050-12-10
112 | 0.017547 | Access Track | RA1 | 30/6/2037 |  |  | 0.017547 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 113 | 2046-12-10
113 | 0.010268 | Cleared | RA4 | 2040-06-30 |  |  | 0.010268 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 114 | 2050-12-10
114 | 0.026135 | Cleared | RA4 | 2040-06-30 |  |  | 0.026135 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 115 | 2050-12-10
115 | 0.66547 | Access Track | RA4 | 2040-06-30 |  |  | 0.66547 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 116 | 2050-12-10
116 | 0.38918 | Access Track | RA1 | 30/6/2037 |  |  | 0.38918 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 117 | 2046-12-10
117 | 0.12865 | Cleared | RA4 | 2040-06-30 |  |  | 0.12865 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 118 | 2050-12-10
118 | 0.61329 | Cleared | RA4 | 2040-06-30 |  |  | 0.61329 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 119 | 2050-12-10
119 | 0.042833 | Access Track | RA1 | 30/6/2037 |  |  | 0.042833 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 120 | 2046-12-10
120 | 0.02573 | Access Track | RA4 | 2040-06-30 |  |  | 0.02573 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 121 | 2050-12-10
121 | 1.0787 | Laydown Yard | RA3 | 2040-06-30 |  |  | 1.0787 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 122 | 2050-12-10
122 | 0.4333 | Haul Road and Laydown Windrows | RA3 | 2040-06-30 |  |  | 0.4333 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 123 | 2050-12-10
123 | 0.23018 | Haul Road and Laydown Windrows | RA3 | 2040-06-30 |  |  | 0.23018 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 124 | 2050-12-10
124 | 0.37972 | Access Track | RA3 | 2040-06-30 |  |  | 0.37972 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 125 | 2050-12-10
125 | 1.3562 | Cleared | RA3 | 2040-06-30 |  |  | 1.3562 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 126 | 2050-12-10
126 | 0.079616 | Haul Road and Laydown Windrows | RA3 | 2040-06-30 |  |  | 0.079616 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 127 | 2050-12-10
127 | 1.7563 | Access Track | RA3 | 2040-06-30 |  |  | 1.7563 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 128 | 2050-12-10
128 | 0.067695 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.067695 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 129 | 2050-12-10
129 | 0.082817 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.082817 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 130 | 2050-12-10
130 | 0.072124 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.072124 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 131 | 2050-12-10
131 | 0.086042 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.086042 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 132 | 2050-12-10
132 | 0.25565 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.25565 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 133 | 2050-12-10
133 | 0.14204 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.14204 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 134 | 2050-12-10
134 | 0.042883 | Access Track | RA1 | 30/6/2037 |  |  | 0.042883 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 135 | 2046-12-10
135 | 1.0269 | Cleared | RA4 | 2040-06-30 |  |  | 1.0269 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 136 | 2050-12-10
136 | 0.044711 | Cleared | RA4 | 2040-06-30 |  |  | 0.044711 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 137 | 2050-12-10
137 | 0.7643 | Dirty Water Drain | RA4 | 30/6/2038 |  |  | 0.7643 | RA4_ | 2039-06-30 | 2039-09-30 | 2039-12-10 | 2040-12-10 | 2040-12-10 | 2043-12-10 | 2048-12-10 | 138 | 2048-12-10
138 | 0.90236 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.90236 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 139 | 2050-12-10
139 | 0.1066 | Cleared | RA4 | 2040-06-30 |  |  | 0.1066 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 140 | 2050-12-10
140 | 0.20152 | Haul Road | RA4 | 2040-06-30 |  |  | 0.20152 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 141 | 2050-12-10
141 | 0.11985 | Cleared | RA4 | 2040-06-30 |  |  | 0.11985 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 142 | 2050-12-10
142 | 0.72976 | Cleared | RA4 | 2040-06-30 |  |  | 0.72976 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 143 | 2050-12-10
143 | 1.1034 | Clean Water Diversion Drain | RA5 | 30/6/2023 |  |  | 1.1034 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 144 | 2031-12-10
144 | 0.54671 | Cleared | RA4 | 2040-06-30 |  |  | 0.54671 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 145 | 2050-12-10
145 | 0.47673 | Access Track | RA3 | 2040-06-30 |  |  | 0.47673 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 146 | 2050-12-10
146 | 0.078512 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.078512 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 147 | 2050-12-10
147 | 0.042581 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.042581 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 148 | 2050-12-10
148 | 0.055696 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.055696 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 149 | 2050-12-10
149 | 0.38601 | Cleared | RA5 | 30/6/2023 |  |  | 0.38601 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 150 | 2031-12-10
150 | 3.6457e-05 | Cleared | RA4 | 2040-06-30 |  |  | 3.6457e-05 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 151 | 2050-12-10
151 | 0.24572 | Cleared | RA5 | 30/6/2023 |  |  | 0.24572 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 152 | 2031-12-10
152 | 1.0471 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 1.0471 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 153 | 2031-12-10
153 | 5.4312 | Cleared | RA5 | 30/6/2023 |  |  | 5.4312 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 154 | 2031-12-10
154 | 0.015654 | Switchyard | RA4 | 2040-06-30 |  |  | 0.015654 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 155 | 2050-12-10
155 | 0.069845 | Cleared | RA4 | 2040-06-30 |  |  | 0.069845 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 156 | 2050-12-10
156 | 0.20589 | Cleared | RA4 | 2040-06-30 |  |  | 0.20589 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 157 | 2050-12-10
157 | 0.073563 | Cleared | RA4 | 2040-06-30 |  |  | 0.073563 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 158 | 2050-12-10
158 | 0.14283 | Cleared | RA5 | 30/6/2023 |  |  | 0.14283 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 159 | 2031-12-10
159 | 0.50528 | Cleared | RA5 | 30/6/2023 |  |  | 0.50528 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 160 | 2031-12-10
160 | 4.0306 | Cleared | RA5 | 30/6/2023 |  |  | 4.0306 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 161 | 2031-12-10
161 | 0.13862 | Cleared | RA4 | 2040-06-30 |  |  | 0.13862 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 162 | 2050-12-10
162 | 0.04332 | Cleared | RA4 | 2040-06-30 |  |  | 0.04332 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 163 | 2050-12-10
163 | 0.3027 | Cleared | RA4 | 2040-06-30 |  |  | 0.3027 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 164 | 2050-12-10
164 | 0.29019 | Access Track | RA4 | 2040-06-30 |  |  | 0.29019 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 165 | 2050-12-10
165 | 0.067821 | Cleared | RA4 | 2040-06-30 |  |  | 0.067821 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 166 | 2050-12-10
166 | 1.2728 | Cleared | RA4 | 2040-06-30 |  |  | 1.2728 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 167 | 2050-12-10
167 | 0.82716 | Access Track | RA4 | 2040-06-30 |  |  | 0.82716 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 168 | 2050-12-10
168 | 0.40268 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.40268 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 169 | 2031-12-10
169 | 0.81464 | Haul Road | RA3 | 2040-06-30 |  |  | 0.81464 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 170 | 2050-12-10
170 | 0.010727 | Dirty Water Drain | RA4 | 2040-06-30 |  |  | 0.010727 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 171 | 2050-12-10
171 | 0.020076 | Clean Water Diversion Drain | RA4 | 2040-06-30 |  |  | 0.020076 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 172 | 2050-12-10
172 | 0.07025 | Access Track | RA1 | 30/6/2037 |  |  | 0.07025 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 173 | 2046-12-10
173 | 0.12152 | Existing Farm Track | RA1 | 30/6/2037 |  |  | 0.12152 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 174 | 2046-12-10
174 | 0.2523 | Cleared | RA4 | 2040-06-30 |  |  | 0.2523 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 175 | 2050-12-10
175 | 0.065656 | Cleared | RA3 | 2040-06-30 |  |  | 0.065656 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 176 | 2050-12-10
176 | 0.91257 | Access Track | RA3 | 2040-06-30 |  |  | 0.91257 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 177 | 2050-12-10
177 | 0.1321 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.1321 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 178 | 2050-12-10
178 | 0.15182 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.15182 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 179 | 2050-12-10
179 | 0.08919 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.08919 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 180 | 2050-12-10
180 | 0.062574 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.062574 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 181 | 2050-12-10
181 | 0.33288 | Laydown Yard | RA5 | 30/6/2023 |  |  | 0.33288 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 182 | 2031-12-10
182 | 0.74196 | Cleared | RA5 | 30/6/2023 |  |  | 0.74196 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 183 | 2031-12-10
183 | 0.79778 | Access Track | RA4 | 2040-06-30 |  |  | 0.79778 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 184 | 2050-12-10
184 | 0.080083 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.080083 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 185 | 2050-12-10
185 | 0.15087 | Clean Water Diversion Drain | RA5 | 30/6/2023 |  |  | 0.15087 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 186 | 2031-12-10
186 | 0.86267 | Access Track | RA5 | 30/6/2023 |  |  | 0.86267 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 187 | 2031-12-10
187 | 0.06775 | Cleared | RA5 | 30/6/2023 |  |  | 0.06775 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 188 | 2031-12-10
188 | 0.076293 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.076293 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 189 | 2050-12-10
189 | 0.020945 | Dirty Water Drain | RA5 | 30/6/2023 |  |  | 0.020945 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 190 | 2031-12-10
190 | 0.067208 | Access Track | RA4 | 2040-06-30 |  |  | 0.067208 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 191 | 2050-12-10
191 | 0.15265 | Access Track | RA5 | 30/6/2023 |  |  | 0.15265 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 192 | 2031-12-10
192 | 0.96792 | Cleared | RA4 | 2040-06-30 |  |  | 0.96792 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 193 | 2050-12-10
193 | 0.044813 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.044813 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 194 | 2050-12-10
194 | 0.063133 | Dirty Water Drain | RA5 | 30/6/2023 |  |  | 0.063133 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 195 | 2031-12-10
195 | 0.021568 | Cleared | RA4 | 2040-06-30 |  |  | 0.021568 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 196 | 2050-12-10
196 | 0.7581 | Laydown Yard | RA5 | 30/6/2023 |  |  | 0.7581 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 197 | 2031-12-10
197 | 0.063314 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.063314 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 198 | 2050-12-10
198 | 0.020988 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.020988 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 199 | 2050-12-10
199 | 0.01873 | Dirty Water Drain | RA4 | 2040-06-30 |  |  | 0.01873 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 200 | 2050-12-10
200 | 0.040957 | Cleared | RA4 | 2040-06-30 |  |  | 0.040957 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 201 | 2050-12-10
201 | 3.4116 | Cleared | RA4 | 2040-06-30 |  |  | 3.4116 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 202 | 2050-12-10
202 | 0.53405 | Cleared | RA5 | 30/6/2023 |  |  | 0.53405 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 203 | 2031-12-10
203 | 2.7457 | Cleared | RA4 | 2040-06-30 |  |  | 2.7457 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 204 | 2050-12-10
204 | 0.0466 | Access Track | RA1 | 30/6/2037 |  |  | 0.0466 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 205 | 2046-12-10
205 | 0.13851 | Access Track | RA4 | 2040-06-30 |  |  | 0.13851 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 206 | 2050-12-10
206 | 0.026622 | Access Track | RA1 | 30/6/2037 |  |  | 0.026622 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 207 | 2046-12-10
207 | 0.29283 | Cleared | RA4 | 2040-06-30 |  |  | 0.29283 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 208 | 2050-12-10
208 | 1.2979 | Cleared | RA4 | 2040-06-30 |  |  | 1.2979 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 209 | 2050-12-10
209 | 0.27095 | Access Track | RA5 | 30/6/2023 |  |  | 0.27095 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 210 | 2031-12-10
210 | 4.7279 | Mine Water Dam | RA3 | 2040-06-30 |  |  | 4.7279 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 211 | 2050-12-10
211 | 1.5151 | Fill Point Dam | RA3 | 2040-06-30 |  |  | 1.5151 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 212 | 2050-12-10
212 | 0.149 | Mine Water Dam | RA3 | 2040-06-30 |  |  | 0.149 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 213 | 2050-12-10
213 | 0.069999 | Raw Water Dam | RA3 | 2040-06-30 |  |  | 0.069999 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 214 | 2050-12-10
214 | 0.094637 | MIA Water Dam | RA3 | 2040-06-30 |  |  | 0.094637 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 215 | 2050-12-10
215 | 0.4732 | MIA Water Dam | RA3 | 2040-06-30 |  |  | 0.4732 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 216 | 2050-12-10
216 | 0.46565 | Overburden Expit Dump | RA3 | 2040-06-30 |  |  | 0.46565 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 217 | 2050-12-10
217 | 0.021102 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.021102 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 218 | 2050-12-10
218 | 0.03951 | Sed Dam | RA3 | 2040-06-30 |  |  | 0.03951 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 219 | 2050-12-10
219 | 0.012301 | Building Main Admin (Small) | RA4 | 2040-06-30 |  |  | 0.012301 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 220 | 2050-12-10
220 | 0.0024016 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0024016 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 221 | 2050-12-10
221 | 0.0017601 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0017601 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 222 | 2050-12-10
222 | 0.0032363 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0032363 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 223 | 2050-12-10
223 | 0.0012643 | Building Demountable | RA4 | 2040-06-30 |  |  | 0.0012643 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 224 | 2050-12-10
224 | 0.43686 | Topsoil Stockpile | RA2 | 2039-06-30 |  |  | 0.43686 | RA2_ |  | 2039-07-30 | 2039-12-10 | 2040-12-10 | 2040-12-10 | 2043-12-10 | 2048-12-10 | 225 | 2048-12-10
225 | 0.27287 | Topsoil Stockpile | RA2 | 2040-06-30 |  |  | 0.27287 | RA2_ |  | 2040-07-30 | 2040-12-10 | 2041-12-10 | 2041-12-10 | 2044-12-10 | 2049-12-10 | 226 | 2049-12-10
226 | 0.63386 | Topsoil Stockpile | RA2 | 2040-06-30 |  |  | 0.63386 | RA2_ |  | 2040-07-30 | 2040-12-10 | 2041-12-10 | 2041-12-10 | 2044-12-10 | 2049-12-10 | 227 | 2049-12-10
227 | 0.60732 | Topsoil Stockpile | RA5 | 30/6/2023 |  |  | 0.60732 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 228 | 2031-12-10
228 | 0.50625 | ROM Mine Water Dam | RA3 | 2040-06-30 |  |  | 0.50625 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 229 | 2050-12-10
229 | 1.913 | Access Track | RA3 | 2040-06-30 |  |  | 1.913 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 230 | 2050-12-10
230 | 0.13162 | Access Track | RA4 | 2040-06-30 |  |  | 0.13162 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 231 | 2050-12-10
231 | 0.030465 | Access Track | RA4 | 2040-06-30 |  |  | 0.030465 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 232 | 2050-12-10
232 | 0.20311 | Access Track | RA4 | 2040-06-30 |  |  | 0.20311 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 233 | 2050-12-10
233 | 0.81205 | Access Track | RA3 | 2040-06-30 |  |  | 0.81205 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 234 | 2050-12-10
234 | 0.38443 | Cleared Highwall Underpass | RA3 | 2040-06-30 |  |  | 0.38443 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 235 | 2050-12-10
235 | 0.20742 | Highway Underpass | RA3 | 2040-06-30 |  |  | 0.20742 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 236 | 2050-12-10
236 | 0.29624 | Cleared Highwall Underpass | RA3 | 2040-06-30 |  |  | 0.29624 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 237 | 2050-12-10
237 | 0.0059319 | Cleared | RA4 | 2040-06-30 |  |  | 0.0059319 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 238 | 2050-12-10
238 | 0.051914 | Cleared | RA4 | 2040-06-30 |  |  | 0.051914 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 239 | 2050-12-10
239 | 1.6729 | Cleared | RA5 | 30/6/2023 |  |  | 1.6729 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 240 | 2031-12-10
240 | 0.01333 | Cleared | RA1 | 30/6/2037 |  |  | 0.01333 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 241 | 2046-12-10
241 | 0.014928 | Cleared | RA1 | 30/6/2037 |  |  | 0.014928 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 242 | 2046-12-10
242 | 0.024595 | Cleared | RA1 | 30/6/2037 |  |  | 0.024595 | RA1_ |  |  | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 243 | 2046-12-10
243 | 0.0030111 | Access Track | RA4 | 2040-06-30 |  |  | 0.0030111 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 244 | 2050-12-10
244 | 0.10545 | Access Track | RA4 | 2040-06-30 |  |  | 0.10545 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 245 | 2050-12-10
245 | 0.0029301 | Cleared | RA4 | 2040-06-30 |  |  | 0.0029301 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 246 | 2050-12-10
246 | 0.07091 | Cleared | RA4 | 2040-06-30 |  |  | 0.07091 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 247 | 2050-12-10
247 | 0.2933 | Cleared | RA4 | 2040-06-30 |  |  | 0.2933 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 248 | 2050-12-10
248 | 0.054735 | Cleared | RA4 | 2040-06-30 |  |  | 0.054735 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 249 | 2050-12-10
249 | 0.024167 | Access Track | RA5 | 30/6/2023 |  |  | 0.024167 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 250 | 2031-12-10
250 | 0.10983 | Access Track | RA3 | 2040-06-30 |  |  | 0.10983 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 251 | 2050-12-10
251 | 0.37437 | Access Track | RA3 | 2040-06-30 |  |  | 0.37437 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 252 | 2050-12-10
252 | 1.4815 | Cleared | RA5 | 30/6/2023 |  |  | 1.4815 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 253 | 2031-12-10
253 | 0.829 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.829 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 254 | 2050-12-10
254 | 0.35748 | Cleared | RA4 | 2040-06-30 |  |  | 0.35748 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 255 | 2050-12-10
255 | 0.47132 | Cleared | RA5 | 30/6/2023 |  |  | 0.47132 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 256 | 2031-12-10
256 | 1.3438 | Cleared | RA5 | 30/6/2023 |  |  | 1.3438 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 257 | 2031-12-10
257 | 0.35379 | Cleared | RA4 | 2040-06-30 |  |  | 0.35379 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 258 | 2050-12-10
258 | 0.32952 | Cleared | RA4 | 2040-06-30 |  |  | 0.32952 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 259 | 2050-12-10
259 | 9.7638 | Levee North | RA4 | 30/6/2037 |  |  | 9.7638 | RA4_ | 2038-06-30 | 2038-09-30 | 2038-12-10 | 2039-12-10 | 2039-12-10 | 2042-12-10 | 2047-12-10 | 260 | 2047-12-10
260 | 1.5314 | Cleared | RA5 | 30/6/2023 |  |  | 1.5314 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 261 | 2031-12-10
261 | 1.9518 | Dam Wall | RA3 | 2040-06-30 |  |  | 1.9518 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 262 | 2050-12-10
262 | 0.43309 | Cleared Not Topsoil Stripped | RA4 | 2040-06-30 |  |  | 0.43309 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 263 | 2050-12-10
263 | 0.25618 | Cleared | RA4 | 2040-06-30 |  |  | 0.25618 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 264 | 2050-12-10
264 | 0.12132 | Access Track | RA5 | 30/6/2023 |  |  | 0.12132 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 265 | 2031-12-10
265 | 0.28738 | Dam Wall | RA3 | 2040-06-30 |  |  | 0.28738 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 266 | 2050-12-10
266 | 0.30929 | Drain | RA5 | 30/6/2023 |  |  | 0.30929 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 267 | 2031-12-10
267 | 0.016563 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.016563 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 268 | 2031-12-10
268 | 0.11448 | Haul Road and Laydown Windrows | RA4 | 2040-06-30 |  |  | 0.11448 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 269 | 2050-12-10
269 | 0.15359 | Topsoil Stockpile | RA5 | 30/6/2023 |  |  | 0.15359 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 270 | 2031-12-10
270 | 0.035043 | Haul Road and Laydown Windrows | RA5 | 30/6/2023 |  |  | 0.035043 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 271 | 2031-12-10
271 | 0.24253 | Main Site Access and Haul Road | RA5 | 30/6/2023 |  |  | 0.24253 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 272 | 2031-12-10
272 | 1.31 | Cleared | RA4 | 2040-06-30 |  |  | 1.31 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 273 | 2050-12-10
273 | 1.1261 | Main Site Access and Haul Road | RA5 | 30/6/2023 |  |  | 1.1261 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 274 | 2031-12-10
274 | 0.83819 | Cleared | RA4 | 2040-06-30 |  |  | 0.83819 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 275 | 2050-12-10
275 | 0.32956 | Cleared | RA4 | 2040-06-30 |  |  | 0.32956 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 276 | 2050-12-10
276 | 1.2478 | Cleared | RA5 | 30/6/2023 |  |  | 1.2478 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 277 | 2031-12-10
277 | 0.024859 | Cleared | RA4 | 2040-06-30 |  |  | 0.024859 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 278 | 2050-12-10
278 | 0.76521 | Cleared | RA4 | 2040-06-30 |  |  | 0.76521 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 279 | 2050-12-10
279 | 0.87607 | Cleared | RA4 | 2040-06-30 |  |  | 0.87607 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 280 | 2050-12-10
280 | 0.88132 | Cleared | RA4 | 2040-06-30 |  |  | 0.88132 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 281 | 2050-12-10
281 | 1.5144 | Cleared | RA5 | 30/6/2023 |  |  | 1.5144 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 282 | 2031-12-10
282 | 0.60459 | Cleared | RA5 | 30/6/2023 |  |  | 0.60459 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 283 | 2031-12-10
283 | 0.15605 | Access Track | RA4 | 2040-06-30 |  |  | 0.15605 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 284 | 2050-12-10
284 | 0.42513 | Access Track | RA3 | 2040-06-30 |  |  | 0.42513 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 285 | 2050-12-10
285 | 0.74093 | Access Track | RA3 | 2040-06-30 |  |  | 0.74093 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 286 | 2050-12-10
286 | 0.22884 | Cleared | RA5 | 30/6/2023 |  |  | 0.22884 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 287 | 2031-12-10
287 | 0.14448 | Access Track | RA5 | 30/6/2023 |  |  | 0.14448 | RA5_ | RM5: 2023-12-10; RM6: 2026-12-10; RM7: 2031-12-10 | 288 | 2031-12-10
288 | 0.22595 | Cleared | RA4 | 30/6/2038 |  |  | 0.22595 | RA4_ | 2039-06-30 | 2039-09-30 | 2039-12-10 | 2040-12-10 | 2040-12-10 | 2043-12-10 | 2048-12-10 | 289 | 2048-12-10
289 | 1.6858 | Cleared | RA4 | 2040-06-30 |  |  | 1.6858 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 290 | 2050-12-10
290 | 0.30862 | Laydown Yard | RA3 | 2040-06-30 |  |  | 0.30862 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 291 | 2050-12-10
291 | 1.1958 | Cleared | RA3 | 2040-06-30 |  |  | 1.1958 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 292 | 2050-12-10
292 | 0.051536 | Communications Tower | RA3 | 2040-06-30 |  |  | 0.051536 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 293 | 2050-12-10
293 | 0.54547 | Access Track | RA4 | 2040-06-30 |  |  | 0.54547 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 294 | 2050-12-10
294 | 2.1613 | Access Track | RA4 | 2040-06-30 |  |  | 2.1613 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 295 | 2050-12-10
295 | 0.98095 | Access Track | RA4 | 2040-06-30 |  |  | 0.98095 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 296 | 2050-12-10
296 | 7.4437 | Clean Water Diversion Drain | RA4 | 2040-06-30 |  |  | 7.4437 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 297 | 2050-12-10
297 | 75.0798 | Final Void | IA1 | 2039-06-30 |  |  | 75.0798 | IA1_ |  |  | 2039-12-10 | 2040-12-10 | 2040-12-10 | 2043-12-10 | 2048-12-10 | 298 | 2048-12-10
298 | 79.9596 | RA2 | RA2 | 30/6/2038 |  |  | 79.9596 | RA2_ |  | 2038-07-30 | 2038-12-10 | 2039-12-10 | 2039-12-10 | 2042-12-10 | 2047-12-10 | 299 | 2047-12-10
299 | 49.0785 | RA2 | RA2 | 30/6/2034 |  |  | 49.0785 | RA2_ |  | 2034-07-30 | 2034-12-10 | 2035-12-10 | 2035-12-10 | 2038-12-10 | 2043-12-10 | 300 | 2043-12-10
300 | 40.5921 | RA2 | RA2 | 30/6/2026 |  |  | 40.5921 | RA2_ |  | 2026-07-30 | 2026-12-10 | 2027-12-10 | 2027-12-10 | 2030-12-10 | 2035-12-10 | 301 | 2035-12-10
301 | 40.6832 | RA2 | RA2 | 30/6/2027 |  |  | 40.6832 | RA2_ |  | 2027-07-30 | 2027-12-10 | 2028-12-10 | 2028-12-10 | 2031-12-10 | 2036-12-10 | 302 | 2036-12-10
302 | 31.1059 | RA2 | RA2 | 30/6/2029 |  |  | 31.1059 | RA2_ |  | 2029-07-30 | 2029-12-10 | 2030-12-10 | 2030-12-10 | 2033-12-10 | 2038-12-10 | 303 | 2038-12-10
303 | 23.5201 | RA2 | RA2 | 30/6/2028 |  |  | 23.5201 | RA2_ |  | 2028-07-30 | 2028-12-10 | 2029-12-10 | 2029-12-10 | 2032-12-10 | 2037-12-10 | 304 | 2037-12-10
304 | 53.729 | RA2 | RA2 | 30/6/2031 |  |  | 53.729 | RA2_ |  | 2031-07-30 | 2031-12-10 | 2032-12-10 | 2032-12-10 | 2035-12-10 | 2040-12-10 | 305 | 2040-12-10
305 | 43.5071 | RA2 | RA2 | 30/6/2032 |  |  | 43.5071 | RA2_ |  | 2032-07-30 | 2032-12-10 | 2033-12-10 | 2033-12-10 | 2036-12-10 | 2041-12-10 | 306 | 2041-12-10
306 | 8.9104 | RA2 | RA2 | 2039-06-30 |  |  | 8.9104 | RA2_ |  | 2039-07-30 | 2039-12-10 | 2040-12-10 | 2040-12-10 | 2043-12-10 | 2048-12-10 | 307 | 2048-12-10
307 | 55.1995 | RA2 | RA2 | 30/6/2037 |  |  | 55.1995 | RA2_ |  | 2037-07-30 | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 308 | 2046-12-10
308 | 38.0183 | RA2 | RA2 | 30/6/2036 |  |  | 38.0183 | RA2_ |  | 2036-07-30 | 2036-12-10 | 2037-12-10 | 2037-12-10 | 2040-12-10 | 2045-12-10 | 309 | 2045-12-10
309 | 37.3742 | RA2 | RA2 | 30/6/2035 |  |  | 37.3742 | RA2_ |  | 2035-07-30 | 2035-12-10 | 2036-12-10 | 2036-12-10 | 2039-12-10 | 2044-12-10 | 310 | 2044-12-10
310 | 33.9258 | RA2 | RA2 | 30/6/2033 |  |  | 33.9258 | RA2_ |  | 2033-07-30 | 2033-12-10 | 2034-12-10 | 2034-12-10 | 2037-12-10 | 2042-12-10 | 311 | 2042-12-10
311 | 52.8574 | RA2 | RA2 | 30/6/2030 |  |  | 52.8574 | RA2_ |  | 2030-07-30 | 2030-12-10 | 2031-12-10 | 2031-12-10 | 2034-12-10 | 2039-12-10 | 312 | 2039-12-10
312 | 35.333 | RA2 | RA2 | 30/6/2036 |  |  | 35.333 | RA2_ |  | 2036-07-30 | 2036-12-10 | 2037-12-10 | 2037-12-10 | 2040-12-10 | 2045-12-10 | 313 | 2045-12-10
313 | 24.2718 | RA2 | RA4 | 2040-06-30 |  |  | 24.2718 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 314 | 2050-12-10
314 | 5.3018 | RA2 | RA4 | 30/6/2036 |  |  | 5.3018 | RA4_ | 2037-06-30 | 2037-09-30 | 2037-12-10 | 2038-12-10 | 2038-12-10 | 2041-12-10 | 2046-12-10 | 315 | 2046-12-10
315 | 17.1066 | RA2 | RA4 | 2040-06-30 |  |  | 17.1066 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 316 | 2050-12-10
316 | 0.083191 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.083191 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 317 | 2031-12-10
317 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 318 | 2031-12-10
318 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 319 | 2031-12-10
319 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 320 | 2031-12-10
320 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 321 | 2031-12-10
321 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 322 | 2031-12-10
322 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 323 | 2031-12-10
323 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 324 | 2031-12-10
324 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 325 | 2031-12-10
325 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 326 | 2031-12-10
326 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 327 | 2031-12-10
327 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 328 | 2031-12-10
328 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 329 | 2031-12-10
329 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 330 | 2031-12-10
330 | 0.080068 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.080068 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 331 | 2031-12-10
331 | 0.036548 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.036548 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 332 | 2031-12-10
332 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 333 | 2031-12-10
333 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 334 | 2031-12-10
334 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 335 | 2031-12-10
335 | 0.065892 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.065892 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 336 | 2031-12-10
336 | 0.088106 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.088106 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 337 | 2031-12-10
337 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 338 | 2031-12-10
338 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 339 | 2031-12-10
339 | 0.089947 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.089947 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 340 | 2031-12-10
340 | 0.089731 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.089731 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 341 | 2031-12-10
341 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 342 | 2031-12-10
342 | 0.09 | Rehabilitated Drill Site | RA1 | 2023-06-30 |  |  | 0.09 | RA1_ |  |  | 2023-12-10 | 2023-12-10 | 2023-12-10 | 2026-12-10 | 2031-12-10 | 343 | 2031-12-10
343 | 13.6722 | Levee South | RA4 | 2040-06-30 |  |  | 13.6722 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 344 | 2050-12-10
344 | 0.84335 | Access Track | RA3 | 2040-06-30 |  |  | 0.84335 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 345 | 2050-12-10
345 | 0.14961 | Access Track | RA3 | 2040-06-30 |  |  | 0.14961 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 346 | 2050-12-10
346 | 1.719 | Hardstand Gravel Base | RA3 | 2040-06-30 |  |  | 1.719 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 347 | 2050-12-10
347 | 3.2243 | RA2 | RA4 | 2040-06-30 |  |  | 3.2243 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 348 | 2050-12-10
348 | 5.3849 | RA2 | RA4 | 2040-06-30 |  |  | 5.3849 | RA4_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 349 | 2050-12-10
349 | 1.9199 | RA2 | RA3 | 2040-06-30 |  |  | 1.9199 | RA3_ | 2041-06-30 | 2041-09-30 | 2041-12-10 | 2042-12-10 | 2042-12-10 | 2045-12-10 | 2050-12-10 | 350 | 2050-12-10