## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Waste Rock Emplacement
Total rehabilitation area size (ha) |  |  |  | 10.7
Commencement of first milestone: RM2 |  |  |  | 2033-12-10
PMLU |  |  |  | Native Habitat
Date area is available | 2033-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 10.7
Milestone completed by | 2037-12-10 | 2050-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM2 | 10.7
RM7 | 1.7
RM9 | 1.7
RM10 |  | 1.7
RM12 |  | 10.7
RM13 |  |  | 10.7
#REF!
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Topsoil Stockpiles
Total rehabilitation area size (ha) |  |  |  | 5.7
Commencement of first milestone: RM4 |  |  |  | 2035-12-10
PMLU |  |  |  | Low Intensity Cattle Grazing
Date area is available | 2035-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 5.7
Milestone completed by | 2038-12-10 | 2050-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM5 | 5.7
RM8 | 5.7
RM11 |  | 5.7
RM14 |  |  | 5.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Leachate Management Dam (LMD) and Erosion and Sediment Control Facility
Total rehabilitation area size (ha) |  |  |  | 0.9
Commencement of first milestone: RM5 |  |  |  | 2025-12-10
PMLU |  |  |  | Native Habitat
Date area is available | 2025-12-10 | 2043-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.5 | 0.9
Milestone completed by | 2028-12-10 | 2045-12-10 | 2055-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 0.5 | 0.9
RM6 | 0.5 | 0.9
RM7 | 0.5 | 0.9
RM8 | 0.5 | 0.9
RM10 |  |  | 0.5
RM13 |  |  |  | 0.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | CDA, CDB, PPD, Sediment Dams and Erosion and Sediment Control Facilities
Total rehabilitation area size (ha) |  |  |  | 13
Commencement of first milestone: RM5 |  |  |  | 2039-12-10
PMLU |  |  |  | Low Intensity Cattle Grazing
Date area is available | 2039-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 13
Milestone completed by | 2052-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 13
RM6 | 13
RM7 | 13
RM8 | 13
RM14 |  | 13
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Infrastructure - waste disposal trench, LMD area, explosive magazine
Total rehabilitation area size (ha) |  |  |  | 11.8
Commencement of first milestone: RM6 |  |  |  | 2025-12-10
PMLU |  |  |  | Native Habitat
Date area is available | 2025-12-10 | 2032-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.7 | 8 | 11.8
Milestone completed by | 2028-12-10 | 1935-12-10 | 2050-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 |  | 0.8
RM3 | 0.7 | 8
RM5 |  | 8
RM7 | 0.7 | 8
RM8 | 0.7 | 8
RM10 |  |  | 11.8
RM13 |  |  |  | 11.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Infrastructure
Total rehabilitation area size (ha) |  |  |  | 35.4
Commencement of first milestone: RM1 |  |  |  | 2032-12-10
PMLU |  |  |  | Low Intensity Cattle Grazing
Date area is available | 2032-12-10 | 2039-12-10 | 2044-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 15.7 | 29.3 | 35.4
Milestone completed by | 2035-12-10 | 2041-12-10 | 2046-12-10 | 1950-12-10 | 1960-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 6.5 | 20.1 | 35.4
RM3 | 15.7 | 29.3 | 35.4
RM5 | 15.7 | 29.3 | 35.4
RM7 | 15.7 | 29.3 | 35.4
RM8 | 15.7 | 29.3 | 35.4
RM11 |  |  |  | 29.3
RM14 |  |  |  |  | 35.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Run of Mine (ROM) Pad, Paste Plant and Batch Plant
Total rehabilitation area size (ha) |  |  |  | 10.1
Commencement of first milestone: RM1 |  |  |  | 2032-12-10
PMLU |  |  |  | Low Intensity Cattle Grazing
Date area is available | 2032-12-10 |  | 2052-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 10.1
Milestone completed by | 2035-12-10 | 2050-12-10 | 2053-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 10.1
RM3 | 10.1
RM5 | 5.3 |  | 4.8
RM7 | 5.3 |  | 4.8
RM8 | 5.3 |  | 4.8
RM11 |  | 5.3
RM14 |  |  |  | 10.1
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Exploration, Roads, Tracks and Borrow Sites
Total rehabilitation area size (ha) |  |  |  | 20.7
Commencement of first milestone: RM6 |  |  |  | 2032-12-10
PMLU |  |  |  | Native Habitat
Date area is available | 2032-12-10 | 2052-12-10 | 2059-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.5 | 6.5 | 20.2 | 20.7
Milestone completed by | 2035-12-10 | 2053-12-10 | 2060-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.5
RM3 | 1 |  | 14.7
RM5 |  | 5
RM7 | 1 | 6 | 19.7
RM8 | 1 |  | 13.8
RM13 |  |  |  | 20.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Exploration, Roads, Tracks and Borrow sites
Total rehabilitation area size (ha) |  |  |  | 38.5
Commencement of first milestone: RM6 |  |  |  | 2032-12-10
PMLU |  |  |  | Low Intensity Cattle Grazing
Date area is available | 2032-12-10 | 2035-12-10 | 2039-12-10 | 2044-12-10 | 2052-12-10 | 2059-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 2.4 | 3.1 | 3.5 | 4.2 | 17.6 | 38.5
Milestone completed by | 2035-12-10 | 1938-12-10 | 1942-12-10 | 2045-12-10 | 2053-12-10 | 2060-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.3
RM3 | 2.1 | 3.1 | 3.5 | 4.2
RM5 |  |  |  |  | 13.4
RM7 | 2.1 | 3.1 | 3.5 | 4.2 | 17.6
RM8 | 2.1 | 3.1 | 3.5 | 4.2 | 17.6
RM14 | [5 empty] | 38.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10
Relevant activities |  |  |  | Underground Openings - Shafts, decline, portal
Total rehabilitation area size (ha) |  |  |  | 0.6
Commencement of first milestone: RM3 |  |  |  | 2032-12-10
PMLU |  |  |  | Native Habitat
Date area is available | 2035-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.6
Milestone completed by | 2045-12-10 | 2060-12-10 |  | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 0.6
RM4 | 0.6
RM7 | 0.6
RM8 | 0.6
RM13 |  | 0.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal (Fixed Plant) | Milestone criteria
RM2 | Infrastructure decommissioning and removal (Fixed Plant) | a) Crest treatments have been applied, and monitoring stations installed consistent with the WRE engineering design with Quality Assurance/Quality Control measures specified by an RPEQ to achieve the following performance objectives: i. Maximum hydraulic conductivity of the cover system is < 1.0 x 10-9m/s for bituminous geomembrane cover ii. Oxygen ingress to the underlying material is restricted iii. Effective overlap/joining of materials b) Batter treatments have been applied consistent with the WRE engineering design with Quality Assurance/Quality Control measures specified by an RPEQ c) A suitably qualified and experienced person has prepared an As-Constructed Report that details the works undertaken, and certified by an RPEQ that construction and encapsulation works were completed in accordance with design specifications, including: i. sub grade preparation ii. chemical and physical properties iii. geometry and spatial characteristics iv. drainage and flow conveyance
RM3 | Remediation of contaminated land | a) Contaminated land investigation completed by suitably qualified person b) Soils and sediments contaminated by site activities have been assessed and managed (e.g. removed/remediated), as recommended by suitably qualified person c) A contaminated land survey carried out by an suitably qualified person including whether contamination unsuitable for the post-mining land use is occurring
RM4 | Landform development and reshaping / re-profiling (Underground Openings) | a)Upper sections of ventilation shafts have been backfilled with ROM borrow material to preclude access to underground workings b)Surface subsidence generated depression as determined by subsidence monitoring is no greater than > 500 mm c) Upper section of mine decline has been backfilled with ROM borrow material to preclude access to underground workings d) Portal sealed and box-cut backfilled with inert material to form a free draining final surface e) A suitably qualified and experienced person has prepared an As-Constructed Report that details the works undertaken, and certified that construction and backfilling of underground openings met the design intent
RM5 | Landform development and reshaping / re-profiling (ROM Pad, Paste Plant and Batch Plant, Infrastructure Area, Topsoil Stockpiles and Borrow Sites) | a) Terrain has been reprofiled with disturbed slopes not steeper than 4 H : 1 V and appropriately verified, with the exception of Borrow Area C b) A suitably qualified and experienced person has prepared a geotechnical stability report and safety assessment for slopes > 30 degrees and > 5m in height## c) Erosion and sediment control systems have been installed
RM6 | Landform development and reshaping / re-profiling (Regulated Dams and Erosion and Sediment Control Facilities) | a) Recommendation by suitably qualified and experienced engineer that Regulated Dam status can be rescinded b) Erosion and sediment control systems have been installed c)Terrain has been reprofiled with disturbed slopes not steeper than 4 H : 1 V and verified by an appropriately qualified person d) Erosion and sediment control facilities (excluding facilities agreed with stakeholders for retention) decommissioned and left free draining e) Mine affected water will be either remediated, removed or disposed in accordance with relevant regulations. f) Contaminated sediment, along with synthetic liners, is remediated, removed or disposed in accordance with relevant regulations.
RM7 | Surface Preparation | a) A suitably qualified person has assessed the characteristics of the soil and growth media and defined requirements for ameliorants and other treatments necessary to achieve the PMLU b) Ameliorants and other treatments (including application of stockpiled growth media) have been applied, as recommended by suitably qualified person. c) Final surface has been deep ripped on surfaces, with the exception of WRE (RA1) and Borrow Area C (RA8) d)Placement of minimum thickness of 150mm of growth media at ROM, Paste Plant and Batch Plant Area (RA7) and borrow site within (RA9), subject to recommendations by suitably qualified person.
RM8 | Revegetation (all disturbed areas excluding WRE and Borrow Area C) | a)Complete seeding using seed mix and sowing rates described in Table 19 of the PRC Plan, or based on more recent seed mix and sowing rates as recommendations by suitably qualified person
RM9 | Revegetation (WRE) | a)Complete seeding to the WRE crest area using seed mix and sowing rates described in Table 19 of the PRC Plan, or based on more recent seed mix and sowing rates as recommendations by suitably qualified person
RM10 | Achievement of surface requirements - Vegetation on Developmental Trajectory (Native Habitat areas) | a) Corrective actions that are recommended by a suitably qualified persons identified through the rehabilitation monitoring methodology has been implemented. b) Corrective action arising from the routine inspections program have been undertaken to include weed control, erosion repair, livestock management. c) Ecosytem Function Analysis index scores compared to equivalent reference sites are: - Stability > 50 % of reference - Infiltration > 40 % of reference - Nutrient Cycling > 20 % of reference - Species Richness > 40 % of reference - Vegetation Dynamics > 20 % of reference - Habitat Complexity > 40 % of reference
RM11 | Achievement of surface requirements - Vegetation on Developmental Trajectory (Low Intensity Cattle Grazing areas) | a)Corrective actions that are recommended by a suitably qualitied persons identified through the rehabilitation monitoring methodology has been implemented. b)Corrective action arising from the routine inspections program have been undertaken to include weed control, erosion repair, livestock management. c) Ecosystem Function Analysis index scores compared to equivalent reference sites are: - Stability > 50 % of reference - Infiltration > 40 % of reference - Nutrient Cycling > 20 % of reference - Vegetation Dynamics > 20 % of reference d) The basal area of grasses is > 30 % of reference
RM12 | Achievement of surface requirements - WRE | a) A suitably qualified person has assessed the performance monitoring data for the WRE and verified that: -No active rill/gully erosion > 500 mm - Water flux into contained PAF waste is < 10 % of rainfall at the installed flux monitoring sites within the cover -Contaminant mass flux out of the WRE exhibits stable or decreasing trends when measured at an appropriate and representative location; if no trend can be determined then no persistent adverse environmental impacts when measured over a minimum 2-year monitoring period.
RM13 | Achievement of post-mining land use to stable condition (Native Habitat areas) | a) Ecosystem Function Analysis index scores compared to Native Habitat reference sites are: - Stability Index > 80 % of reference - Infiltration > 60 % of reference - Nutrient Cycling > 60 % of reference - Species Richness > 60 % of reference - Vegetation Dynamics > 40 % of reference - Habitat Complexity > 60 % of reference b) Proportion of Category 3 restricted invasive plant species is not >10% of total vegetation groundcover** c) Weed densities will be similar to surrounding reference sites## d) No unrepaired active gullies (i.e. showing active sediment deposition and sides/floor devoid of cover) > 1 m deep## e) Surface water quality at downstream compliance points to meet contaminant limits defined in the current EA## f) Assessment and validation by suitably qualified person that the groundwater quality is safe, does not cause environmental harm (benchmarked to appropriate reference site(s)) and is able to sustain the nominated PMLU g)Evidence in rehabilitation report that appropriate risk assessment for geotechnical stability at the WRE, Underground Openings and Borrow Area C has been undertaken and control measures are in place## h) Contaminated Land Site Investigation verifies residual contamination presents no unacceptable risk to achieving the PMLU i) Backfill of ventilation shaft complete to pose no unacceptable safety risks to humans or wildlife j)Underground opening certified as safe by a suitably qualified geotechnical engineer (this only applies to RA10) **Defined by Biosecurity Act 2014
RM14 | Achievement of post-mining land use to stable condition (Low Industry Cattle Grazing areas) | a) Assessment of carrying capacity by an appropriatley qualified person demonstrates a sustainable grazing outcome has been achieved b) Ecoystem Function Analysis index scores compared to equivalent reference sites are: - Stability > 80 % of reference - Infiltration > 60 % of reference - Nutrient Cycling > 60 % of reference - Vegetation Dynamics > 40 % of reference c) The basal area of grasses is > 60 % of reference d) Proportion of Category 3 restricted invasive plant species is not >10% of total vegetation groundcover** e) Weed densities will be similar to surrounding reference sites## f) No unrepaired active gullies (i.e. showing active sediment deposition and sides/floor devoid of cover) > 1 m deep## g) Evidence in rehabilitation report that appropriate risk assessment for geotechnical stability at the ROM, Paste Plant and Batch Plant, Infrastructure and Water Dam areas has been undertaken and control measures are in place## h) Surface water quality at downstream compliance points to meet contaminant limits defined in the current EA## i) Assessment and validation by suitably qualified person that the groundwater quality is safe, does not cause environmental harm (benchmarked to appropriate reference site(s)) and is able to sustain the nominated PMLU j) Assessment and validation by suitably qualified person that the long-term risks presented by groundwater contamination do not preclude the PMLU being sustained k) Contaminated Land Site Investigation verifies residual contamination presents no unacceptable risk to achieving the PMLU **Defined by Biosecurity Act 2014
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones