## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Spoil Dumps
Total rehabilitation area size (ha) |  |  |  | 3824.1289
Commencement of first milestone: RM3 |  |  |  | 2024-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2024-12-10 | 2029-12-10 | 2034-12-10 | 2039-12-10 | 2044-12-10 | 2049-12-10 | 2054-12-10 | 2059-12-10 | 2064-12-10 | 2069-12-10 | 2074-12-10 | 2079-12-10 | 2084-12-10 | 2089-12-10 | 2094-12-10 | 2099-12-10 | 2104-12-10 | 2109-12-10 | 2114-12-10 | 2119-12-10
Cumulative area available (ha) | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.1289
Milestone completed by | 2029-12-10 | 2034-12-10 | 2039-12-10 | 2044-12-10 | 2049-12-10 | 2054-12-10 | 2059-12-10 | 2064-12-10 | 2069-12-10 | 2074-12-10 | 2079-12-10 | 2084-12-10 | 2089-12-10 | 2094-12-10 | 2099-12-10 | 2104-12-10 | 2109-12-10 | 2114-12-10 | 2119-12-10 | 2124-12-10
Milestone Reference | 2029-12-10: Cumulative area achieved (ha)
RM3 | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.1289
RM5 | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.1289
RM8 | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.1289
RM11 |  |  | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.0398
RM14 |  |  |  |  | 172 | 364.5 | 557 | 635.6257 | 737.4625 | 855.4893 | 979.1169 | 1085.4513 | 1204.5585 | 1339.7688 | 1518.4674 | 1754.8841 | 1875.3127 | 2095.0398 | 2958.0398 | 3824.1289

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Creek Diversions and Crossings
Total rehabilitation area size (ha) |  |  |  | 260.9262
Commencement of first milestone: RM1 |  |  |  | 2034-12-10
PMLU |  |  |  | Watercourse
Date area is available | 2034-12-10 | 2037-12-10 | 2047-12-10 | 2060-12-10 | 2063-12-10 | 2073-12-10 | 2099-12-10 | 2102-12-10
Cumulative area available (ha) | 2034-12-10: 179.8725; 2060-12-10: 196.6992; 2099-12-10: 249.7158; 2102-12-10: 260.9262
Milestone completed by | 2037-12-10 | 2047-12-10 | 2057-12-10 | 2063-12-10 | 2073-12-10 | 2083-12-10 | 2102-12-10 | 2104-12-10 | 2112-12-10 | 2114-12-10 | 2122-12-10 | 2124-12-10
Milestone Reference | 2037-12-10: Cumulative area achieved (ha)
RM1 | 2037-12-10: 179.8725; 2063-12-10: 196.6992; 2102-12-10: 249.7158; 2104-12-10: 260.9262
RM3 | 2037-12-10: 179.8725; 2063-12-10: 196.6992; 2102-12-10: 249.7158; 2104-12-10: 260.9262
RM6 | 2037-12-10: 179.8725; 2063-12-10: 196.6992; 2102-12-10: 249.7158; 2104-12-10: 260.9262
RM9 | 2037-12-10: 179.8725; 2063-12-10: 196.6992; 2102-12-10: 249.7158; 2104-12-10: 260.9262
RM12 | 2047-12-10: 179.8725; 2073-12-10: 196.6992; 2112-12-10: 249.7158; 2114-12-10: 260.9262
RM15 | 2057-12-10: 179.8725; 2083-12-10: 196.6992; 2122-12-10: 249.7158; 2124-12-10: 260.9262

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Infrastructure Areas - MIA, workshop, dams, roads and general infrastructure
Total rehabilitation area size (ha) |  |  |  | 1069.7478
Commencement of first milestone: RM1 |  |  |  | 2098-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2098-12-10 | 2101-12-10
Cumulative area available (ha) | 717.2691 | 1069.7478
Milestone completed by | 2101-12-10 | 2103-12-10 | 2111-12-10 | 2113-12-10 | 2115-12-10 | 2121-12-10 | 2123-12-10 | 2125-12-10 | 2128-12-10 | 2130-12-10 | 2133-12-10 | 2138-12-10
Milestone Reference | 2101-12-10: Cumulative area achieved (ha)
RM1 | 2101-12-10: 717.2691; 2103-12-10: 1069.7478
RM2 | 2111-12-10: 598.2472; 2113-12-10: 950.7503; 2121-12-10: 1069.7478
RM3 | 2113-12-10: 598.2472; 2115-12-10: 950.7503; 2123-12-10: 1069.7478
RM4 | 2113-12-10: 598.2472; 2115-12-10: 950.7503; 2123-12-10: 1069.7478
RM7 | 2113-12-10: 598.2472; 2115-12-10: 950.7503; 2123-12-10: 1069.7478
RM10 | 2123-12-10: 598.2472; 2125-12-10: 950.7503; 2133-12-10: 1069.7478
RM13 | 2128-12-10: 598.2472; 2130-12-10: 950.7503; 2138-12-10: 1069.7478

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Roads, creek corridor areas, exploration and general infrastructure
Total rehabilitation area size (ha) |  |  |  | 1549.3564
Commencement of first milestone: RM1 |  |  |  | 2034-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2034-12-10 | 2036-12-10 | 2039-12-10 | 2049-12-10 | 2059-12-10 | 2076-12-10 | 2079-12-10 | 2089-12-10 | 2099-12-10
Cumulative area available (ha) | 2034-12-10: 355.5128; 2059-12-10: 542.6664; 2099-12-10: 1549.3564
Milestone completed by | 2036-12-10 | 2039-12-10 | 2049-12-10 | 2059-12-10 | 2076-12-10 | 2079-12-10 | 2089-12-10 | 2099-12-10 | 2100-12-10 | 2103-12-10 | 2113-12-10 | 2123-12-10
Milestone Reference | 2036-12-10: Cumulative area achieved (ha)
RM1 | 2036-12-10: 355.5128; 2076-12-10: 542.6664; 2100-12-10: 1549.3564
RM3 | 2039-12-10: 355.5128; 2079-12-10: 542.6664; 2103-12-10: 1549.3564
RM5 | 2039-12-10: 355.5128; 2079-12-10: 542.6664; 2103-12-10: 1549.3564
RM8 | 2039-12-10: 355.5128; 2079-12-10: 542.6664; 2103-12-10: 1549.3564
RM11 | 2049-12-10: 355.5128; 2089-12-10: 542.6664; 2113-12-10: 1549.3564
RM14 | 2059-12-10: 355.5128; 2099-12-10: 542.6664; 2123-12-10: 1549.3564

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA7
Relevant activities |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  | 361.2438
Commencement of first milestone: RM10 |  |  | 2024-12-10
PMLU |  |  | Cattle Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 361.2438
Milestone completed by | 2034-12-10 | 2039-12-10
Milestone Reference | Cumulative area achieved (ha)
RM10 | 361.2438
RM17 |  | 361.2438

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10
Relevant activities |  |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 62.7437
Commencement of first milestone: RM8 |  |  |  | 2024-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2024-12-10 | 2024-12-10
Cumulative area available (ha) | 45.9251 | 62.7437
Milestone completed by | 2024-12-10 | 2026-12-10 | 2034-12-10 | 2036-12-10 | 2044-12-10 | 2046-12-10
Milestone Reference | Cumulative area achieved (ha)
RM8 | 45.9251 | 62.7437
RM11 |  |  | 45.9251 | 62.7437
RM18 |  |  |  |  | 45.9251 | 62.7437

## RA12
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA12
Relevant activities |  |  |  | Roper Project - Spoil Dumps
Total rehabilitation area size (ha) |  |  |  | 658.1652
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2024-12-10
Cumulative area available (ha) | 658.1652
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2038-12-10 | 2041-12-10 | 2048-12-10 | 2051-12-10 | 2058-12-10 | 2061-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM0.1 | 2026-12-10: 658.1652
RM0.2 | 2032-12-10: 658.1652
RM0.3 | 2033-12-10: 658.1652
RM0.4 | 2034-12-10: 658.1652
RM3 | 2038-12-10: 263.2661; 2041-12-10: 658.1652
RM5 | 2038-12-10: 263.2661; 2041-12-10: 658.1652
RM8 | 2038-12-10: 263.2661; 2041-12-10: 658.1652
RM11 | 2048-12-10: 263.2661; 2051-12-10: 658.1652
RM14 | 2058-12-10: 263.2661; 2061-12-10: 658.1652

## RA13
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA13
Relevant activities |  |  |  | Roper Project - Spoil Dumps
Total rehabilitation area size (ha) |  |  |  | 518.5605
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 518.5605
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2038-12-10 | 2041-12-10 | 2048-12-10 | 2051-12-10 | 2053-12-10 | 2056-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM0.1 | 2026-12-10: 518.5605
RM0.2 | 2032-12-10: 518.5605
RM0.3 | 2033-12-10: 518.5605
RM0.4 | 2034-12-10: 518.5605
RM3 | 2038-12-10: 246; 2041-12-10: 518.5605
RM4 | 2038-12-10: 246; 2041-12-10: 518.5605
RM7 | 2038-12-10: 246; 2041-12-10: 518.5605
RM10 | 2048-12-10: 246; 2051-12-10: 518.5605
RM13 | 2053-12-10: 246; 2056-12-10: 518.5605

## RA14
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA14
Relevant activities |  |  |  | Roper Project - Infrastructure Areas - Murphy's dam, haulroad and general infrastructure
Total rehabilitation area size (ha) |  |  |  | 98.9811
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 98.9811
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2037-12-10 | 2057-12-10 | 2060-12-10 | 2070-12-10 | 2075-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM0.1 | 2026-12-10: 98.9811
RM0.2 | 2032-12-10: 98.9811
RM0.3 | 2033-12-10: 98.9811
RM0.4 | 2034-12-10: 98.9811
RM1 | 2037-12-10: 98.9811
RM2 | 2057-12-10: 98.9811
RM3 | 2060-12-10: 98.9811
RM4 | 2060-12-10: 98.9811
RM7 | 2060-12-10: 98.9811
RM10 | 2070-12-10: 98.9811
RM13 | 2075-12-10: 98.9811

## RA15
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA15
Relevant activities |  |  |  | Roper Project - Roads, creek corridor areas, exploration and general infrastructure
Total rehabilitation area size (ha) |  |  |  | 505.9345
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2024-12-10
Cumulative area available (ha) | 505.9345
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2036-12-10 | 2039-12-10 | 2049-12-10 | 2059-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM0.1 | 2026-12-10: 505.9345
RM0.2 | 2032-12-10: 505.9345
RM0.3 | 2033-12-10: 505.9345
RM0.4 | 2034-12-10: 505.9345
RM1 | 2036-12-10: 505.9345
RM3 | 2039-12-10: 505.9345
RM5 | 2039-12-10: 505.9345
RM8 | 2039-12-10: 505.9345
RM11 | 2049-12-10: 505.9345
RM14 | 2059-12-10: 505.9345

## RA16
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA16
Relevant activities |  |  |  | Roper Project - Tailings Storage Facility and Coal Rejects Dump
Total rehabilitation area size (ha) |  |  |  | 158.0495
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 158.0495
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2037-12-10 | 2057-12-10 | 2062-12-10 | 2072-12-10 | 2077-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM0.1 | 2026-12-10: 158.0495
RM0.2 | 2032-12-10: 158.0495
RM0.3 | 2033-12-10: 158.0495
RM0.4 | 2034-12-10: 158.0495
RM1 | 2037-12-10: 158.0495
RM2 | 2057-12-10: 158.0495
RM3 | 2062-12-10: 158.0495
RM4 | 2062-12-10: 158.0495
RM7 | 2062-12-10: 158.0495
RM10 | 2072-12-10: 158.0495
RM13 | 2077-12-10: 158.0495

## RA17
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA17
Relevant activities |  |  |  | Roper Project - Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 323.8021
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 323.8021
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2044-12-10 | 2049-12-10
Milestone Reference | Cumulative area achieved (ha)
RM0.1 | 323.8021
RM0.2 |  | 323.8021
RM0.3 |  |  | 323.8021
RM0.4 |  |  |  | 323.8021
RM10 |  |  |  |  | 323.8021
RM17 | [5 empty] | 323.8021

## RA18
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA18
Relevant activities |  |  |  | Roper Project - Existing Rehabilitation
Total rehabilitation area size (ha) |  |  |  | 123.8477
Commencement of first milestone: RM0.1 |  |  |  | 2024-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2024-12-10
Cumulative area available (ha) | 123.8477
Milestone completed by | 2026-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2036-12-10 | 2046-12-10 | 2056-12-10
Milestone Reference | Cumulative area achieved (ha)
RM0.1 | 123.8477
RM0.2 |  | 123.8477
RM0.3 |  |  | 123.8477
RM0.4 |  |  |  | 123.8477
RM8 |  |  |  |  | 123.8477
RM11 | [5 empty] | 123.8477
RM18 | [6 empty] | 123.8477

## RA19
Post-mining land uses (PMLU)
Rehabilitation area |  | RA19
Relevant activities |  | Progressively Certified Rehabilitation
Total rehabilitation area size (ha) |  | 294.3727
Commencement of first milestone: |  | Rehabilitation has been progressively certified by DESI
PMLU |  | Cattle Grazing
Date area is available
Cumulative area available (ha)
Milestone completed by
Milestone Reference | Cumulative area achieved (ha)

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Void
Total size (ha) |  |  |  | 1481.36
Commencement of first milestone: MM1 |  |  |  | 2094-12-10
NUMA |  |  |  | NUMA
Date area is available | 2094-12-10 | 2096-12-10 | 2098-12-10 | 2100-12-10
Cumulative area available (ha) | 265.1085 | 538.2754 | 654.7033 | 1481.36
Milestone completed by | 2096-12-10 | 2098-12-10 | 2100-12-10 | 2102-12-10 | 2138-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 265.1085 | 538.2754 | 654.7033 | 1481.36
MM2 | 265.1085 | 538.2754 | 654.7033 | 1481.36
MM3 |  |  |  |  | 1481.36

## IA2
Non-use management area (NUMA)
Improvement area |  |  | IA2
Relevant activities |  |  | Void
Total size (ha) |  |  | 454.2622
Commencement of first milestone: MM1 |  |  | 2098-12-10
NUMA |  |  | NUMA
Date area is available | 2098-12-10
Cumulative area available (ha) | 454.2622
Milestone completed by | 2100-12-10 | 2138-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 454.2622
MM2 | 454.2622
MM3 |  | 454.2622

## Rehabilitation Area Milesto
Milestone reference | Rehabilitation milestone | Milestone criteria
RM0.1 | Project ground works | 0.1 Ground works: a) Investigation and development of plan for large scale leucaena management b) Establish safe access to landforms for data collection and progressive rehabilitation activities.
RM0.2 | Project data collection | 0.2 Progressive ground works and sufficient data collection for modelling: a) Ongoing leucaena management and earthworks b) Drilling and installation of additional groundwater bores and water monitoring c) Drilling and installation of geochemical boreholes and monitoring d) Additional tailings and rejects material testing e) Additional waste characterisation f) Additional tailings geotechnical characterisation g) On-going land contamination investigation.
RM0.3 | Project modelling | 0.3 Updated modelling and landform: a) Flood modelling b) Hydrogeological modelling c) Water balance modelling d) Hydrogeochemical modelling e) Landform design iterations.
RM0.4 | Project designs and plans | 0.4 Final landform, designs and updated plans: a) Final landform design b) Cover design c) Water management plan d) Void closure plan e) Risk assessment.
RM1 | Infrastructure decommissioning and removal | 1.1 All infrastructure to be retained onsite must be safe, stable and not cause environmental harm. 1.2 All infrastructure and services to be retained onsite must have a signed landholder statement, declaring that they will accept responsibility for the infrastructure (except for those items in 1.4). 1.3 If the underlying landholder is also the EA holder (or a parent corporation or a subsidiary corporation), consent to retain the infrastructure is required from the administering authority (except for those items in 1.4). In seeking consent the holder must justify how the infrastructure will provide a benefit or improvement to the use of the land and/or community once mining has ceased. 1.4 Below-ground infrastructure, services and waste (as per the Environmental Authority (EPML00865013) waste schedule) deeper than 0.5m in relation to the final landform surface can be retained provided it can meet the following: a) All pipelines have been drained; and b) All below-ground infrastructure (installed after the approval date of this transitional PRCP) to be retained must be mapped; and c) The intended PMLU is not compromised; and d) There is no ongoing risk of environmental harm. 1.5 With the exception of 1.2, 1.3 and 1.4 above, the following are complete: a) All services disconnected, terminated and removed b) All buildings and associated infrastructure dismantled and removed c) All hardstand, concrete areas and roads (bitumen, blue metal, aggregate) removed d) All pipelines drained and removed e) All waste, not authorised under the Environmental Authority (EPML00865013) waste schedule, removed f) All surface water drainage infrastructure removed g) All drillholes, bores, sediment ponds and sumps decommissioned h) All machinery and equipment removed from site i) Mine water dams are decommissioned j) Watercourse crossings and culverts removed. 1.6 Assessment of mine water dams is completed by an AQP1 and identified sediment and water management actions are completed. 1Appropriately qualified person (AQP) means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods or literature
RM2 | Remediation and/or management of contaminated land | 2.1 Contaminated Land Investigation Document completed in accordance with the Environmental Protection Act 1994, including a site investigation report, and, where required, a Validation Report and/or a draft Site Management Plan. 2.2 The Contaminated Land Investigation Document confirms the area within the mining leases (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410) does not present an unacceptable risk to the post-mining land use. 2.3 Despite 2.1 and 2.2, where contaminated land investigations are undertaken for individual areas of progressive rehabilitation that do not cover an entire Lot on Plan, the investigations will be undertaken by a Suitably Qualified Person to a standard, that at the time of investigation, would be suitable to form part of a future Environmental Protection Act 1994 compliant Contaminated Land Investigation Document for that property, and does not need to achieve all requirements for a contaminated land submission to the administering authority.
RM3 | Landform development and reshaping | 3.1 Erosion and sediment control systems are installed as per the construction design and verified by an AQP1. Spoil Dumps (RA1, RA12) 3.3 Landforms are constructed such that there will be no runoff from landform tops onto batter slopes. 3.4 Landforms reshaped with maximum 30% slopes. 3.5 Tertiary spoil to be covered with minimum 1m Permian spoil for slopes >5% and for slopes >15% at least 0.5m of the upper 1m Permian cover is to be competent rock. 3.6 Permian spoil to be covered with minimum 0.5m competent rock on >15% slopes. 3.7 AQP1 certifies that as constructed landform achieves design criteria for geotechnical stability with a Factor of Safety (FoS) ≥ 1.5 Tailings Storage Facilities and rejects (RA16) 3.7 Tailings and rejects to be capped with at least 2m of competent benign spoil. 3.8 Landforms to be non-ponding. 3.9 Landforms are reshaped with slopes not exceeding 12%. 3.10 AQP1 certifies that as constructed landform achieves design criteria for geotechnical stability with a Factor of Safety (FoS) ≥ 1.5. Watercourses (RA2) 3.11 Disturbed natural watercourse bed and banks returned to a profile similar to the pre-disturbance condition. Other areas 3.12 Landforms are reshaped with slopes not exceeding 12% (RA3, RA13, RA14). 3.13 Landforms are reshaped with slopes not exceeding 15% (RA4, RA15).
RM4 | Surface preparation (cattle grazing) | 4.1 Topsoil placed at minimum depth of 150mm in areas where topsoil has previously been removed. 4.2 Assessment of growth media characteristics and the development of an amelioration and physical treatment plan is completed by an AQP1 and reviewed and endorsed by a third party AQP1, to ensure growth media is suitable for target vegetation establishment, the PMLU and stability of the landform. 4.3 Ameliorant and physical treatments such as fertiliser, gypsum and/or organic matter are applied as identified in criteria 4.2. 4.4 Deep rip at least 300mm into soil/subsoil profile along contour of slopes.
RM5 | Surface preparation (woodland habitat) | 5.1 Topsoil placed at minimum depth of 100mm or alternative growth media at minimum depth of 300mm, in areas where topsoil has previously been removed. 5.2 Assessment of growth media characteristics and the development of an amelioration and physical treatment plan is completed by an AQP1 and reviewed and endorsed by a third party AQP1, to ensure growth media is suitable for target vegetation establishment, the PMLU and stability of the landform. 5.3 Ameliorant and physical treatments such as fertiliser, gypsum and/or organic matter are applied as identified in criteria 5.2. 5.4 Deep rip at least 300mm into soil/subsoil profile along contour of slopes.
RM6 | Surface preparation (watercourse) | 6.1 Topsoil placed at minimum depth of 150mm in areas where topsoil has previously been removed. 6.2 Assessment of growth media characteristics and the development of an amelioration and physical treatment plan is completed by an AQP1 and reviewed and endorsed by a third party AQP1, to ensure growth media is suitable for target vegetation establishment, the PMLU and stability of the landform. 6.3 Ameliorant and physical treatments such as fertiliser, gypsum and/or organic matter are applied as identified in criteria 6.2. 6.4 Deep rip at least 300mm into soil/subsoil profile along contour of slopes.
RM7 | Revegetation (cattle grazing) | 7.1 Completed seeding in accordance with recommended pasture mixes and seeding rates as shown in Table 40: Recommended species list and seeding rates for cattle grazing PMLU. 7.2 At least four species of 3P pasture species and two legumes, including at least two native pasture species, from Table 40: Recommended species list and seeding rates for cattle grazing PMLU are to be applied per application area. 7.3 Minimum seeding rates of 16kg/ha of coated pasture seed and 4kg/ha of uncoated legume seed will be used, unless adjusted by an AQP1 based on results of rehabilitation monitoring.
RM8 | Revegetation (woodland habitat) | 8.1 Completed seeding in accordance with recommended woodland habitat species mix and seeding rates in Table 42: Recommended species list* and seeding rates for woodland habitat PMLU (RA1, RA12), or as recommended by an AQP1 if vegetation is targeting a regional ecosystem (RA4, RA15)2. 8.2 Minimum seeding rates of 6kg/ha of tree species, 4kg/ha of woody understory species and 10kg/ha of grasses will be used, unless adjusted by an AQP1 based on results of rehabilitation monitoring (RA1, RA12). 8.3 Non-native seed must not be used for the revegetation of woodland habitat PLMU (except when sterile cover crops or Cynodon dactylon are used). 2Seed application may not be required in all RA4 areas. *If recommended species are not available, substitute with species from RE 11.4.2, RE 11.4.13, RE 11.5.2, RE 11.5.3 and RE 11.10.7.
RM9 | Revegetation (watercourse) | 9.1 Completed seeding in accordance with recommended watercourse species mix and seeding rates in Table 43: Recommended species list and seeding rates for watercourse revegetation PMLU – upper and mid banks and Table 44: Recommended species list and seeding rates for watercourse revegetation PMLU – lower banks. 9.2 Species chosen should reflect regional ecosystem 11.3.25. 9.3 Minimum seeding rates of: a) For the upper and mid banks – 6kg/ha uncoated trees species, 4kg/ha uncoated woody understorey species and 10kg/ha uncoated grasses and other groundcover species b) For the lower banks – 5kg/ha of uncoated tree species, 10kg/ha uncoated ground species. 9.4 Non-native seed must not be used for the revegetation of watercourse PLMU (except when sterile cover crops or Cynodon dactylon are used).
RM10 | Achievement of surface requirements (cattle grazing) | 10.1 Vegetation meets the following: a) >50% established and self-sustaining vegetation groundcover, of which at least 50% of dry matter yield is 3P pasture species as listed in Table 40: Recommended Species list and seeding rates for cattle grazing b) Minimum composition of three species of 3P grasses (RA3, RA13, RA14, RA16) and two species of 3P grasses (RA7, RA17) present per hectare (averaged). 10.2 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with site-specific surface water quality limits (RA3, RA13, RA14, RA16). 10.3 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications and There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 10.4 Despite criteria 10.3, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not expose environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gullies; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 2 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 3Stabilised erosion: one or both of the following conditions apply: no evidence of sediment movement; sides and/or floors of erosion form are revegetated.
RM11 | Achievement of surface requirements (woodland habitat) | 11.1 Groundcover: a) >15% slopes must achieve ≥80% groundcover, consisting of at least 50% vegetation groundcover4 b) ≤15% slopes must achieve ≥50% groundcover, consisting of at least 50% vegetation groundcover4. 11.2 Woodland habitat vegetation meets the following: a) BioCondition score of ≥18/60 based on the averaged benchmarks for the representative regional ecosystems as listed in Table 68: BioCondition benchmarks and scoring of site-based attributes for representative regional ecosystems and as assessed by an AQP1 using the modified ‘BioCondition Assessment Manual’ (version 2.2) methodology (RA1, RA4, RA12, RA15), or b) Species richness of ≥2 native trees, ≥3 native shrubs and ≥4 grasses (exotic and native species) (RA10, RA18). 11.3 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with site-specific surface water quality limits (RA1, RA4, RA12, RA15). 11.4 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 11.5 Despite criteria 11.4, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not expose environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gullies; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 2 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 4Vegetation groundcover: Means plants, plant litter, tree leaf litter, twigs and woody debris that protect the soil surface from erosion.
RM12 | Achievement of surface requirements (watercourse) | 12.1 Groundcover: a) >15% slopes must achieve ≥80% groundcover, consisting of at least 50% vegetation groundcover4 b) ≤15% slopes must achieve ≥50% groundcover, consisting of at least 50% vegetation groundcover4. 12.2 Watercourse vegetation meets the following: a) Species richness: • ≥2 native trees and ≥2 native shrubs representative of RE 11.3.25 • ≥2 grass species (exotic and native species) b) Tree canopy cover ≥13%. 12.3 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with site-specific surface water quality limits. 12.4 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 12.5 Despite criteria 12.4, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not expose environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gullies; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 2 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features.
RM13 | Achievement of post-mining land use to a stable condition (cattle grazing – RA3, RA13, RA14, RA16) | 13.1 Hazard assessment completed by an AQP1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. 13.2 Vegetation meets the following criteria: a) >50% established and self-sustaining vegetation groundcover b) At least 60% of pasture dry matter yield consists of 3P grasses with a minimum composition of three 3P grasses present per hectare (averaged) c) Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP1 as appropriately managed. 13.3 Land suitability class assessed by an AQP1 and certified that the land has achieved a post-mining land suitability class of 3 or better for cattle grazing, or not different from pre-mining class if it is class 4; where assessment of rehabilitation is in accordance with Short (2023). Class 4 is only accepted if the limitations are water availability, soil nutrient5 or sub-soil erosion. 13.4 For any Class 4 land suitability areas, land condition is assessed as Good (A) condition for non-grazed areas, or Good (A) or Fair (B) condition for grazed areas using the Grazing Land Management ABCD land condition framework. 13.5 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 13.6 Despite criteria 13.5, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not expose environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gully; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 5 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 13.7 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with Appendix 2 – Surface water quality limits. 13.8 Verification by a suitably qualified person through a site inspection, records review and aerial imagery to confirm: a) Requirements of any Site Management Plan have been met; b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the intended PMLU; and c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2. 5Only applies when soil nutrient status cannot reasonably be ameliorated, as determined by an AQP.
RM14 | Achievement of post-mining land use to a stable condition (woodland habitat – RA1, RA4, RA12, RA15) | 14.1 Hazard assessment completed by an AQP1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. 14.2 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 14.3 Despite criteria 14.2, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not exposed environmentally problematic materials; and c) The cause of the gully is known and has been resolved; d) Have established and persistent vegetation cover at the head of the gully; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 5 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 14.4 Rehabilitation is assessed as geotechnically stable by an AQP1 with FoS≥1.5 (RA1, RA12). 14.5 Groundcover: a) >15% slopes must achieve ≥80% groundcover, consisting of at least 50% vegetation groundcover4 b) ≤15% slopes must achieve ≥50% groundcover, consisting of at least 50% vegetation groundcover4. 14.6 Woodland habitat vegetation meets the following: a) BioCondition score of ≥35/60 based on the averaged benchmarks for the representative regional ecosystems as listed in Table 68: BioCondition benchmarks and scoring of site-based attributes for representative regional ecosystems and as assessed by an AQP1 using the modified ‘BioCondition Assessment Manual’ (version 2.2) methodology b) Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP1 as appropriately managed. 14.7 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with site-specific surface water quality limits. 14.8 Verification by a suitably qualified person through a site inspection, records review and aerial imagery to confirm: a) Requirements of any Site Management Plan have been met; b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the intended PMLU; and c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2.
RM15 | Achievement of post-mining land use to a stable condition (watercourse – RA2) | 15.1 Hazard assessment completed by an AQP1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. 15.2 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 15.3 Despite criteria 15.2, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not exposed environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gully; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 5 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 15.4 Geomorphic index score: greater than or equal to upstream or downstream values (Index of Diversion Condition method6). 15.5 Watercourse vegetation meets the following: a) Riparian vegetation index score: greater than or equal to upstream or downstream values (Index of Diversion Condition method6) b) Species richness: • ≥2 native trees and • ≥2 native shrubs c) Tree canopy cover ≥20% d) Median tree canopy height ≥10m e) Recruitment of at least two woody perennial species in ecological dominant layer d) Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP1 as appropriately managed. 15.6 Assessment by an AQP1 that the watercourse diversion has an Index of Diversion Condition (IDC) score >10. 15.7 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur and it is safe to do so. The representative samples comply with site-specific surface water quality limits. 15.8 Verification by a suitably qualified person through a site inspection, records review and aerial imagery to confirm: a) Requirements of any Site Management Plan have been met; b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the intended PMLU; and c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2. 6For watercourse rehabilitation not within a diversion (i.e. crossings/culverts), a modified IDC method with a reduced number of monitoring points within each reach will be used.
RM17 | Achievement of post-mining land use to a stable condition (cattle grazing existing rehabilitation – RA7, RA17) | 17.1 Hazard assessment completed by an AQP1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. 17.2 Vegetation meets the following: a) >50% established and self-sustaining vegetation groundcover on slopes ≤15%, comprising at least 50% dry matter yield 3P pasture species b) >70% established and self-sustaining vegetation groundcover on slopes >15%, comprising at least 50% dry matter yield 3P pasture species c) Consists of at least two species of 3P grasses per hectare (averaged) d) Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP1 as appropriately managed e) Leucaena leucocephala must be actively managed to ensure plants >2m high do not exceed stem density of 250 stems per hectare (1 per 40m2) mean of total area. 17.3 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 17.4 Despite criteria 17.3, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not exposed environmentally problematic materials; and c) The cause of the gully is known and has been resolved; and d) Have established and persistent vegetation cover at the head of the gully; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 5 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 17.5 Land condition: assessed as Good (A) condition for non-grazed areas, or Good (A) or Fair (B) condition for grazed areas, for 5 consecutive years using the Grazing Land Management ABCD land condition framework. 17.6 Verification by a suitably qualified person through a site inspection, records review and aerial imagery to confirm: a) Requirements of any Site Management Plan have been met; b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the intended PMLU; and c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2.
RM18 | Achievement of post-mining land use to a stable condition (woodland habitat existing rehabilitation – RA10, RA18) | 18.1 Hazard assessment completed by an AQP1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. 18.2 Woodland habitat vegetation meets the following: a) Species richness: • ≥2 native trees, • ≥3 native shrubs, and • ≥4 grasses (exotic and native species) b) Tree canopy cover ≥16% c) Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤5% of vegetation groundcover, with the exception of Parthenium hysterophorus which must not exceed 10% vegetation groundcover and assessed by an AQP1 as appropriately managed. 18.3 Groundcover: a) >15% slopes must achieve ≥80% groundcover, consisting of at least 50% vegetation groundcover4 b) ≤15% slopes must achieve ≥50% groundcover, consisting of at least 50% vegetation groundcover4. 18.4 AQP1 certifies that: a) There is no severe sheet, rill or gully erosion present (as defined in Table 64: Erosion classifications); and b) Mass movement is absent; and c) All other erosion, including tunnel erosion, requiring intervention has been remediated and does not impact achieving the PMLU. 18.5 Despite criteria 18.4, gullies are acceptable on the final landform provided they meet the following criteria, as certified by an AQP1: a) Do not exceed 1m in depth at any point; and b) Do not exposed geochemically and highly saline problematic materials; and c) The cause of the gully is known and has been resolved; d) Have established and persistent vegetation cover at the head of the gully; and e) Are in a stabilised3 state, demonstrated by monitoring data over a 5 year period; and f) Do not provide a safety hazard within the context of the PMLU; and g) Do not impact the stability or performance of engineered drainage features. 18.6 Verification by a suitably qualified person through a site inspection, records review and aerial imagery to confirm: a) Requirements of any Site Management Plan have been met; b) Notifiable activities have not been undertaken post completion of RM2 that would impact the use of the land for the intended PMLU; and c) There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of structural stability | IA1.1 Void backfill will be completed at the end of mining for flood mitigation at: a) The northern and southern end-walls of Lotus/Campbell void b) The northern and southern end-walls of Gilbert void c) The northern end-wall of Price/ Leichhardt void d) The end-walls adjacent to Rolf Creek of East Pit voids. IA1.2 Highwall landforms must: a) Prevent surface flow of floodwater into the void b) Be geotechnically stable when floodwater is against the creek-side batter c) Prevent seepage flow of floodwater into the void d) Not be constructed with dispersive material e) Have maximum 30% slopes with rock for scour protection. IA1.3 The final design for highwall landform must be completed by an AQP1 based on the latest flood modelling and materials data prior to construction. IA1.4 Final residual voids are not subject to inundation from floodwaters up to and including the 0.1% AEP. IA1.5 The high-wall, end-wall and low-wall achieve a FoS ≥1.5 within the NUMA extents as determined by an AQP1. IA1.6 A minimum distance of 50m is to be designed between the residual void crest and the toe of the safety bund, where against an external perimeter mining lease (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410), boundary. IA1.7 The location of the voids and associated safety bunds does not cause instability or degradation to the land outside of the mining lease (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410), boundary. IA1.8 Low-walls are free-draining into the void lake with a maximum 37 degree slopes. IA1.9 Residual voids must not overtop. IA1.10 Residual voids collectively act as groundwater sinks within the relevant mining lease (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410) boundary post closure as demonstrated by groundwater modelling defined in condition PRCP12.
MM2 | Achievement of surface requirements | IA2.1 Competent safety bund or equivalent landform in place to prevent access to the residual void, at the geotechnical set-back distance. IA2.2 Fencing erected, where required to prevent access to the residual void, around the perimeter of the safety bund. IA2.3 Warning signage placed along the fence line (nominally one sign every 100m). IA2.4 A minimum distance of 25m is to be designed between the residual void low-wall crest within the NUMA and the safety bund or equivalent landform in IA2.1.
MM3 | Achievement of sufficient improvement | IA3.1 Certification from an AQP1 that: a) The residual void is safe to humans and livestock b) The water level and quality in the void will not cause environmental harm to the surrounding environment, as demonstrated by groundwater level, quality monitoring and modelling c) Voids retain flood immunity, supported by flood modelling re-run at end of life and calibrated against the final landform d) The highwall landform has been constructed in accordance with the final design e) Appropriate safety infrastructure at the geotechnical set-back distance has been installed to prevent access to the NUMA f) The residual void will not present an unacceptable risk of environmental harm outside of the relevant external perimeter mining lease (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410), boundary g) Erosion of the landform within the NUMA area will not negatively impact on the stability of any adjacent rehabilitation areas, or their ability to sustain their PMLU. IA3.2 Monitoring and maintenance of exclusion fences and bunds to be carried out to ensure they remain effective.
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## Conditions
Condition # | PRCP Condition
PRCP11 | With respect to groundwater: a) The monitoring bores listed in Table 74: Groundwater monitoring locations must be installed by 2050; and b) Following monitoring bore installation, groundwater quality must be monitored six monthly at, but not limited to, bores specified in Table 74: Groundwater monitoring locations; and c) The holder must develop site-specific groundwater quality limits for the bores listed in Table 74: Groundwater monitoring locations; and d) The groundwater model and water balance model must be recalibrated and predictions rerun at least every five years commencing from 2050.
PRCP12 | With respect to groundwater the following must be demonstrated prior to surrender: a) Groundwater quality results for compliance bores have not exceeded the site-specific groundwater quality limits, for 3 consecutive results within the five-year period immediately prior to surrender; and b) There is no environmental harm beyond the boundaries of the mining leases (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410), and c) Predictive groundwater modelling as per the Australian Groundwater Modelling Guidelines (current version), undertaken at the completion of all mining, confirms the network of residual voids will collectively develop into groundwater sinks and prevent environmental harm through the release of contaminants from the void lakes beyond the tenure boundaries post-closure.
PRCP13 | With respect to surface water: a) The holder must install monitoring equipment at the relevant surface water monitoring locations specified in Table 73: Surface water monitoring locations and undertake at least one year of surface water quality monitoring prior to the completion of surface preparations for the entire site; and b) Surface water quality must be monitored at the locations specified in Table 73: Surface water monitoring locations at least once per month when flows at the downstream gauging station record 1m3/second, when safe to collect samples; and c) The holder must develop site-specific surface water quality limits for the watercourses listed in Table 73: Surface water monitoring locations.
PRCP14 | With respect to surface water the following must be demonstrated prior to surrender: a) Surface water quality must not exceed the site-specific surface water quality limits within the 5-year period immediately prior to surrender; b) If the surface water quality exceeds criteria a), the applicable upstream/reference site must be compared to the downstream site result; and quality result measured at a downstream site must be equal to or less than the quality result measured at the applicable upstream/reference site.
PRCP15 | Where the surface water quality at the downstream site exceeds the upstream site result as per PRCP14b), an AQP1 must complete an assessment of the cause of the exceedance and risk of rehabilitation not achieving a stable condition (PRCP 14) within the schedule timeframe and: a) Where there is a low risk to achieving a stable condition from the mining tenure (ML1782, ML70126, ML70127, ML70325, ML70328, ML70350, ML70369, ML70370, ML70410), then no further action is to be taken; or c) Where there is a risk greater than low to achieve a stable condition, then an assessment of potential environment harm and any changes or rectification actions to rehabilitation activities must be determined and implemented.
PRCP16 | The assessment/s under PRCP15 must be completed and provided to the administering authority within 3 months of receiving the relevant sampling results.
PRCP17 | Despite PRCP14, PRCP15a) can be triggered 3 times over 5 consecutive years prior to surrender.
PRCP18 | If PRCP15b) is triggered the 5-year timeframe under PRCP14a) is reset.