## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA1
Relevant activities |  |  | Infrastructure
Total rehabilitation area size (ha) |  |  | 2.39
Commencement of first milestone: RM1 |  |  | 2037
PMLU |  |  | Grazing
Date area is available | 2037-12-10 | 2041-12-10
Cumulative area available (ha) | 2.39 | 2.39
Milestone completed by | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 2.39
RM2 | 2.39
RM3 | 2.39
RM4 | 2.39
RM6 | 2.39
RM9 |  | 2.39
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Topsoil Stockpiles
Total rehabilitation area size (ha) |  |  |  | 6
Commencement of first milestone: RM2 |  |  |  | 2022
PMLU |  |  |  | Grazing
Date area is available | 2022-12-10 | 2030-12-10 | 2036-12-10 | 2041-12-10
Cumulative area available (ha) | 0.33 | 0.33 | 6 | 6
Milestone completed by | 2030-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 0.33 |  | 6
RM3 | 0.33 |  | 6
RM4 | 0.33 |  | 6
RM6 | 0.33 |  | 6
RM8 |  | 0.33 |  | 6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | ROM and Product Stockpiles
Total rehabilitation area size (ha) |  |  |  | 8.39
Commencement of first milestone: RM2 |  |  |  | 2022
PMLU |  |  |  | Grazing
Date area is available | 2022-12-10 | 2030-12-10 | 2037-12-10 | 2041-12-10
Cumulative area available (ha) | 0.92 | 0.92 | 8.39 | 8.39
Milestone completed by | 2030-12-10 | 2037-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 |  |  | 8.39
RM2 | 0.92 |  | 8.39
RM3 | 0.92 |  | 8.39
RM4 | 0.92 |  | 8.39
RM6 | 0.92 |  | 8.39
RM8 |  | 0.92 |  | 8.39
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Waste and Overbuden Dumps
Total rehabilitation area size (ha) |  |  |  | 12.92
Commencement of first milestone: RM2 |  |  |  | 2024
PMLU |  |  |  | Grazing
Date area is available | 2024-12-10 | 2026-12-10 | 2028-12-10 | 2030-12-10 | 2036-12-10 | 2041-12-10
Cumulative area available (ha) | 1.43 | 2.89 | 4.19 | 8.89 | 12.92 | 12.92
Milestone completed by | 2026-12-10 | 2028-12-10 | 2030-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 1.43 | 2.89 | 4.19 | 8.89 | 12.92
RM3 |  |  | 1.43 | 8.89 | 12.92
RM4 |  |  | 1.43 | 8.89 | 12.92
RM6 |  |  | 1.43 | 1.43 | 12.92
RM8 |  |  |  | 1.43 | 8.89 | 12.92
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA5
Relevant activities |  |  | Roads and Tracks
Total rehabilitation area size (ha) |  |  | 5.63
Commencement of first milestone: RM2 |  |  | 2040
PMLU |  |  | Road
Date area is available | 2040-12-10 | 2041-12-10
Cumulative area available (ha) | 5.63 | 5.63
Milestone completed by | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 5.63
RA8 |  | 5.63
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Sediment Dams and Stormwater Controls
Total rehabilitation area size (ha) |  |  |  | 5.59
Commencement of first milestone: RM2 |  |  |  | 2022
PMLU |  |  |  | Water Storage
Date area is available | 2022-12-10 | 2030-12-10 | 2036-12-10 | 2041-12-10
Cumulative area available (ha) | 0.01 | 0.01 | 5.59 | 5.59
Milestone completed by | 2030-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 0.01 |  | 5.59
RM9 |  | 0.1 |  | 5.59
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA7
Relevant activities |  |  | Eastern Open Pit (Backfill to RL 524)
Total rehabilitation area size (ha) |  |  | 0.77
Commencement of first milestone: RM5 |  |  | 2022
PMLU |  |  | Water Storage
Date area is available | 2022-12-10 | 2030-12-10
Cumulative area available (ha) | 0.77 | 0.77
Milestone completed by | 2030-12-10 | 2031-12-10
Milestone Reference | Cumulative area achieved (ha)
RM5 | 0.77
RM2 | 0.77
RM7 |  | 0.77
RM10 |  | 0.77
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Main Pit Voids (East-West Pit; Phoenix Pit)
Total rehabilitation area size (ha) |  |  |  | 18.73
Commencement of first milestone: RM1 |  |  |  | 2027
PMLU |  |  |  | Water Storage
Date area is available | 2027-12-10 | 2030-12-10 | 2036-12-10 | 2041-12-10
Cumulative area available (ha) | 16.74 | 16.74 | 18.73 | 18.73
Milestone completed by | 2030-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 16.74 |  | 18.73
RM5 | 16.74 |  | 18.73
RM7 | 16.74 |  | 18.73
RM9 |  | 16.74 |  | 18.73
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Main Pit Voids (Aspinal Pit)
Total rehabilitation area size (ha) |  |  |  | 1.26
Commencement of first milestone: RM5 |  |  |  | 2022
PMLU |  |  |  | Grazing
Date area is available | 2022-12-10 | 2037-12-10 | 2041-12-10
Cumulative area available (ha) | 1.26 | 1.26 | 1.26
Milestone completed by | 2037-12-10 | 2041-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RM5 | 1.26
RM2 |  | 1.26
RM7 |  | 1.26
RM3 |  | 1.26
RM4 |  | 1.26
RM6 |  | 1.26
RM8 |  |  | 1.26
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA10
Relevant activities |  |  | Existing Rehabilitation
Total rehabilitation area size (ha) |  |  | 9.31
Commencement of first milestone: RM2 |  |  | 2022
PMLU |  |  | Grazing
Date area is available | 2022-12-10 | 2030-12-10
Cumulative area available (ha) | 9.31 | 9.31
Milestone completed by | 2030-12-10 | 2031-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 9.31
RM3 | 9.31
RM4 | 9.31
RM6 | 9.31
RM8 |  | 9.31
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Milestone Areas
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) | All services disconnected;
|  | b) | All built and service infrastructure demolished and removed (except where agreed in writing by the post-mining land owner);
|  | c) | All concrete, bitumen, aggregate and fencing removed (where not owned by or required post-mining by the landholder);
|  | d) | All waste and rubbish removed;
|  | e) | All water within mine storages and sediment basins removed (except where agreed in writing by the post-mining land owner); and
|  | f) | Conduct contaminated land assessment where required and if a contamination is suspected.
RM2 | Landform development and reshaping | a) | Major earthworks completed;
|  | b) | Pit voids backfill completed to final landform designs with fully co-mingled and mixed material (ore, waste rock, overburden);
|  |  | i) | Pit ≤35⁰ batters; and
|  |  | ii) | Waste dumps 3⁰ to 5⁰ crowns and ≤25⁰ batters.
|  | c) | Landform is reshaped to be free-draining and blend in with surrounding topography slopes ≤5%;
|  | d) | Erosion and sediment controls installed to AQP design specifications (if applicable); and
|  | e) | All waste, rubbish and mobile equipment and machinery removed.
RM3 | Surface preparation | a) | Topsoil is placed an average thickness of not less than 150mm;
|  | b) | An assessment of soil growth media characteristics is completed by an AQP and amelioration and other treatments required identified;
|  | c) | Ameliorant and physical treatments are applied as identified; and
|  | d) | Rip across contour ≥300mm.
RM4 | Revegetation / Seeding (Grazing) | a) | Completed seeding in accordance with recommended pature mix (grasses, cover crops and legumes) and seeding rates (up to ≥5kg/ha); and
|  |  |  | Common name | Scientific name | Sowing rate (kg/ha)
|  |  |  | Kangaroo Grass | Themeda triandra | 5
|  |  |  | Katambora Rhodes Grass | Chloris gayana | 1
|  |  |  | Slender Bamboo Grass | Austrostipa verticillata | 5
|  |  |  | Barbed-Wire Grass | Cymbopogon refractus | 5
|  |  |  | Creeping Bluegrass | Bothriochloa insculpta | 1
|  |  |  | Twitch Grass | Elymus repens | 1
|  |  |  | Shrubby Stylos | Stylosanthes scabra | 5
|  |  |  | Fine-Stem Stylo | Stylosanthes guianensis vari. intermedia | 2
[5 empty] | TOTAL | 25
|  | b) | Seed spread and raked (≤1cm depth).
RM5 | Establishment of Grazing PMLU surface conditions | a) | Vegetation groundcover ≥75% and/or is comparative to analogue site;
|  | b) | Cover crops and pasture species are established (RM5);
|  | c) | Areas of bare ground (exposed topsoil) is limited (≤25m2);
|  | d) | No severe rill, gully or sheet erosion visible within rehabilitation areas 2-years after commencing rehabilitation;
|  | e) | Persistent weed cover ≤10% above weed cover in analogue site; and
|  | f) | Carrying capacity is ≥75% of carrying capacity in an analogue site.
RM6 | Establishment of Water Storage PMLU surface conditions | a) | Void crests and walls are monitored by an AQP to ensure long-term stabilities are achieved;
|  | b) | Vegetation cover surrounding water storage areas are increasing (marginal grazing PMLU surrounding water storage PMLU); and
|  | c) | Water quality physico chemical indicators do not exceed trigger values for livestock (beef cattle) drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water - Volume 3 Primary Industries (ANZECC and ARMCANZ, 2000).
RM7 | Establishment of geotechnically stable surface conditions (i.e. water storage, residual voids, backfilled pits) | a) | Assessment of backfilled areas (pits, waste dumps) as geotechnically stable by a suitably qualified person(s); and
|  |  | i) | No evidence of slumping;
|  |  | ii) | Final slope status and geometry suitable (pit face slopes <70⁰);
|  |  | iii) | Backfill condition and engineering characteristics suitable; and
|  |  | iv) | Failure mechanicsms.
|  | b) | Assessment of backfilled areas (pits, waste dumps) are in accordance with final landform designs by a suitably qualified person(s).
RM8 | Achievement of Grazing PMLU to a stable condition | a) | AQP assessment confirms safety hazards in rehabilitation area are not significantly different to surrounding unmined landscapes subject to the same land use;
|  | b) | Rehabilitation is assessed as geotechnically stable, by an AQP, with FoS ≥1.5 (ANCOLD, 2017);
|  | c) | AQP assessment confirms rehabiliated land is erosionally stable with groundcover ≥50%, and 70% of slopes ≤ 20% gradient;
|  | d) | Rainfall runoff from the area is not significantly different to upstream values for pH, EC and turbidity to meet 95% aquatic ecosystem protection level defined in Australian and New Zealand Guidelines for Fresh and Marine Water - Volume 2 Aquatic Ecosystems (ANZECC and ARMCANZ, 2000).
|  | e) | Land suitability for grazing pasture is assessed ≥3 or not different from pre-mining class if≥ 4; and
|  | f) | Species density is ≥4 species per hectare.
RM9 | Achievement of Water Storage PMLU to a stable condition | a) | AQP assessment confirms geotechnical stability, with FoS ≥1.5 (ANCOLD, 2017), has been achieved to facilitate safe access by humans and livestock;
|  | b) | AQP assessment confirms rehabilitated land is erosionally stable with groundcover ≥50%, and 70% of slopes ≤ 20% gradient;
|  | c) | Water quality physico chemical indicators do not exceed trigger values for livestock (beef cattle) drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water - Volume 3 Primary Industries (ANZECC and ARMCANZ, 2000); and
|  | d) | Ground cover ≥50% achieved in areas of the water storage catchment.
RM10 | Achievement of Eastern Open Pit Backfill to RL 524 PMLU to a stable condition | a) | AQP assessment of backfilled areas (pits, waste dumps) as geotechnically stable; and
|  |  | i) | No evidence of slumping;
|  |  | ii) | Final slope status and geometry suitable (pit face slopes <70⁰);
|  |  | iii) | Backfill condition and engineering characteristics suitable; and
|  |  | iv) | Failure mechanicsms.
|  | b) | AQP assessment of portion of backfilled area in Eastern Open Pi is in accordance with final landform designs.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones