## WRAC Instructions
DO NOT PRINT THIS PAGE | - This prints out the final WRAC sheets
Instructions for the use of this WRAC template
- This prints out the risk matrix and critical controls for use by the work group
Only fill out cells that are coloured in Light Blue
This template has been protected to avoid unapproved changes.
1. YCC WRAC Front Page
a) Identify the scope of the risk assessment. This may also include what the risk assessment does not cover.
b) Add in the internal and external stakeholders.
2. WRAC
a) Once the team has been taken through the example provided in the WRAC, hide or delete those rows.
b) Hide or delete any blank rows for each identified task/activity.
c) Delete any task/activity rows that aren't required.
d) Highlight the WRAC rows and go to Page Layout > Print area and Select Set Print Area
3. Action Plan_Attend_NC Issues
a) Document any actions that have been agreed upon in the WRAC.
b) Document all WRAC attendees, noting their role, experience and have them sign the hard copy.
c) Document any disagreed matters, noting the person who has disagreed, the reason for the non-consensus, the date and their signature.
d) Obtain signatures by the department head and the SSE (if required). Note that the SSE shall sign off all SOP underpinning WRAC's.
4. Risk Matrix and 5. Core Hazards Critical Controls
a) These are reference material only and are not required to be printed with the WRA for record keeping purposes.
Print final WRAC
Print references

## 1 YCC BBRA Front Page
BROAD BRUSH RISK ASSESSMENT
Title: | Yarrabee Coal Company Pty Ltd PRCP Risk Assessment |  |  | Date of WRAC: | 2024-03-07
Purpose and Scope:
The purpose of the Risk Assessment is to: identify the risks of a stable condition for land not being achieved for the nominated PMLUs, identify the risks of the NUMAs causing environmental harm and not being safe and structurally stable, and detail an approach to manage and minimise the risks identified. The scope includes rehabilitating mining-related disturbance to the agreed landform and PMLUs/NUMAs within mining leases ML80172, ML80049, ML1770, ML80096, ML80195, ML80198, ML80104, ML80196, ML80197, and ML80050. The Boonal Haul Road and Boonal Coal Stockpile and Train Load Out facility are out of scope.
RISK METHODOLOGY:
This risk assessment shall be conducted in accordance with the YCC Risk Management Procedure. The risk assessment shall be scored using the approved Yancoal Risk Matrix. The above referenced procedure has been prepared to ensure compliance to the following tools: AS/NZS ISO 31000:2009 Risk Management; Recognised Standard 2 – Risk Management; Yancoal Risk Matrix; and Compliance requirements for data entry into the Intellex system. General Hazards have been recorded at the front of the risk assessment to allow the capture of information once rather than it being repeated in each process.
OPERATIONAL OVERVIEW
EXTERNAL CONTEXT: The Yarrabee Coal Mine is a wholly owned subsidiary of Yancoal Australia since Yancoal acquired Felix Resources Pty Ltd in December 2009. The Yarrabee Open Cut Coal Mine is located approximately 40km northeast of Blackwater in Central Queensland’s Bowen Basin, approximately 150km west of Rockhampton and 280km northwest of the Port of Gladstone. Yarrabee produces low volatile, high-energy, pulverised coal injection (LVPCI) coal which is exported to steelmakers in the Asian region. The mine is one of a small number of LVPCI mines producing high quality coals located in the Bowen Basin. In addition, thermal coal is produced and provided to export markets. The mine operates under the following jurisdictional boundaries: • Mining Operations – Coal Mining Safety and Health Act 1999; • Electrical Infrastructure – jointly through the Coal Mining Safety and Health Act 1999 and Electrical Safety Act 2002; • Radiation Safety – Radiation Safety Act 1999; • Explosives – Explosives Act 1999; • Environment – Environmental Protection Act 1994; and • Exploration – Minerals Resources Act 1989. Licence to operate is provided through mining leases (ML1770, ML80049, ML80050, ML80096, ML80104, ML80172, ML80195, ML80196, ML80197, ML80198) and environmental consent (EPML00844613) which defines the conditions of operations including the required controls for the interrelation with neighbouring property owners.
INTERNAL CONTEXT: Yarrabee Coal commenced operations in 1969 as a sole trader operation and has grown to its current standing with 387 full time equivalent employees per month. The Yarrabee coal deposit is characterised by multiple economic resource areas. This means that the resource has to be mined as a series of remote mining pits. Pits are generally located in areas where economic strip ratio is favourable and geological processes are minimal. The deposit is characterised by a series of large scale thrust faults trending in a Northwest – Southeast orientation. Numerous smaller faults are present in all mining areas and are identified by advanced drilling. YCC generally operates multiple pits at any one time. The mine’s 4 overburden fleets are split between these pits. Mining activities are generally trending towards the eastern reaches of the deposit as large strike pits are located in these areas. The mine’s CHPP (preparation plant) is located roughly in the centre of the mining leases. The train load out is located at Boonal, some 37km South of the Yarrabee mining area. Mining activities carried out at YCC is that of open cut strip mining method. This method comprises predominately truck and excavator removal of overburden and coal material. Top level unconsolidated tertiary sand and clay based material is free dug, while all other consolidated Permian materials are first drilled and blasted before removal via hydraulic excavator. Coal mining is conducted using excavators with no pre-blasting of coal measures, however, dozer ripping is often employed to loosen coal for mining. Coal is generally split into two main products: • Bypass; and • Wash coal. Bypass coal is stockpiled on various pit ROM pads for crushing and subsequent hauling to the train load out. Wash coal is loaded in pit and hauled to the CHPP for crushing and washing. Product coal is road hauled about 37km to the Boonal load out facility on the Blackwater system and then railed to the RG Tanna and WICET Terminals in Gladstone for export to customers. The Yarrabee Coal Company produces a low volatile, high-energy pulverised coal injection (PCI) product - predominantly used in the steel industry and thermal products used for power generation. The coal is produced in alignment to agreed specifications as per nominated specification sheets provided by Yancoal Marketing. Product coal is sold to a number of export customers. Production at Yarrabee has grown from a modest 1.5 million tonnes (Mt) in 2005 to up to 4Mt in 2019 as per Environmental Consent limits.
Stakeholders:
Internal |  |  | External
Employees Contractors Yancoal
Risk Assessment assumes that current controls are adequate and working:
The following controls (based on the Nertney Wheel) are considered common controls and are stated once in the context and are not repeated in the Risk Assessment table. These controls are considered as in place and adequate when scoring this risk assessment. Level 1 Risk Assessments include (PRIDE), Level 2 Risk assessments in this risk assessment include (JSA), Standard 11, Site Induction, Tool Box Meetings for Task Specific Requirements All persons who work on site, must be authorised to perform work on the site. All persons that operate/drive on site shall be authorised by the Site Senior Executive (SSE) or their appointed Delegate prior to operating any vehicle or mobile equipment on site. All personnel performing “high risk work” will possess competencies that are mapped or equivalent to the RII National Competency Framework. Minimum specifications defined for all equipment and vehicles, managed via introduction to site inspections and authorisations - identified in pre delivery inspection sheets, specifications outlined in vehicles and mobile equipment standard Safe People • Personnel present fit for work unaffected by drugs, alcohol, fatigue or any other impairment. Persons who work on site, must be authorised to perform work on the site including the operation of any vehicles or equipment. • Supervisors hold the competencies required by the Safety and Health Advisory Committee. • Personnel shall be inducted prior to the performance of any work. • Personnel have the right to stop work, where they believe that there is an unacceptable level of risk. Safe Equipment • All light and medium vehicles and heavy mobile plant including contractor equipment (except under escort) shall be inspected prior to first use on site. • Maintenance work is completed as per OEM recommendations. • Pre-start inspections are completed as per site rules and defects are reported and managed appropriately. Safe Procedures • CMW's participate in the site PRIDE and JSA processes. • Hazard reports are used to identify and report hazards. • Daily pre-shift meetings are held and address relevant hazards and information. • OCE Reports are developed and address relevant hazards. • SOP’s / SWI’s are available in Intelex. Hardcopies (uncontrolled) are available in the crib-hut and OCE Office. Access is available via the computer in the HST training room. • Trigger Action Response Plans (TARPS) in place for significant hazards. • Workplace Inspections and Access Control, specifically regarding the withdrawal of persons in unacceptable levels of risk. • Industry safety alerts are distributed and communicated to personnel. • Third party contractors are verified for equipment and process prior to the commencement of work. • Positive communications required at all times – which means that the communication is met with a verbal response. • Safety Interactions are conducted. • Audits and inspections are conducted as planned. Safe Environment • Excavation areas are only opened after inspection by the OCE. • Personnel are not permitted to go past “hazardous / restricted / signed area” signs without the permission of the OCE. • Maximum speed limits = 60 kph unless otherwise signed or conditions dictate. • Road furniture is installed throughout the mine to clearly delineate the roads, intersections etc. • Exclusion zones are established for high risk tasks and must be obeyed (e.g., blasting, working at height, geotechnical zones, brake testing areas etc.). • Weather conditions are monitored on a daily and weekly basis and actions are taken to respond to identified weather conditions. Mitigation • First aid kits available. • Dedicated site based paramedic and stocked first aid room. • Emergency Response Plan (including Emergency Response Team and ESO). • ERT Vehicle and Truck available. • Lightning detectors are available. • Designated helicopter landing zone. • First aid personnel available on site. • Strategically placed defibrillators and trauma grab bags. • Local emergency services. • Rescue helicopters available in Rockhampton.
Definitions: |  |  | Reference Materials:
ALARA As Low AS Reasonably Achievable EA Environmental Authority ERT Emergency Rescue Team JSA Job Safety Analysis LTA Less than Adequate MoC Management of Change OCE Open Cut Examiner PPE Personal Protective Equipment PRIDE Prevent Risk in Daily Environment PRO Procedure |  | SI Safety Interaction SOP Standard Operating Procedure SSE Site Senior Executive SSHR Site Safety & Health Rep SWI Safe Work Instruction TARP Trigger Action Response Plan YCC Yarrabee Coal Company WAH Working at Height WRAC Workplace Risk Assessment & Control | Recognised Standard 02 – Control of Risk Management Practices ISO31000:2018 Risk Management Coal Mining Safety and Health Act 1999 Coal Mining Safety and Health Regulation 2017 Yarrabee SHMS DNRME Hazard Database
Spell checker

## BBRA
| Title: |  | Yarrabee Coal Company Pty Ltd PRCP Risk Assessment
| Date of WRAC: |  | 2024-03-07
| RISK ASSESSMENT | [20 empty] | JUSTIFICATION
RISK ID | Task/ Activity | Aspect | Risk Description | PRCP Consequences | YCC Consequences | Cause(s) | Inherent Consequence | Yancoal Core Hazard? | Existing Control(s) | Critical Control | HoC | Initial Risk |  |  | Proposed Controls | HoC | Residual Risk |  |  | Principal Hazard? | Control Owner (Dept) | Justification for Selection | Performance Measures and Constraints | Reporting and Monitoring Requirements | Resource Requirements | Timing | Responsibility
[12 empty] | C | L | Risk |  |  | C | L | Risk
1.1 | Operating Constraints | General | Suspension of mining operations (care & maintenance) or premature closure of mine. | PRCP schedule delay Harm to People Environmental Impact Impact to Reputation | P - Harm to People E - Environmental Impact R - Impact to Reputation | *Uneconomic market conditions and/or cost-prohibitive operating conditions. |  |  | EC01- Progressive rehabilitation. EC02 - Financial surety payments to QLD Financial Provisioning Scheme - Approved ERC Decision |  |  | 4 | D | 14 (H) | PRCP DEVELOPMENT 01 - Develop a PRCP Plan and Schedule and establish progressive rehabilitation milestones and required completion criteria. PC01- Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. |  | 4 | E | 10 (M) | NO |  | *Limited controls are available to manage market conditions. *To ensure progressive rehabilitation is completed to achieve the milestone criteria. | *Protocol (checklist) developed and communicated. *Rehabilitation milestones and criteria. | *Annual risk category allocation review/decision - QLD Financial Provisioning Scheme. | Financial and JORC reports. | Annual | Yarrabee Coal Company Pty Ltd
1.2 |  | General | Insufficient technical and operational resources to plan and implement the rehabilitation plan. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Loss of/inability to attract the required technical and operational skills due to industry skills shortages and market competition. *Internal resourcing cannot manage PRCP scheduling and reporting obligations and complexity. *Undocumented rehabilitation planning systems and processes. *Rehabilitation planning and mining operational processes are not adequately integrated. *Scheduling and availability of mining resources not aligned to achieve the PRCP schedule. |  |  | EC01- Progressive rehabilitation. EC03 - Internal mine planning processes (including integration of rehabilitation planning) EC04 - Annual Budget process EC05 - Engagement of external contractors/consultants to meet skill and resource requirements. |  |  | 3 | A | 20 (H) | PRCP DEVELOPMENT 01 - Develop a PRCP Plan and Schedule and establish progressive rehabilitation milestones and required completion criteria. PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC03 - Develop and implement an IT document/record control and retention strategy to mitigate the loss of PRCP records. PC04 - Develop a PRCP obligations register to determine resourcing requirements and assign responsibilities. PC05 - Update annual budget, 5YP and LOM planning processes to integrate the approved PRCP landform, and rehabilitation milestones obligations. |  | 3 | B | 17 (H) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. *Enhance document management and retention. *To quantify the operational resources required to support PRCP implementation. | *Protocol (checklist) developed and communicated. *IT document/record control and retention strategy developed. *PRCP responsibilities mapped and assigned. | *Annual budgeting process. *Staff and contractor performance reviews. | IT Systems Personnel and equipment | Annual | Yarrabee Coal Company Pty Ltd
1.3 |  | General | Roles and responsibilities for rehabilitation planning and execution are poorly defined or communicated. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Undocumented rehabilitation planning systems and processes. *Rehabilitation planning and mining operational processes are not adequately integrated. *Onboarding processes and position descriptions are inadequate. *Scheduling and availability of mining resources not aligned to achieve the PRCP schedule. |  |  | EC06 - Documented Position Descriptions are prepared by Human Resources. EC07 - YCC Environmental Management Plans (within the EMS) describe roles and responsibilities for relevant positions. |  |  | 2 | C | 8 (M) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC04 - Develop a PRCP obligations register to determine resourcing requirements and assign responsibilities. |  | 2 | D | 5 (L) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. | *Protocol (checklist) developed and communicated. *Position descriptions updated (where relevant). | *Staff and contractor performance reviews. | Human Resources support | Annual or more frequent if required | YCC - Human Resources Manager
1.4 |  | General | Inadequate document and spatial data management to demonstrate compliance with the required rehabilitation milestones and criteria. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Data loss due to no centralised data/record storage system. *Document and spatial management systems are not aligned to support the complexity of the PRCP reporting requirements. *Internal resourcing cannot manage the complex PRCP scheduling and reporting obligations. *Historical technical studies and data not available to support the approved rehabilitation milestones completion criteria. |  |  | EC03 - Internal mine planning processes (including integration of rehabilitation planning) EC05 - Engagement of external contractors/consultants to meet skill and resource requirements. |  |  | 2 | A | 16 (H) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC03 - Develop and implement an IT document/record control and retention strategy to mitigate the loss of PRC Plan records. |  | 2 | C | 8 (M) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. *Enhance document management and retention. | *Protocol (checklist) developed and communicated. *IT document/record control and retention strategy developed. *PRCP responsibilities mapped and assigned. | *Annual Return reporting *3 Yearly PRCP audits | IT Systems Personnel and equipment | Annual or more frequent if required | Yancoal - Approvals Manager
1.5 |  | General | Loss of stakeholder support for the agreed PMLU e.g. land suitability class. | PRCP not approved | O - Asset Damage and Other Consequential Losses | *Inadequate stakeholder engagement and consultation. *Supply of insufficient or inaccurate information. |  |  | EC08 - Operational stakeholder (including Government) engagement - irregular frequency. |  |  | 3 | B | 17 (H) | PRCP DEVELOPMENT 02 - Implement a structured stakeholder engagement program to confirm acceptance of the YCC PRC Plan. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC06 - Implement a structured stakeholder engagement plan to support the operational implementation of the PRC Plan. |  | 3 | E | 6 (M) |  |  | *To ensure PMLU meets the relevant stakeholder expectations. | Stakeholder engagement plan implemented | Stakeholder engagement records | Consultant support | 2024-12-01 | YCC - E&C Team Leader
1.6 |  | General | Future regulatory changes make the NUMAs unacceptable. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Legislative and regulation amendments by the QLD government. |  |  | EC08 - Operational stakeholder (including Government) engagement - irregular frequency. EC09 - Monitor regulatory changes and provide submissions on future regulatory changes as required. |  |  | 4 | C | 18 (H) | PRCP DEVELOPMENT 03 - Submitting a properly made PRC Plan and Schedule, seeking approval for the agreed PMLU and NUMAs to protect against potential approval appeals. |  | 4 | E | 10 (M) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. | PRCP application deemed properly made by DESI | Not Applicable | Consultant support | 2024-12-01 | Yarrabee Coal Company Pty Ltd
1.7+8:14 |  | General | The rehabilitation monitoring program does not adequately measure completion criteria. | PRCP schedule delay Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Historical rehabilitation monitoring did not consider the new completion criteria. *Undocumented rehabilitation planning systems and processes. |  |  | EC10 - Annual rehabilitation monitoring program. |  |  | 2 | B | 12 (M) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC03 - Develop and implement an IT document/record control and retention strategy to mitigate the loss of PRCP records. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRC Plan. |  | 2 | D | 5 (L) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. | *Tracking against the relevant milestone criteria. | *Rehabilitation monitoring program and records. *Annual Return reporting *3 Yearly PRCP audits | Consultant support | Annual or more frequent if required | YCC - E&C Team Leader
2.1 | Waste Emplacement (Out of Pit) | Landform | The landform surface is physically unstable (rilling, erosion and mass movement) preventing PMLU from being achieved. | PRCP schedule delay Harm to People Environmental Impact Increased rework and M&M costs | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Landforms not constructed to the approved design. *Geotechnical and erosional instability due to rock strata and overburden material characteristics. *Inadequate overburden and topsoil amelioration (dispersive material). *Landform not free-draining, causing surface ponding. *Uncontrolled concentrated surface water flows causing sediment mobilisation (sheet/rilling erosion). *Inadequate ground cover due to failed vegetation establishment and/or unsuitable species. *Final ground preparation leaves a rough and untraversable surface e.g. large rocks, uneven surface etc. |  |  | EC03 - Internal mine planning processes (including integration of rehabilitation planning). EC11 - WRD designed by an AQP to achieve a Factor of Safety of 2.0. EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC13 - Existing landforms have integrated Landloch geofluvial recommendations. EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design, including slope angle e.g., survey control, and as-built. EC15 - Amelioration of topsoil and subsoil material using generic rates. EC16 - Rock mulching of steeper slopes (where required). EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). |  |  | 3 | B | 17 (H) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRC Plan. PC08 - Water Management system to be designed by AQP and constructed by experienced persons. PC9 - Amelioration of topsoil and subsoil material using AQP recommended rates based on specific rehabilitation area soil testing. |  | 1 | C | 4 (L) |  |  | *To ensure progressive rehabilitation is completed to achieve the milestone criteria. *RPEQ and AQP signoff to ensure designs meet current standards. | *Tracking against the relevant milestone criteria. *RPEQ and AQP sign off | *Geotechnical observations and monitoring *Rehabilitation monitoring program and records. *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
2.2 |  | Landform | Slope angles too steep or rough to support PMLU e.g. grazing | PRCP schedule delay Harm to People Environmental Impact Increased rework and M&M costs | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Landforms not constructed to the approved design. *Some legacy landforms are not consistent with the new PRCP completion criteria. *Over dumping against approved limits (approval boundary ). *Final ground preparation leaves a rough and untraversable surface e.g. large rocks, uneven surface etc. |  |  | EC03 - Internal mine planning processes (including integration of rehabilitation planning). EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design, e.g., survey control and as-built. EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). |  |  | 2 | D | 5 (L) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRC Plan. PRCP DEVELOPMENT 04 - Where required, legacy landform criteria are to be detailed in the PRC Plan. |  | 1 | C | 4 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *RPEQ and AQP signoff to ensure designs meet current standards. | *Tracking against the relevant milestone criteria. *Geotechnical design. *RPEQ and AQP sign off. | *Geotechnical observations and monitoring *Rehabilitation monitoring program and records. *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
2.3 |  | Release to Water | Modified landform changes surface hydrological regime affecting downstream environment and water users. | Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Landforms not constructed to the approved design. *Changes to natural drainage paths and reduction in surface flow disrupt downstream water-dependent flora and fauna ecosystems. *Changed stream geomorphology, resulting in modified instream sediment transport processes. *Pit inundation during flood events (harvesting surface flow). |  |  | EC11 - WRD designed by an AQP to achieve a Factor of Safety of 2.0. EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as-built. EC18 - Construction of landform to achieve 1:1000 AEP flood immunity (12-Mile Creek flood study). EC19 - The existing Yen Pit Levee (and clean water diversion) and A Pit Levee prevent flood water from inundating mining areas. EC20 - Implementation of the Yarrabee Erosion and Sediment Control Plan (ESCP). EC21 - External surface water monitoring program (including annual REMP) to assess downstream water quality, morphology, and aquatic changes. |  |  | 3 | C | 13 (H) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC08 - Water Management system to be designed by AQP and constructed by experienced persons. |  | 3 | D | 9 (M) |  |  | *To ensure progressive rehabilitation is completed to the required standard. | *Tracking against the relevant milestone criteria. *RPEQ and AQP sign off | *Geotechnical observations and monitoring *Rehabilitation monitoring program and records. *ESCP monitoring program and records. *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
2.4 |  | Release to Water - Sediment-laden Water | Discharge of sediment-laden water into the receiving environment due to surface erosion. | PRCP schedule delay Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Landforms not constructed to the approved design. *Stormwater runoff from disturbed areas during rainfall events. *Erosion and sediment controls are not designed, constructed or maintained. *Inadequate ground cover due to failed vegetation establishment and/or unsuitable species. |  |  | EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). EC20 - Implementation of the Yarrabee Erosion and Sediment Control Plan (ESCP). EC21 - External surface water monitoring program (including annual REMP) to assess downstream water quality, morphology, and aquatic changes. EC22 - Operation and maintenance of a mine water management system e.g. Pumps, pipes, dams. |  |  | 3 | B | 17 (H) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC08 - Water Management system to be designed by AQP and constructed by experienced persons. PC010 - All external draining catchments to maintain a site-specific ESCP detailing the required erosion and sediment controls. |  | 3 | D | 9 (M) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To prevent environmental harm. | *Tracking against the relevant milestone criteria. *RPEQ and AQP sign-off. *Site-specific ESCP Plans developed and implemented. | *Geotechnical observations and monitoring *Rehabilitation monitoring program and records. *ESCP monitoring program and records. **Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
2.5 |  | Release to Water - Contaminant | Discharge of acidic/saline water into the receiving environment, causing environmental harm (surface water and groundwater). | PRCP schedule delay Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Landforms not constructed to the approved design *Chemical instability resulting in acid/saline seepage (Geochemical properties of overburden material not understood or monitored). *Inadequate waste tracking and dumping strategy. *Inadequate design and construction of the water management system. |  |  | EC20 - Implementation of the Yarrabee Erosion and Sediment Control Plan (ESCP). EC21 - External surface water monitoring program (including annual REMP) to assess downstream water quality, morphology, and aquatic changes. EC22 - Operation and maintenance of a mine water management system e.g. Pumps, pipes, dams. EC23 - Internal surface water quality sampling program to assess changes. EC24 - Preferential placement of weathered materials (< 1m cover) below topsoil to cover saline sandstone material. |  |  | 3 | C | 13 (H) | PRCP DEVELOPMENT 05 - Review the adequacy of the overburden material geochemical testing program to identify Potentially Acid Forming (PAF) and/or high saline risk materials and review current mineral waste management practices. PC08 - Water Management system to be designed by AQP and constructed by experienced persons. PC11 - Informed by the geochemical analysis, update the internal surface water monitoring program. |  | 3 | D | 9 (M) |  |  | *To improve knowledge of future geochemical risk and inform best management practices. | A geochemical study is completed. *AQP sign-off. Updated Mineral Waste Management Plan (or similar) | *Material characterisation study report. *Operational geochemical testing program and records. *Surface water monitoring program and records | *AQP *Laboratory | Annual or more frequent if required | YCC - Geologist
2.6 |  | Ecology - Flora and Fauna (Terrestrial) | Inadequate growth medium (topsoil) to support rehabilitation. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Inadequate topsoil volumes to rehabilitate current disturbance areas. *Poor soil structure and fertility due to inherent physical and chemical properties limiting seed germination and plant growth. |  |  | EC15 - Amelioration of topsoil and subsoil material using generic rates. EC25 - Implement topsoil salvaging management recommendations based on soil type as described in the Rehabilitation Management Plan (RMP). EC26 - Maintain topsoil inventory to quantify supplementary growth medium requirements. EC27 - Preferential placement of weathered materials (< 1m cover) below topsoil to cover saline sandstone material. EC28 - Application of organics e.g. cow manure, biosolids to improve topsoil organic fraction. |  |  | 3 | A | 20 (H) | PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC12 - Support industry research and/or conduct site-specific trials into topsoil substitution and enhancement alternatives, e.g. Tailings to Topsoil PC13 - Source alternative organic material suppliers to enhance existing topsoil inventories. PC14 - Review current topsoil salvage and amelioration practices to optimise topsoil management e.g. amelioration/biological enhancement before salvage. PC09 - Amelioration of topsoil and subsoil material using AQP recommended rates based on specific rehabilitation area soil testing. |  | 3 | B | 17 (H) |  |  | *To identify opportunities for optimising current and future growth medium resources to address the current topsoil volume deficit. | Topsoil inventory deficit. | Topsoil inventory tracking. | *Research organisations *Alternative growth medium suppliers *Laboratory | As required. | YCC - E&C Team Leader
2.7 |  | Ecology - Flora and Fauna | Poor germination percentage/tube stock survival delay or prevent PMLU from being achieved. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Physically unstable landform (erosion). *Poor soil structure and fertility due to inherent physical and chemical properties limiting seed germination and plant growth. *Ground preparation and seeding methodology/equipment not suitable for conditions. *Poor seed viability. *Species mix not suitable for the soil type, aspect and landform. *Competition in native vegetation PMLU from undesirable invasive species, e.g. Chloris gayana and Cenchrus ciliaris, and other weed species. *Unfavourable weather conditions and extreme climate variables, e.g. extended dry periods and intense storm events. |  |  | EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC15 - Amelioration of topsoil and subsoil material using generic rates. EC16 - Rock mulching of steeper slopes (where required). EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). EC25 - Implement topsoil salvaging management recommendations based on soil type as described in the Rehabilitation Management Plan (RMP). EC29 - Seeding/tube stock planting is completed to align with optimal seasonal conditions EC30 - Seeding/tube stock planting completed by experienced persons with fit-for-purpose equipment. |  |  | 2 | B | 12 (M) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC09 - Amelioration of topsoil and subsoil material using AQP recommended rates based on specific rehabilitation area soil testing. PC12 - Support industry research and/or conduct site-specific trials into topsoil substitution and enhancement alternatives, e.g. Tailings to Topsoil PC13 - Source alternative organic material suppliers to enhance existing topsoil inventories. PC14 - Review current topsoil salvage and amelioration practices to optimise topsoil management e.g. amelioration/biological enhancement before salvage. PC15 - Review seed storage and inventory controls to mitigate impacts to seed viability PC16 - Review the effectiveness of YCC-ENV-MP-209-004 Invasive Species (Flora and Fauna) Management Plan and update the ongoing control program accordingly. PC17 - Support industry research and/or conduct site-specific trials e.g. fire and grazing to assess opportunities to modify invasive species composition. |  | 2 | D | 5 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To reduce risk of rehabilitation failure. | *Tracking against the relevant milestone criteria.. | *Rehabilitation monitoring program and records. *Annual rehabilitation reporting. *Seed inventory tracking. | *Rehabilitation monitoring consultants *Research organisations. *Alternative growth medium suppliers *Suitable seed storage facility. | Annual or more frequent if required | YCC - E&C Team Leader
2.8 |  | Ecology - Flora and Fauna | Sown seed mix and planted tube stock species are incompatible with the approved PMLU. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Historical seed mix/tube stock species were not selected to achieve a specific Regional Ecosystem or PMLU. *Domination by certain planted species, e.g. Buffel Grass, prevents the required species diversity. *The nominated native species cannot be sourced or are unavailable due to industry demand. |  |  | C17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). EC30 - Seeding/tube stock planting completed by experienced persons with fit-for-purpose equipment. |  |  | 2 | A | 16 (H) | PRCP DEVELOPMENT 06 - Specify in the PRCP, the required species mix to achieve the agreed PMLU outcomes. PRCP DEVELOPMENT 07—The approved PRCP will detail legacy rehabilitation areas and established species that are not consistent with the proposed species. PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule PC03 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC18 - Identify local seed sources and/or seed merchants to secure future seed requirements. |  | 2 | C | 8 (M) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To ensure the correct seed mix aligns with PMLU and is available. *Identify management practices to modify species composition to achieve the required PMLU | *Tracking against the relevant milestone criteria.. *Research and trials. | *Rehabilitation monitoring program and records. *Annual rehabilitation reporting. *Research and trial reports. | *Rehabilitation monitoring consultants *Research organisations. *Alternative seed suppliers | Annual or more frequent if required | YCC - E&C Team Leader
2.9 |  | Ecology - Flora and Fauna | Poor resilience/survival of established rehabilitation prevents sustainable long-term PMLU outcomes. | PRCP schedule delay Increased rework and M&M costs | O - Asset Damage and Other Consequential Losses | *Poor soil structure and fertility due to inherent physical and chemical properties limiting seed germination and plant growth. *Bushfires (severity and frequency). *Changes in climatic conditions over time. *Overgrazing from domestic and native animals. *Competition from undesirable invasive species, e.g.Chloris gayana and Cenchrus ciliaris, and other weed species. |  |  | C17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). |  |  | 2 | C | 8 (M) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC12 - Support industry research and/or conduct site-specific trials, e.g. fire and grazing, to assess opportunities to modify invasive species composition. PC19 - Support industry research and/or conduct site-specific resilience trials on established rehabilitation areas e.g. Bushfire burn. |  | 2 | C | 8 (M) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To ensure the seed mix aligns with PMLU and is available. *Identify management practices to demonstrate rehabilitation resilience. | *Tracking against the relevant milestone criteria.. *Research and trials. | *Rehabilitation monitoring program and records. *Annual rehabilitation reporting. *Research and trial reports. | *Rehabilitation monitoring consultants *Research organisations. | Annual or more frequent if required | YCC - E&C Team Leader
3.1 | Backfilled Voids | Landform | The backfilled void landforms of C-Pit, DE-Pit, DOM3 and H-Pit are physically unstable (settlement/subsidence) preventing PLMU from being achieved. | PRCP schedule delay Harm to People Increased rework and M&M costs | P - Harm to People O - Asset Damage and Other Consequential Losses | *Subsidence/settlement of backfilled material creating an uneven surface. *Landform not free-draining, causing surface ponding. *Overburden dumping strategy does enable a final landform sympathetic to the surrounding landscape to be achieved. *Final ground preparation leaves a rough and untraversable surface e.g. large rocks, uneven surface etc. *Changes to the mine plan impact the availability of suitable backfill material. |  |  | EC12 - WRD final landform design incorporates water management and erosion control features such as drainage swales/channels and sediment dams. EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as built. EC14 - Amelioration of topsoil and subsoil material using generic rates. EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). EC18 - Construction of landform to achieve 1:1000 AEP flood immunity (12-mile Creek flood study). |  |  | 2 | D | 5 (L) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements. PC03 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC09 - Amelioration of topsoil and subsoil material using AQP recommended rates based on specific rehabilitation area soil testing. PC20- Landform design to consider elevating the final surface profile and benching at the Highwall interface zone to mitigate against sheer failure. |  | 2 | D | 5 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *RPEQ and AQP signoff to ensure designs meet current standards. | *Tracking against the relevant milestone criteria.. *RPEQ and AQP Sign off | *Rehabilitation monitoring program and records. *Water quality monitoring program *Annual rehabilitation reporting. *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs *Rehabilitation monitoring consultants | Annual or more frequent if required | YCC - Technical Services Manager
3.2 |  | Groundwater | Backfilled void groundwater quality is poor and contaminates local groundwater systems. | PRCP schedule delay Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Leaching of contaminants into local groundwater system as a source. |  |  | EC31 - Residual voids are modelled as groundwater ‘sinks’ (Engeny, 2018). EC32 - No connectivity with Mackenzie River Alluviums. |  |  | 3 | D | 9 (M) | PRCP DEVELOPMENT 05- Review the adequacy of the overburden material geochemical testing program to identify Potentially Acid Forming (PAF) and/or high saline risk materials and review current mineral waste management practices. PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09- Assess groundwater conditions and impacts from mining activities and future landforms. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC21 - Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. |  | 3 | D | 9 (M) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To prevent environmental harm. | *Tracking against the relevant milestone criteria.. *Groundwater criteria. *AQP Sign off | *Rehabilitation monitoring program and records. *Groundwater quality monitoring program and records. *Annual rehabilitation reporting. | *Groundwater monitoring network *Environmental monitoring consultants. *Laboratory | Annual or more frequent if required | YCC - E&C Team Leader
3.3 |  | Soil | Landform is not free-draining resulting poor water quality runoff and salt accumulation in the soil. | PRCP schedule delay Environmental Impact Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Subsidence/settlement of backfilled material. *Landform not free-draining, causing surface ponding. *Evaporation of saline ponded water results in salt accumulation in the soil, adversely impacting vegetation growth. |  |  | EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as built. EC17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). |  |  | 2 | D | 5 (L) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. |  | 2 | D | 5 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *RPEQ and AQP signoff to ensure designs meet current standards. | *Tracking against the relevant milestone criteria.. *RPEQ and AQP Sign off | *Rehabilitation monitoring program and records. *Water quality monitoring program *Annual rehabilitation reporting. *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs *Rehabilitation monitoring consultants | Annual or more frequent if required | YCC - Technical Services Manager
See 2.6 |  | Ecology - Flora and Fauna (Terrestrial) | Inadequate growth medium (topsoil) to support rehabilitation. (SEE RISK ID 2.6) | [8 empty] | 3 | A | 20 (H) |  |  | 3 | B | 17 (H)
See 2.7 |  | Ecology - Flora and Fauna | Poor germination percentage/tube stock survival rates delay rehabilitation milestones or prevent PMLU from being achieved. (SEE RISK ID 2.7) | [8 empty] | 2 | B | 12 (M) |  |  | 2 | D | 5 (L)
See 2.8 |  | Ecology - Flora and Fauna | Sown seed mix and planted tube stock species are not compatible with the approved PMLU. (SEE RISK ID 2.8) | [8 empty] | 2 | A | 16 (H) |  |  | 2 | C | 8 (M)
See 2.9 |  | Ecology - Flora and Fauna | Poor long-term resilience/survival of established rehabilitation areas prevents sustainable PMLU outcomes. (SEE RISK ID 2.9) | [8 empty] | 2 | C | 8 (M) |  |  | 2 | C | 8 (M)
4.1 | NUMAs | Landform | Catastrophic pit wall failure (high-wall and end wall) | PRCP schedule delay Environmental Impact Harm to People Increased rework and M&M costs Impact to Reputation | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Unstable geotechnical conditions e.g. YEN Pit end wall due to interface with coal-weathered zone *Seismic activity. *Inadequate water management around the high wall and end wall. *Geotechnical design criteria not achieved. |  |  | EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as built. EC19 - The existing Yen Pit Levee (and clean water diversion) and A Pit Levee prevent flood water from inundating mining areas. EC33 -An AQP completed a residual void pit slope stability study to inform the residual void slope design criteria for geotechnical and erosion hazards. EC34 - Design criteria for high walls and end walls require a factor of safety against slope instability of 2 |  |  | 2 | A | 16 (H) | PC22 - Landforms around voids will be established to provide immunity from the 1:1000 AEP flood level. PC23 - Reinstate flow lines on natural ground contours around constructed landforms to divert surface water around voids. PC24 - Complete an AQP geotechnical review of the final residual void (slope angle and length) to confirm its geotechnical stability and required remedial actions. PC25 - Treat Highwall e.g. Blast, regrade and low wall e.g. regrade, based on geotechnical design criteria. PC26 - Partially backfill CE North Void to achieve geotechnical design criteria against approval boundary limits. PC27 - Slopes of partially backfilled voids (A-Pit, CE-North and DOM1) to be shaped to a maximum slope of 25% (or another suitable slope determined by landform and erosion studies). PC28- Construct pit barricades/ safety Berm and erect safety signage per the RMP. PC29 - Landforms around the voids constructed to limit the slopes and slope lengths conveying surface run-off onto end and high walls. |  | 2 | D | 5 (L) |  |  | *RPEQ and AQP signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure landform is safe | *Tracking against the relevant milestone criteria.. *Geotechnical design. *RPEQ and AQP Sign off | *Geotechnical observations and monitoring *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
4.2 |  | Landform | The landform is physically unstable (erosion) | PRCP schedule delay Environmental Impact Harm to People Increased rework and M&M costs | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Overburden material comprising Quaternary, Tertiary and weathered Permian strata is chemically and physically unstable to runoff and rainfall impacts. *Inadequate water management around the high wall and end wall. *Approval boundary constraints prevent drainage features from being constructed around CE North Highwall. *Upslope flow line erosion caused by constructed drainage controls. |  |  | EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as built. EC19 - The existing Yen Pit Levee (and clean water diversion) and A Pit Levee prevent flood water from inundating mining areas. EC33 -An AQP completed a residual void pit slope stability study to inform the residual void slope design criteria for geotechnical and erosion hazards. EC34 - Design criteria for high walls and end walls require a factor of safety against slope instability of 2. |  |  | 2 | B | 12 (M) | PC02 - Establish progressive rehabilitation in accordance with the PRC Plan and Schedule PC22 - Landforms around voids will be established to provide immunity from the 1:1000 AEP flood level. PC23- Reinstate flow lines on natural ground contours around constructed landforms to divert surface water around voids. PC24 - Complete an AQP geotechnical review of the final residual void (slope angle and length) to confirm its geotechnical stability and required remedial actions. PC25 - Treat Highwall e.g. Blast, regrade and low wall e.g. regrade, based on geotechnical design criteria. PC26 - Partially backfill CE North Void to achieve geotechnical design criteria against approval boundary limits. PC27 - Slopes of partially backfilled voids (A-Pit, CE-North and DOM1) to be shaped to a maximum slope of 25% (or another suitable slope determined by landform and erosion studies). PC28 - Construct pit barricades/ safety Berm and erect safety signage per the RMP. PC29 - Landforms to be designed and constructed to limit the inward draining catchment area of the void to the smallest extent possible PC30 - Establish Native vegetation on the void batters to assist in surface stablisation. |  | 2 | D | 5 (L) |  |  | *RPEQ and AQP signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe | *Tracking against the relevant milestone criteria.. *Geotechnical design. *RPEQ and AQP sign off. | *Geotechnical observations and monitoring *Survey monitoring and As-Built drawings | *RPEQ and AQP *Engineering designs | Annual or more frequent if required | YCC - Technical Services Manager
4.3 |  | Groundwater | Void depressurises the local groundwater aquifer, impacting GDE and water users. | Environmental Impact Impact to Reputation | E - Environmental Impact R - Impact to Reputation | *Excavation of open cut pit depressurises the natural groundwater system * Reduction of groundwater levels and yield from local groundwater bores |  |  | EC35 - Groundwater assessment confirms that the aquifer is low-yielding, poor quality and not suitable for stock and domestic consumption. EC36 - There are no known or mapped GDE or private bores within the depressurisation zone. EC37 - There is no significant evidence of inflows from groundwater within the currently active pits (Engeny 2018). |  |  | 1 | C | 4 (L) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC21 - Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. PC31 - Review the potential existence of GDE and mining related impacts. |  | 1 | D | 2 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To prevent environmental harm. | *Tracking against the relevant milestone criteria.. *Groundwater criteria. *AQP Sign off | *Rehabilitation monitoring program and records. *Groundwater quality monitoring program and records. *Annual rehabilitation reporting. | *Groundwater monitoring network *Environmental monitoring consultants. *Laboratory | Annual or more frequent if required | YCC - E&C Team Leader
4.4 |  | Groundwater | Void water quality is poor and contaminates local groundwater and surface water systems (Source) | Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Leaching of contaminants into local groundwater system due to depressurisation * Elevated void water levels interact with surface water systems, impacting aquatic systems and water quality. |  |  | EC31 - Residual voids are modelled as groundwater ‘sinks’ (Engeny, 2018). EC37 - There is no significant evidence of inflows from groundwater within the currently active pits (Engeny 2018). EC38 - Current water balance modelling confirms void capacity will not be exceeded (Engeny, 2018). |  |  | 1 | C | 4 (L) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PRCP DEVELOPMENT 10 - Calibrate and update the residual void Water balance model based on groundwater assessment. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC21- Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. PC29 - Landforms to be designed and constructed to limit the inward draining catchment area of the void to the smallest extent possible |  | 1 | D | 2 (L) |  |  | *To ensure progressive rehabilitation is completed to the required standard. *To prevent environmental harm. | *Tracking against the relevant milestone criteria.. *Surface water criteria. *AQP Sign off | *Rehabilitation monitoring program and records. *Surface water monitoring program and records *Annual rehabilitation reporting. | *Environmental monitoring consultants. *Laboratory | Annual or more frequent if required | YCC - E&C Team Leader
4.5 |  | Surface water | Pit water exceeds void containment and discharges into the receiving environment (including DOM1 - TSF ) | Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Failure of A Pit Levee and Yen Pit Levee and clean water diversions resulting in flood water inundation of A-Pit, CE-North and DOM1 voids. *Harvesting of surface water flows from surrounding catchment areas. *Extreme wet climate conditions increase surface water harvesting. |  |  | EC19 - The existing Yen Pit Levee (and clean water diversion) and A Pit Levee prevent flood water from inundating mining areas. EC38 - Current water balance modelling confirms void capacity will not be exceeded (Engeny, 2018). |  |  | 3 | C | 13 (H) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PRCP DEVELOPMENT 10 - Calibrate and update the residual void water balance model based on groundwater assessment. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC21 - Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. PC22 - Landforms around voids will be established to provide immunity from the 1:1000 AEP flood level. PC23 - Reinstate flow lines on natural ground contours around constructed landforms to divert surface water around voids. PC29 - Landforms to be designed and constructed to limit the inward draining catchment area of the void to the smallest extent possible |  | 3 | D | 9 (M) |  |  | *RPEQ signoff to ensure designs meet current standards. *To ensure progressive rehabilitation is completed to the required standard. *To prevent environmental harm. | *Tracking against the relevant milestone criteria.. *Surface water and groundwater criteria. *Engineering design *AQP Sign off | *Rehabilitation monitoring program and records. *Groundwater quality monitoring program and records. *Surface water monitoring program and records * Residual void water balance model *Annual rehabilitation reporting. | *RPEQ and AQP *Groundwater monitoring network *Environmental monitoring consultants. | Annual or more frequent if required | YCC - E&C Team Leader
4.6 |  | Landform | NUMA extent exceeds approved limits (approval boundary ) e.g. CE Pits | PRCP schedule delay Environmental Impact Impact to Reputation | E - Environmental Impact R - Impact to Reputation | *Proximity of the current void extent prevents geotechnical design criteria from being achieved. *High wall and end wall failure due to unstable geotechnical conditions. *High wall and end wall failure due to inadequate water management. |  |  | EC14 - QA/QC processes are incorporated into engineered structures and built landforms to confirm conformance with design e.g. survey control and as built. EC19 - The existing Yen Pit Levee (and clean water diversion) and A Pit Levee prevent flood water from inundating mining areas. EC33 -An AQP completed a residual void pit slope stability study to inform the residual void slope design criteria for geotechnical and erosion hazards. |  |  | 3 | A | 20 (H) | PC22 - Landforms around voids will be established to provide immunity from the 1:1000 AEP flood level. PC23 - Reinstate flow lines on natural ground contours around constructed landforms to divert surface water around voids. PC24 - Complete an AQP geotechnical review of the final residual void (slope angle and length) to confirm its geotechnical stability and required remedial actions. PC25 - Treat Highwall e.g. Blast, regrade and low wall e.g. regrade, based on geotechnical design criteria. PC26 - Partially backfill CE North Void to achieve geotechnical design criteria against approval boundary limits. PC29 - Landforms to be designed and constructed to limit the inward draining catchment area of the void to the smallest extent possible |  | 3 | D | 9 (M) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe | *Tracking against the relevant milestone criteria.. *Geotechnical design. *RPEQ sign off. | *Geotechnical observations and monitoring *Survey monitoring and As-Built drawings | *RPEQ and AQP. *Engineering designs. | Annual or more frequent if required | YCC - Technical Services Manager
5.1 | TSF | Surface Water | TSF capping construction delay or failure to support the required PMLU ((DE-PIT – Grazing and DOM 1 TSF - NUMA). | PRCP schedule delay Environmental Impact Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Residual tailings do not achieve the required drying and consolidation/settlement to support the required capping design. *Inadequate engineered capping design. *Inadequate suitable material to achieve capping design criteria. *Capping not installed in accordance with design. *Proposed vegetation species compromise TSF cap integrity e.g. root penetration. |  |  | EC39 - DOM 1 tailings are contained within a residual void. EC40 - DE Pit is not considered a regulated structure, with tailings primarily contained within a residual void. |  |  | 2 | A | 16 (H) | PC32 - A TSF design engineer (RPEQ) to prepare a detailed geotechnical design for the capping and closure of TSF (including rehabilitation considerations). PC33 - Capping construction activities to be supervised by experienced persons and certification of the As-Built by an SQP following construction. |  | 2 | D | 5 (L) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Tracking against the relevant milestone criteria.. *Geotechnical capping design. *RPEQ sign off. | *Geotechnical observations and monitoring *Groundwater quality monitoring program and records. *Survey monitoring and As-Built drawings *Capping As-built certification. | *RPEQ. *Engineering designs. *Groundwater monitoring network. | For facility closure | YCC - Technical Services Manager
5.2 |  | Surface Water | Catastrophic failure of TSF wall (DE-Pit). | PRCP schedule delay Environmental Impact Harm to People Increased rework and M&M costs Impact to Reputation | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *The dam wall and TSF cap do not function in accordance with the design criteria. *Inadequate management of surface water, causing gully erosion. |  |  | EC40 - DE Pit is not considered a regulated structure, with tailings primarily contained within a residual void. |  |  | 1 | C | 4 (L) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PRCP DEVELOPMENT 11 - Review tailings management strategy to determine LOM tailings disposal requirements. PC32 - A TSF design engineer (RPEQ) to prepare a detailed geotechnical design for the capping and closure of TSF (including rehabilitation considerations). PC34 - Complete a wet cover capping design study for DOM1 if required. |  | 1 | D | 2 (L) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Tracking against the relevant milestone criteria.. *Engineering wall design *RPEQ sign off. | *Geotechnical observations and monitoring *Survey monitoring and As-Built drawings | *RPEQ. *Engineering designs. | For facility closure | YCC - Technical Services Manager
5.3 |  | Groundwater | Contaminated groundwater seepage into the receiving environment causes environmental harm (DE-PIT and DOM 1 TSF). | Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *TSF void becomes a groundwater source. *Changed long-term hydrogeological conditions due to increased groundwater recharge. |  |  | EC31 - Residual voids are modelled as groundwater ‘sinks’ (Engeny, 2018). EC41 - Historical testing of tailings confirms that there are no contaminants and are considered to be alkaline, non-saline and non-acid producing (UDP, 2015). J32:J39 |  |  | 2 | C | 8 (M) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC21 - Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. PC32 - A TSF design engineer (RPEQ) to prepare a detailed geotechnical design for the capping and closure of TSF (including rehabilitation considerations). PC34 - Complete a wet cover capping design study for DOM1. |  | 2 | D | 5 (L) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Tracking against the relevant milestone criteria.. *Geotechnical capping design. *RPEQ sign off. | *Geotechnical observations and monitoring *Groundwater quality monitoring program and records. *Survey monitoring and As-Built drawings | *RPEQ. *Engineering designs. *Groundwater monitoring network. | For facility closure | YCC - Technical Services Manager
see 4.5 |  | Surface Water | Pit water exceeds void containment and discharges into the receiving environment causing environmental harm (including DOM1 - TSF ). (SEE RISK ID 4.5) | [8 empty] | 3 | C | 13 (H) |  |  | 3 | D | 9 (M)
6.1 | Infrastructure Decommissioning | PRCP Development | Failure to remove or make safe mining infrastructure creates an unsafe PMLU. | PRCP schedule delay Harm to People Environmental Impact Increased rework and M&M costs Impact to Reputation | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Poor site records resulting in services being unable to be located. *Exploration holes not sealed (grouted) and drill pad and sumps not rehabilitated. *Failure to reach an agreement to retain infrastructure with the underlying landholder. *Inadequate decommissioning planning and execution. *Hazardous materials not removed. *Contaminated lands not identified and/or remediated. |  |  | EC02 - Financial surety payments to QLD Financial Provisioning Scheme - Approved ERC Decision. EC42 - The location of above-ground and below-ground services are detailed in the Site Services Register. EC43 - Sealing and rehabilitation status of exploration holes are detailed in the sites Geodatabase EC44 - The location of hazardous materials maintained in a Hazardous Materials Register |  |  | 3 | C | 13 (H) | PC35- Engage an AQP for closure and decommissioning planning. PC36 - Engaged an AQP to complete Phase 1 and Phase 2 (if required) land contamination investigations. PC37- Engage an AQP and licenced contractor for decommissioning plant and equipment. PC38 - Complete the current exploration borehole audit program across all tenements to confirm the status of sealing and drill pad rehabilitation in accordance with the relevant government guidelines and standards. PC39 - Establish a written agreement with the underlying landholder detailing infrastructure condition and maintenance requirements, e.g. Property Management Plan. |  | 3 | D | 9 (M) | NO |  | *RPEQ and AQP signoff to ensure decommissioning activities meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | * Assessment using site services and geodatabase registers. *Physical inspections and testing. *As-Built drawings *Decommissioning Plan *RPEQ and AQP signoff | *External and Internal Audits *Decommissioning Plan *Survey monitoring and As-Built drawings | *RPEQ and AQP * Assessment using site services and geodatabase registers. *As-Built drawings | Prior to cessation of Mining. | YCC - Technical Services Manager
6.2 |  | Infrastructure | Retained infrastructure is not fit for final land use e.g. Buildings, Dams | Harm to People Environmental Impact Impact to Reputation | P - Harm to People E - Environmental Impact R - Impact to Reputation | *Lack of maintenance compromises structural integrity, e.g. buildings, water management infrastructure *Retained dams have reduced storage capacity due to excessive sediment buildup. |  |  | EC45 - Operational inspections and maintenance programs e.g. work orders |  |  | 1 | C | 4 (L) | PC35 - Engage an AQP for closure and decommissioning planning. PC39 - Establish a written agreement with the underlying landholder detailing infrastructure condition and maintenance requirements, e.g. Property Management Plan. |  | 1 | D | 2 (L) |  |  | *RPEQ and AQP signoff to ensure designs meet current standards. *To ensure the landform is safe. | *Physical inspections and testing. *As-Built drawings *RPEQ and AQP signoff *Property Management Plan | *Monitoring and maintenance records. *Survey monitoring and As-Built drawings | *RPEQ and AQP *As-Built drawings | Prior to cessation of Mining. | YCC - E&C Team Leader
6.3 |  | Infrastructure | Retained dam water quality is unsuitable to support PMLU e.g. grazing | Environmental Impact | E - Environmental Impact | *Elevated salt levels *Contaminated lands not identified and/or remediated. |  |  | EC24 - Internal surface water quality sampling program to assess changes. |  |  | 1 | C | 4 (L) | PC35 - Engage an AQP for closure and decommissioning planning. PC39 - Establish a written agreement with the underlying landholder detailing infrastructure condition and maintenance requirements, e.g. Property Management Plan. |  | 1 | D | 2 (L) |  |  | *AQP signoff to ensure the water storage meets the intended PMLU. | *Physical inspections and testing. * AQP signoff *Property Management Plan | *Surface water monitoring records. | *AQP *Environmental monitoring consultants. *Laboratory | Prior to asset transfer. | YCC - E&C Team Leader
6.4 |  | Land | Unauthorised waste disposal and/or waste generation exceeds waste disposal capacity. | PRCP schedule delay Environmental Impact Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Inappropriate waste disposal practices. *Inadequate decommissioning planning and execution. |  |  | EC46 - YCC Environmental Authority Authorises in-pit waste disposal (ERA60) and access to the Council's licenced waste management facility. EC42 - The location of above-ground and below-ground services are detailed in the Site Services Register. EC47 - Implementation of Waste Management Plan and waste tracking. EC48- The existing waste management system is supported by licenced contractors. EC49 - Contractor Management Systems |  |  | 2 | C | 8 (M) | PC35 - Engage an AQP for closure and decommissioning planning. PC37 - Engage an AQP and licenced contractor for decommissioning plant and equipment. |  | 2 | D | 5 (L) |  |  | *AQP signoff to ensure decommissioning activities meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | * Decommissioning Plan *Physical inspections and testing. *As-Built drawings *AQP signoff | *External and Internal Audits *Decommissioning Plan *Survey monitoring and As-Built drawings | * AQP *As-Built drawings | Prior to and during decommissioning. | YCC - E&C Team Leader
6.5 |  | Land/Groundwater | Hazardous materials contamination of land and groundwater | PRCP schedule delay Environmental Impact Increased rework and M&M costs | P - Harm to People E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Hazardous materials not removed. *Contaminated lands not identified and/or remediated. |  |  | EC42 - The location of above-ground and below-ground services are detailed in the Site Services Register. EC44 - The location of hazardous materials maintained in a Hazardous Materials Register - EC49 - Contractor Management Systems |  |  | 2 | C | 8 (M) | PC35 - Engage an AQP for closure and decommissioning planning. PC36-. Engaged an AQP to complete Phase 1 and Phase 2 (if required) land contamination investigations. PC37 - Engage an AQP and licenced contractor for decommissioning plant and equipment. |  | 2 | D | 5 (L) |  |  | *AQP signoff to ensure decommissioning activities meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | * Decommissioning Plan *Physical inspections and testing. *Decommissioning Plan. *As-Built drawings *AQP signoff | *Phase 1 and 2 land contamination investigations reports. *Groundwater quality monitoring program and records. *Survey monitoring. | * AQP *As-Built drawings *Groundwater quality monitoring program and records. | Prior to and during decommissioning. | YCC - E&C Team Leader
6.6 |  | Heritage | Damage to, or loss of, heritage values (European and Aboriginal) | Environmental Impact Impact to Reputation | E - Environmental Impact R - Impact to Reputation | *Physical damage to heritage items. |  |  | EC49 - Contractor Management Systems EC50 - Heritage surveys completed across all existing mining disturbance areas and location of known heritage items maintained in the site Heritage database. EC51 - All new disturbance activities are subject to the Ground Disturbance Permit (GDP) due diligence. |  |  | 2 | C | 8 (M) | PC35 - Engage an AQP for closure and decommissioning planning. PC40- Consultation with heritage organisations and Traditional Owners during closure and decommissioning planning. |  | 2 | D | 5 (L) |  |  | *AQP signoff to ensure decommissioning activities meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Heritage Register. *Stakeholder Engagement * Decommissioning Plan *Physical inspection *AQP signoff | *Survey monitoring. | * AQP *Stakeholder engagement records | Prior to and during decommissioning. | YCC - E&C Team Leader
7.1 |  | Landform | Twelve Mile Creek - The landform does not support the geomorphic function of the proposed Twelve Mile Creek diversion and flood plain. | PRCP schedule delay. Environmental Impact Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *The proposed diversion functional design is inadequate. *The diversion and flood plain is not constructed to design. *Channel and bank erosion. *Insufficient or unsuitable construction material. *Unconsolidated backfill material of C & D Pit causes diversion channel instability. *Unsuccessful rehabilitation establishment. *A Pit landform does not contain a 1:1000 AEP flood level. *Groundwater interaction (into and away from) with mined areas. |  |  | E17 - Care and maintenance of rehabilitation areas informed by the rehabilitation monitoring program (EC10). |  |  | 2 | B | 12 (M) | PRCP DEVELOPMENT 09 - Assess groundwater conditions and to assess impacts from mining activities and future landforms. PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC07 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC22 - Landforms around voids will be established to provide immunity from the 1:1000 AEP flood level. PC41—An AQP-prepared detailed functional creek diversion design is to be developed to meet the required QLD government and industry design standards. |  | 2 | D | 5 (L) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm | *Detailed function creek diversion design *As-Built drawings *RPEQ sign off | *Rehabilitation monitoring program and records. *Diversion Monitoring program and records *Survey monitoring and As-Built drawings | *RPEQ *Environmental monitoring consultants. | For diversion construction | YCC - E&C Team Leader
7.2 |  | Surface water | Twelve Mile Creek – Poor water quality due to hydrological interaction with adjacent mined areas (including backfilled pits C&D). | PRCP schedule delay Environmental Impact Increased rework and M&M costs Impact to Reputation | E - Environmental Impact O - Asset Damage and Other Consequential Losses R - Impact to Reputation | *Landforms not constructed to the approved design. *Highly permeable material in the unmined barrier e.g. alluviums or unconsolidated back fill. *Chemical instability resulting in acid/saline seepage (Geochemical properties of overburden and backfilled material not understood or monitored). *Unauthorised contaminated waste disposal in C & D Pit. |  |  | EC21 - External surface water monitoring program (including annual REMP) to assess downstream water quality, morphology, and aquatic changes. EC47 - Implementation of Waste Management Plan and waste tracking. EC48 - The existing waste management system is supported by licenced contractors. |  |  | 3 | C | 13 (H) | PRCP DEVELOPMENT 08 - Finalise the installation of a groundwater monitoring system to assess current baseline conditions, which will support groundwater impact assessments and model calibrations. PRCP DEVELOPMENT 09 - Assess groundwater conditions and impacts from mining activities and future landforms. PC03 - Align and implement future rehabilitation monitoring programs with the approved PRCP. PC19 - Review and update the groundwater monitoring program to incorporate the new groundwater monitoring network. PC41—An AQP-prepared detailed functional creek diversion design is developed to meet the required QLD government and industry design standards. |  | 3 | D | 9 (M) |  |  | *RPEQ signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Detailed functional creek diversion design *As-Built drawings *RPEQ sign off | *Rehabilitation monitoring program and records. *Diversion Monitoring program and records. *Surface water monitoring program and records. *Groundwater monitoring program and records. *Survey monitoring and As-Built drawings | *RPEQ *Environmental monitoring consultants. *Laboratory | During the construction and annually or more frequent if required for operation of the Creek Diversion. | YCC - E&C Team Leader
See 2.7 |  | Ecology - Flora and Fauna | Twelve Mile Creek—Poor germination percentages and tube stock survival rates (SEE RISK ID 2.7) | [8 empty] | 2 | B | 12 (M) |  |  | 2 | D | 5 (L)
See 2.8 |  | Ecology - Flora and Fauna | Twelve Mile Creek - Sown seed mix and planted tube stock species are not compatible with the approved PMLU. (SEE RISK ID 2.8) | [8 empty] | 2 | A | 16 (H) |  |  | 2 | C | 8 (M)
See 2.9 |  | Ecology - Flora and Fauna | Twelve Mile Creek - Poor long-term resilience/survival of established rehabilitation areas prevents sustainable PMLU outcomes. (SEE RISK ID 2.9) | [8 empty] | 2 | C | 8 (M) |  |  | 2 | C | 8 (M)
7.3 |  | Landform | Reinstated drainage flow lines are unstable. | PRCP schedule delay Environmental Impact Increased rework and M&M costs | E - Environmental Impact O - Asset Damage and Other Consequential Losses | *Flow line channel profile and grade are insufficient for water velocity and flow. *Inadequate geomorphic features e.g. bed grade controls. *Inadequate vegetation establishment/stabilisation of bank and channel. *Secondary erosion head cuts from or at intercepting flowlines. | [5 empty] | 2 | A | 16 (H) | PC01 - Develop a site-specific landform and rehabilitation technical protocol to define operational QA/QC requirements to support the PRC Plan and Schedule implementation. PC08 - Water Management system to be designed by AQP and constructed by experienced persons. PC23 - Reinstate flow lines on natural ground contours around constructed landforms to divert surface water around voids. |  | 2 | D | 5 (L) |  |  | *AQP signoff to ensure designs meet current standards. *To prevent environmental harm. *To ensure the landform is safe. | *Detailed functional drain designs *As-Built drawings *AQP sign off | *Rehabilitation monitoring program and records. *Surface water monitoring program and records. *ESCP monitoring program and records. *Survey monitoring and As-Built drawings | *AQP *Environmental monitoring consultants. *Laboratory | During the construction and annually or more frequently if required for the operation of the drains. | YCC - E&C Team Leader
Spell checker

## 3 Action Plan_Attend_NC Issues
Title: | Yarrabee Coal Company Pty Ltd PRCP Risk Assessment
Date of WRAC: | 2024-03-07
ACTION PLAN: Please complete for all extreme and high risks. (When allocating accountabilities ensure person is competent for the allocated role/task)
Action |  |  |  |  | Who | When
PARTICIPANTS
Name | Company | Organisational Role | Process Role (Facilitator/Team Member) | Experience (Yrs) | Consensus Yes/No | Signature
Jamie Lees | ESG Consulting | Facilitator | Facilitator | 21 | Yes o No o
Megan Dawson | Yancoal | Superintendent - Approvals | Team member | 17 | Yes o No o
David Drew | Minserve | Mining Engineer | Team member | 22 | Yes o No o
Lee James | YCC | Mining Manager | Team member | 27 | Yes o No o
Kirsten Gollogly | Resource Strategies | Approvals Consultant | Team member | 24 | Yes o No o
Phoebe French | Resource Strategies | Approvals Consultant | Team member | 3 | Yes o No o
Jeff Hansen | Yancoal | QLD Technical Manager | Team member | 15 | Yes o No o
Sloane Hobbs | YCC | Snr HST Advisor | Team member | 3 | Yes o No o
Josh Peters | Resource Strategies | Approvals Consultant | Team member | 21 | Yes o No o
Troy King | YCC | CHPP Superintendent | Team member | Not specified | Yes o No o
Michael Moore | Yancoal | Manager - Approvals | Team member | 35 | Yes o No o
Michael Priestly | YCC | SSE/Operations Manager | Team member | 30 | Yes o No o
Charmain Grouch | YCC | Commercial Manager | Team member | 10 | Yes o No o
Godfrey Banda | YCC | Technical Services Manager | Team member | 15 | Yes o No o
Jazmin Byles | YCC | Senior Process Engineer | Team member | 10 | Yes o No o
Andrew Lau | YCC | YCC Mine Closure Manager | Team member | 20 | Yes o No o
NON-CONSENSUS MATTERS
Name | Reason for Non-Consensus |  |  |  | Date | Signature
High Risks require Department Head sign off and Extreme requires SSE Sign off as per the Yancoal Risk Matrix: Majority consensus reached by those persons participating in this risk assessment, any non-consensus has been noted at the back of this form.
Department Head Approval: |  |  |  | SSE Approval:
Name: |  |  |  | Name:
Signature: |  |  |  | Signature:
Date: |  |  |  | Date:
Spell checker

## 4 Risk Matrix
YANCOAL RISK MATRIX REFERENCE SHEET
Loss Type |  | Consequence
|  | 1 - Insignificant | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Catastrophic
(P) Harm to People |  | Slight injury or health effects – | Minor injury or health effects – | Serious bodily injury or health | Single fatality | Multiple fatalities
|  | report only (RO) or first aid injury (FAI) | medical treatment injury (MTI) or restricted work injury (RWI) | effects –lost time injury (LTI)
(E) Environmental Impact |  | Environmental nuisance – trivial or negligible, short term impact to area of low significance, minimal or no physical remediation required No regulation. Cost < $1K | Minor environmental harm – short term impact to area of limited local significance, limited physical remediation Reportable Breach /Minor Non-Compliance, potential warning notice, other notices (infringement / prosecution) unlikely. Costs $1K - $10K | Serious environmental harm – medium term impact to area of local conservation value, medium term physical remediation, actual community health impacts or significance or pollution or contamination Infringement Notice but Prosecution unlikely Costs $10k - $100k | Major environmental harm – long term reversible impacts to area of regional conservation significance, health statistics in community alter as a result of this incident or pollution or contamination Prosecution Costs $100k - $1M | Extreme environmental harm – irreversible impacts on environmental values of extreme & widespread areas, or those of national conservation significance, community fatalities or pollution or contamination Prosecution, License revoked Costs > $1M
(O) Asset Damage and Other Consequential Losses |  | Slight damage | Minor damage | Local damage | Major damage | Extreme damage
|  | < $1M or < 1 day disruption to operation | $1M - $5M. Or < 1 week disruption to operation | $5M - $20M or < 1 month disruption to operation | $20M -$100M or < 6 Months Partial loss of operation | > $100M or > 6 months substantial or total loss of operation
(R) Impact on Reputation |  | Slight impact – Public awareness may exist but no public concern Isolated compliance failure – no brand damage | Limited impact – Some local public concern Intervention of regulating authority – minimal brand damage | Considerable impact - Regional public concern Major compliance failure involving fines – medium brand damage | National impact – National public concern Temporary withdrawal of license to operate – significant brand damage | International impact - International public attention Loss of shareholder confidence – irreparable brand damage
Likelihood | Likelihood Guide | Level of Risk
A (Almost Certain) | Likely that the unwanted event could occur several times per year at this location | 11 (Moderate) | 16 (High) | 20 (High) | 23 (Extreme) | 25 (Extreme)
B (Likely) | Likely that the unwanted event could occur several times per year in the Australian mining industry; or could happen annually | 7 (Moderate) | 12 (Moderate) | 17 (High) | 21 (Extreme) | 24 (Extreme)
C (Possible) | The unwanted event could well have occurred in the Australian mining industry at some time in the past 10 years | 4 (Low) | 8 (Moderate) | 13 (High) | 18 (High) | 22 (Extreme)
D (Unlikely) | The unwanted event has happened in the Australian mining industry at some time; or could happen in 50 years | 2 (Low) | 5 (Low) | 9 (Moderate) | 14 (High) | 19 (High)
E (Rare) | The unwanted event has never been known to occur in the Australian mining industry; or is highly unlikely that it could ever occur | 1 (Low) | 3 (Low) | 6 (Moderate) | 10 (Moderate) | 15 (High)
Risk Rating | Risk Level | Guidelines for Risk Matrix
21 to 25 | Extreme | Stop operations or don’t proceed with activity (Make Safe). Do not proceed with activity until reviewed and authorised by SSE.
13 to 20 | High | Imperative to eliminate or reduce risk by introduction of controls. Do not proceed with activity until reviewed and authorised by Department Head.
6 to 12 | Moderate | Corrective action to be determined. Do not proceed without authorisation from Supervisor.
1 to5 | Low | Safe to continue activity once risk is minimised.

## 5 Core Hazard Critical Controls
YANCOAL CORE HAZARDS AND CRITICAL HAZARDS REFERENCE SHEET
CORE HAZARD | CRITICAL CONTROL
Airborne Dust and Contaminants | AC-CC-3 Blast exclusion zones established using condition-based on determination of fume corridor
Airborne Dust and Contaminants | AD-CC-1 Pressurised cabins are operated and maintained to minimise workers exposure to dust
Airborne Dust and Contaminants | AD-CC-4 Routine medical testings (incl. chest x-ray) and actioning of abnormalities
Confined Space | CS-CC-1 Barriers (inlc. Signage) installed to restrict direct access. Barrier type dependent on the confined space and identified level of risk
Confined Space | CS-CC-2 Confined space atmosphere control, monitoring and response
Confined Space | CS-CC-3 Identify and isolate equipment and area that could impact the confined space, including upstream and downstream processes
Confined Space | CS-CC-4 Confined space worker is safely removed from confined space if required, following site rescue plan.
Explosives | EX-CC-1 Controlled recovery of misfire conducted under supervision of shotfirer/qualified person
Explosives | EX-CC-2 Identification of hot and/or reactive ground and development & compliance with loading rules to suit site conditions
Explosives | EX-CC-3 Implement and enforce exclusion zones based on potential exposure to explosive energies.
Exposure to Energised Plant and Equipment | EP-CC-1 Equipment maintained to design requirements
Exposure to Energised Plant and Equipment | EP-CC-3 Workers to apply locks or tags to dedicated and marked isolation points to isolate mechanical, electrical and stored energy
Exposure to Energised Plant and Equipment | EP-CC-4 To verify that equipment is compliant with site standards prior to use
Exposure to Energised Plant and Equipment | EP-CC-5 For energised plant tasks, workers correctly identify hazards and follow energised plant procedure
Fire and Explosion | FE-CC-1 Fire systems designed, installed and maintained to required standards
Fire and Explosion | FE-CC-2 Emergency response capability, including controlled withdrawal
Fire and Explosion | FE-CC-3 Monitor and respond to gas monitoring/ alarms to maintain gas limits below explosive range
Ground or Strata | GF-CC-1 Development of mine plans in accordance with geotehcnical guidelines and condition
Ground or Strata | GF-CC-2 Construction to plan
Ground or Strata | GF-CC-3 Monitoring for geotechnical hazards on excavated/constructed walls, and slopes and responding to abnormalities
Ground or Strata | GF-CC-4 Stand-off zones implemented
Ground or Strata | GF-CC-5 Redirection of water away from walls and dump faces
High Voltage | HV-CC-1 Use of remote switching of HV switchgear
High Voltage | HV-CC-2 Maintain minimum approach distances for any HV live exposed conductors
High Voltage | HV-CC-3 Worker to verify isolation and prove de-energised by using non-contact tester and discharging circuit immediately before touching any exposed HV conductor
Inrush, Inundation and Storage Dams | II-CC-1 Water level monitoring, pumping, controlled dewatering and modifying water flow/path/storage
Inrush, Inundation and Storage Dams | II-CC-2 Engineered fit for purpose, designed and constructed water control structures
Inrush, Inundation and Storage Dams | II-CC-3 Engineered fit for purpose, designed and constructed water control structures
Inrush, Inundation and Storage Dams | II-CC-4 Inspections for unexpected water/ gas accumulations/ changes and corrective actions
Lifting, Cranage and Suspended Loads | LC-CC-1 No personnel to go beneath loads suspended by a crane/ lifting equipment (incl. loading/unloading trucks) or load crush zone (consider pendulum effect) and barricade where appropriate
Lifting, Cranage and Suspended Loads | LC-CC-2 Only use lifting cranes, winches, jibs etc. that have been approved for use on site and had pre-start checks for integrity of lifting components (inlc. Hooks, sheaves, ropes, pawls, outriggers etc.)
Lifting, Cranage and Suspended Loads | LC-CC-3 Only use lifting gear checked for integrity, and has correct WLL and specific labelling for the task (incl. slings, chains, shackles, spreader bars, grabs etc.)
Stockpile and Reclaim Tunnel | SP-CC-1 No loaders or dozers to work near shear faces greater in height than the equipment height
Stockpile and Reclaim Tunnel | SP-CC-2 Equipment operating on stockpiles to be fitted with appropriate functional safety equipment (incl. ROPs/FOPs, self-rescuer, etc.)
Stockpile and Reclaim Tunnel | SP-CC-3 Only authorised personnel permitted to access stockpiles
Structures and Fixed Plant | FS-CC-1 Structural integrity, maintenance and design
Structures and Fixed Plant | FS-CC-2 Commissioning of new and/or modified structures and buildings
Structures and Fixed Plant | FS-CC-3 Load within design specifications of the structure
Tyres | T-CC-1 Scheduled NDT testing based on site data for rims
Tyres | T-CC-2 No entry zone during inflation and deflation >10psi based on blast line of fire
Tyres | T-CC-3 Always deflate to specified pressure prior to dismounting and/or disassembling
Tyres | T-CC-4 Only use qualified and competent people to perform tyre fitting and repair work
Tyres | T-CC-5 Selection of engineered fall-back protection arms on tyre handlers
Vehicle Interactions | VI-CC-1 Separation of two-way traffic with centre dividers on corners and when road width is less than 3.5 x equipment width
Vehicle Interactions | VI-CC-2 Workers to stop equipment when visibility is reduced below threshold or road conditions are deemed not safe to continue operating
Vehicle Interactions | VI-CC-3 Only operate equipment with fully functioning brakes and steering
Vehicle Interactions | VI-CC-4 Workers will park in designated parking areas and/or park so that vehicle is fundamentally stable.
Vehicle Interactions | VI-CC-5 Workers to obtain positive communications before entering an active work zones
Vehicle Interactions | VI-CC-6 Workers will comply with intersection rules/signage (including using horns on UG blind corners)
Vehicle Interactions | VI-CC-7 Railing, bunds and bollards to prevent equipment going over edge or contacting other equipment/ infrastructure
Vehicle Interactions | VI-CC-8 Adequate first aid response and rescue response
Working at Heights | WH-CC-1 When completing work outside of permanent walkways, personnel to select work at height equipment that is fit for intended purpose
Working at Heights | WH-CC-2 When no hard barrier is available, suitable fall restraint system installed to prevent unprotected workers going over exposed edges
Working at Heights | WH-CC-3 Temporary barrier installed to prevent access to area until permanent floor/barrier is reinstalled
Working at Heights | WH-CC-4 Workers to comply with drop/exclusion zones and signage when work is taking place at heights

## Lists (hidden)
1 | A | Elim | 1 (L) |  |  |  | 1 | 2 | 3 | 4 | 5
2 | B | Sub | 2 (L) |  |  | A | 11 (M) | 16 (H) | 20 (H) | 23 (E) | 25 (E)
3 | C | Isol | 3 (L) |  |  | B | 7 (M) | 12 (M) | 17 (H) | 21 (E) | 24 (E)
4 | D | Eng | 4 (L) | Mining |  | C | 4 (L) | 8 (M) | 13 (H) | 18 (H) | 22 (E)
5 | E | Adm | 5 (L) | Maintenance |  | D | 2 (L) | 5 (L) | 9 (M) | 14 (H) | 19 (H)
|  | PPE | 6 (M) | CHPP |  | E | 1 (L) | 3 (L) | 6 (M) | 10 (M) | 15 (H)
|  | Post | 7 (M) | Technical Services
|  |  | 8 (M) | Exploration
|  |  | 9 (M) | Projects |  |  | Insignificant
Prev |  |  | 10 (M) | HST |  |  | Minor
Mitig |  |  | 11 (M) | HR |  |  | Moderate
|  |  | 12 (M) | Commercial |  |  | Major
Yes |  |  | 13 (H) |  |  |  | Catastrophic
No |  |  | 14 (H)
15 (H)
16 (H)
17 (H)
|  |  | 18 (H) | Gravity | naturally occurring energy which causes things, or materials, or people to fall or move downward. Includes high/low wall, stockpiles (slumps), liquids (pipes, tanks/containers, dams), elevated equipment (conveyors, cranes, truck trays) , and people working at heights.
|  |  | 19 (H) | Electrical | includes all types and voltages of electricity from HV to batteries to induction, and static electricity. Includes lightning.
|  |  | 20 (H) | Mechanical | includes mobile equipment as well as moving parts on stationary equipment.
|  |  | 21 ( E ) | Chemical | energy in the form of gases, liquids, solids of which some are natural eg. water, methane, coal, whilst others are introduced eg fuels, acetylene, solvents. Acids and Alkilines. Remember some chemicals react violently if mixed together
|  |  | 22 ( E ) | Pressure | air, water, pneumatics, springs, gases, oil and grease are all possible stores of pressure energy-including accumulators.
|  |  | 23 ( E ) | Noise/Vibration | noise is also a pressure energy but as the most significant compensated health issue is considered separately.
|  |  | 24 ( E ) | Thermal | hot or cold conditions, surfaces or substances.
|  |  | 25 ( E ) | Radiation | in the form of sun light or ionising and non-ionising radiation eg. density gauges, downhole bore loggers and X-ray's.
|  |  |  | Body Mechanics | includes the human body’s own energy to move which includes lifting, pushing, pulling, climbing, positioning.
|  |  |  | Biological | covers the many sources of energy in other forms of life from wildlife to viruses or bacteria.
|  |  |  | Atmosphere | toxic or flammable gases, low or elevated oxygen levels,
|  |  |  | Weather | rain and flooding, strong winds and lightning.
|  |  |  | Explosive | unplanned detonation, catostrophic failure of storage vessels
GF-CC-1 – Mine plans developed within geotechnical parameters
GF-CC-2– Construction to plan
GF-CC-3 – Monitoring for geotechnical hazards
GF-CC-4 – Stand-off Zones
GF-CC-5 – Water directed away from wall and dump faces
VI-CC-1 –Separation of Two Way Traffic with Centre Dividers
VI-CC-2 – Stop Equipment when Road Conditions no Longer Safe
VI-CC-3 – Functional Brakes and Steering
VI-CC-4 – Fundamentally Stable Parking
VI-CC-5 – Positive Communications
VI-CC-6 – Compliance with Intersection Rules and Signage
VI-CC-7 – Railings, Bunds and Bollards
VI-CC-8 – Adequate First Aid and Rescue Response
CC-1 – Barriers (incl. signage) installed to restrict direct access. Barrier type dependent on the confined space and identified level of risk.
CC-2 – Confined space atmosphere control, monitoring and response.
CC-3 – Identify and isolate equipment and area that could impact the confined space, including upstream and/or downstream processes.
CC-4 – Person can be removed from confined space as per site rescue plan
CC-1 – When completing work outside of permanent walkways, personnel to select work at heights equipment that is fit for intended purpose
CC-2 – Fall arrest or restraint equipment utilised to prevent falls when no hard barrier is present
CC-3 – Temporary barriers installed to prevent access to area until permanent floor or barrier is reinstalled
CC-4 – Workers comply with drop zones when there is a risk of falling objects
CC-1 – Equipment is maintained to original design requirements
CC-3 – Workers to apply locks/tags to dedicated isolation points to isolate sources of energy
CC-4 – All equipment is introduced to site
CC-5 – Workers correctly identify hazards and follow energised plant procedure
T-CC-1 – Scheduled non-destructive testing (NDT) based on site data for rims.
T-CC-2 – No-entry zones during inflation and deflation >10 psi based on blast ‘line of fire’.
T-CC-3 – Always deflate to specified pressure prior to dismounting and/or disassembling.
T-CC-4 – Only use qualified and competent people to perform tyre fitting and repair work.
SP-CC-1 – Stockpile equipment not to work near shear faces greater in height than equipment height.
SP-CC-2 – Equipment operating on stockpiles to be fitted with appropriate functional safety equipment.
SP-CC-3 – Only authorised personnel to access stockpiles.
SP-CC-4 – Dozer operators not to enter within zone of influence of operating feeder.
AD-CC-1 – Pressurised cabins are operated and maintained to minimise worker exposure to dust (Surface only)
AD-CC-4 – Routine medical testing (incl. chest x-rays) and actioning of abnormalities
EX-CC-1 – Controlled recovery of misfire conducted under supervision of shotfirer/qualified person
EX-CC-2 – Identification of hot/reactive ground and development & compliance with loading rules
EX-CC-3 – Implement and enforce exclusion zones based on potential exposure to explosive energies
HV-CC-1 – Use of remote switching of HV switchgear
HV-CC-2 – Maintain minimum approach distances for any HV live exposed conductors
HV-CC-3 – Worker to verify isolation and prove de-energised by using non-contact tester and discharging circuit immediately before touching any exposed HV conductor
FE-CC-1 – Fire systems designed, installed and maintained to required standards
FE-CC-2 – Emergency response capability
FE-CC-3 – Monitor and respond to gas monitoring alarms
LC-CC-1 – No personnel to go beneath loads suspended by cranage/ lifting equipment or load crush zones, and barricade where appropriate
LC-CC-2 – Only use lifting cranes, winches, jibs etc. that have been approved for use on site and have undergone pre-start checks for the integrity of lifting components
LC-CC-3 – Only use lifting gear checked for integrity, and has correct WLL and specific labelling for the task
II-CC-1 – Water level monitoring, pumping, controlled dewatering and modifying water flow/path/storage
II-CC-2 – Engineered fit for purpose, designed and constructed control structures
II-CC-7 – Maintain standoff distances and/or barrier between workings in accordance with all available data