## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | In-pit and Out-of-pit Waste Emplacement (Slopes <12.5%)
Total rehabilitation area size (ha) |  |  |  | 944
Commencement of first milestone: RM5 |  |  |  | 2025-12-10
PMLU |  |  |  | Grazing
Date area is available | 2025-12-10 | 2027-12-10 | 2029-12-10 | 2031-12-10 | 2033-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10 | 2041-12-10 | 2043-12-10 | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10 | 2055-12-10 | 2057-12-10
Cumulative area available (ha) | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 480 | 624 | 658 | 701 | 798.94 | 837.55 | 886.86 | 893.7 | 909.13 | 944
Milestone completed by | 2027-12-10 | 2029-12-10 | 2031-12-10 | 2033-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10 | 2041-12-10 | 2043-12-10 | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10 | 2055-12-10 | 2057-12-10 | 2059-12-10 | 2061-12-10 | 2063-12-10 | 2065-12-10 | 2067-12-10 | 2069-12-10 | 2071-12-10 | 2073-12-10
Milestone Reference | 2027-12-10: Cumulative area achieved (ha)
RM5 | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 480 | 624 | 658 | 701 | 798.94 | 837.55 | 886.86 | 893.7 | 909.13 | 944
RM6 |  | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 480 | 624 | 658 | 701 | 798.94 | 837.55 | 886.86 | 893.7 | 909.13 | 944
RM7 |  | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 780 | 624 | 658 | 701 | 799 | 838 | 887 | 894 | 909 | 944
RM8 |  |  |  |  | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 480 | 624 | 658 | 701 | 798.94 | 837.55 | 886.86 | 894 | 909.13 | 944
RM9 | [7 empty] | 73 | 114 | 149 | 182 | 194 | 260 | 349 | 480 | 624 | 658 | 701 | 798.94 | 837.55 | 886.86 | 893.7 | 909.13 | 944
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2027-12-10 to 2045-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2027-12-10 to 2045-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2027-12-10 to 2045-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2027-12-10 to 2045-12-10

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | In-pit and Out-of-Pit Waste Emplacement (Slopes 0 to <27%)
Total rehabilitation area size (ha) |  |  |  | 1264
Commencement of first milestone: RM5 |  |  |  | 2024-12-10
PMLU |  |  |  | Native Vegetation
Date area is available | 2024-12-10 | 2030-12-10 | 2032-12-10 | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10 | 2056-12-10
Cumulative area available (ha) | 56 | 97 | 148 | 225 | 304 | 338 | 357 | 467 | 580 | 709 | 813 | 911 | 1099 | 1213 | 1264
Milestone completed by | 2026-12-10 | 2032-12-10 | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10 | 2056-12-10 | 2058-12-10 | 2060-12-10 | 2062-12-10 | 2064-12-10 | 2066-12-10 | 2068-12-10 | 2070-12-10 | 2072-12-10 | 2074-12-10 | 2076-12-10 | 2078-12-10 | 2080-12-10 | 2082-12-10
Milestone Reference | 2026-12-10: Cumulative area achieved (ha)
RM5 | 2026-12-10: 56; 2032-12-10: 97; 2034-12-10: 148; 2036-12-10: 225; 2038-12-10: 304; 2040-12-10: 338; 2042-12-10: 357; 2044-12-10: 467; 2046-12-10: 580; 2048-12-10: 709; 2050-12-10: 813; 2052-12-10: 911; 2054-12-10: 1099; 2056-12-10: 1213; 2058-12-10: 1264
RM6 | 2032-12-10: 56; 2034-12-10: 97; 2036-12-10: 148; 2038-12-10: 225; 2040-12-10: 304; 2042-12-10: 338; 2044-12-10: 357; 2046-12-10: 467; 2048-12-10: 580; 2050-12-10: 709; 2052-12-10: 813; 2054-12-10: 911; 2056-12-10: 1099; 2058-12-10: 1213; 2060-12-10: 1264
RM7 | 2032-12-10: 56; 2034-12-10: 97; 2036-12-10: 148; 2038-12-10: 225; 2040-12-10: 304; 2042-12-10: 338; 2044-12-10: 357; 2046-12-10: 467; 2048-12-10: 580; 2050-12-10: 709; 2052-12-10: 813; 2054-12-10: 911; 2056-12-10: 1099; 2058-12-10: 1213; 2060-12-10: 1264
RM10 | 2038-12-10: 56; 2040-12-10: 97; 2042-12-10: 148; 2044-12-10: 225; 2046-12-10: 304; 2048-12-10: 338; 2050-12-10: 357; 2052-12-10: 467; 2054-12-10: 580; 2056-12-10: 709; 2058-12-10: 813; 2060-12-10: 911; 2062-12-10: 1099; 2064-12-10: 1213; 2066-12-10: 1264
RM11 | 2054-12-10: 56; 2056-12-10: 97; 2058-12-10: 148; 2060-12-10: 225; 2062-12-10: 304; 2064-12-10: 338; 2066-12-10: 357; 2068-12-10: 467; 2070-12-10: 580; 2072-12-10: 709; 2074-12-10: 813; 2076-12-10: 911; 2078-12-10: 1099; 2080-12-10: 1213; 2082-12-10: 1264
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2026-12-10 to 2048-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2026-12-10 to 2048-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2026-12-10 to 2048-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2026-12-10 to 2048-12-10

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Twelve Mile Creek Diversion
Total rehabilitation area size (ha) |  |  |  | 53
Commencement of first milestone: RM5 |  |  |  | 2035-12-10
PMLU |  |  |  | Native Vegetation (Riparian)
Date area is available | 2035-12-10
Cumulative area available (ha) | 53
Milestone completed by | 2037-12-10 | 2038-12-10 | 2039-12-10 | 2044-12-10 | 2059-12-10
Milestone Reference | Cumulative area achieved (ha)
RM5 | 53
RM6 |  | 53
RM7 |  |  | 53
RM12 |  |  |  | 53
RM13 |  |  |  |  | 53
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Water Management Infrastructure (Water Storage)
Total rehabilitation area size (ha) |  |  |  | 18
Commencement of first milestone: RM1 |  |  |  | 2056-12-10
PMLU |  |  |  | Water Storages
Date area is available | 2056-12-10
Cumulative area available (ha) | 18
Milestone completed by | 2058-12-10 | 2060-12-10 | 2062-12-10 | 2063-12-10 | 2064-12-10 | 2066-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 18
RM2 |  | 18
RM5 |  |  | 18
RM6 |  |  |  | 18
RM7 |  |  |  |  | 18
RM14 | [5 empty] | 18
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | DE-Pit TSF
Total rehabilitation area size (ha) |  |  |  | 2
Commencement of first milestone: RM1 |  |  |  | 2037-12-10
PMLU |  |  |  | Native Vegetation
Date area is available | 2037-12-10
Cumulative area available (ha) | 2
Milestone completed by | 2039-12-10 | 2041-12-10 | 2046-12-10 | 2048-12-10 | 2049-12-10 | 2050-12-20 | 2055-12-20 | 2070-12-20
Milestone Reference | 2039-12-10: Cumulative area achieved (ha)
RM1 | 2039-12-10: 2
RM2 | 2041-12-10: 2
RM3 | 2046-12-10: 2
RM5 | 2048-12-10: 2
RM6 | 2049-12-10: 2
RM7 | 2050-12-20: 2
RM10 | 2055-12-20: 2
RM11 | 2070-12-20: 2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | DE-Pit TSF and DOM1 TSF
Total rehabilitation area size (ha) |  |  |  | 59
Commencement of first milestone: RM1 |  |  |  | 2037-12-10
PMLU |  |  |  | Grazing
Date area is available | 2037-12-10 | 2039-12-10 | 2041-12-10 | 2046-12-10 | 2048-12-10 | 2049-12-10 | 2053-12-10
Cumulative area available (ha) | 7 | 7 | 7 | 7 | 7 | 7 | 59
Milestone completed by | 2039-12-10 | 2041-12-10 | 2046-12-10 | 2048-12-10 | 2049-12-10 | 2050-12-20 | 2055-12-10 | 2057-12-10 | 2060-12-10 | 2062-12-10 | 2064-12-10 | 2065-12-10 | 2066-12-10 | 2071-12-10 | 2076-12-10
Milestone Reference | 2039-12-10: Cumulative area achieved (ha)
RM1 | 2039-12-10: 7; 2041-12-10: 7; 2046-12-10: 7; 2048-12-10: 7; 2049-12-10: 7; 2050-12-20: 7; 2055-12-10: 59
RM2 | 2041-12-10: 7; 2046-12-10: 7; 2048-12-10: 7; 2049-12-10: 7; 2050-12-20: 7; 2055-12-10: 7; 2057-12-10: 59
RM3 | 2046-12-10: 7; 2048-12-10: 7; 2049-12-10: 7; 2050-12-20: 7; 2055-12-10: 7; 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 59
RM5 | 2048-12-10: 7; 2049-12-10: 7; 2050-12-20: 7; 2055-12-10: 7; 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 7; 2064-12-10: 59
RM6 | 2049-12-10: 7; 2050-12-20: 7; 2055-12-10: 7; 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 7; 2064-12-10: 7; 2065-12-10: 59
RM7 | 2050-12-20: 7; 2055-12-10: 7; 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 7; 2064-12-10: 7; 2065-12-10: 7; 2066-12-10: 59
RM8 | 2055-12-10: 7; 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 7; 2064-12-10: 7; 2065-12-10: 7; 2066-12-10: 7; 2071-12-10: 59
RM9 | 2057-12-10: 7; 2060-12-10: 7; 2062-12-10: 7; 2064-12-10: 7; 2065-12-10: 7; 2066-12-10: 7; 2071-12-10: 7; 2076-12-10: 59
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2039-12-10 to 2062-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2039-12-10 to 2062-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2039-12-10 to 2062-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2039-12-10 to 2062-12-10

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Infrastructure Areas (Retained Infrastructure)
Total rehabilitation area size (ha) |  |  |  | 12
Commencement of first milestone: RM1 |  |  |  | 2057-12-10
PMLU |  |  |  | Retained Infrastructure
Date area is available | 2057-12-10
Cumulative area available (ha) | 12
Milestone completed by | 2059-12-10 | 2061-12-10 | 2063-12-10 | 2064-12-10 | 2068-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 12
RM2 |  | 12
RM5 |  |  | 12
RM6 |  |  |  | 12
RM15 |  |  |  |  | 12
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Infrastructure Areas (Grazing)
Total rehabilitation area size (ha) |  |  |  | 292
Commencement of first milestone: RM1 |  |  |  | 2043-12-10
PMLU |  |  |  | Grazing
Date area is available | 2043-12-10 | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10 | 2055-12-10
Cumulative area available (ha) | 9.82 | 44.5 | 91.73 | 106 | 117.04 | 134.6 | 292
Milestone completed by | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10 | 2055-12-10 | 2057-12-10 | 2059-12-10 | 2061-12-10 | 2063-12-10 | 2065-12-10 | 2067-12-10 | 2069-12-10 | 2071-12-10 | 2073-12-10 | 2075-12-10
Milestone Reference | 2045-12-10: Cumulative area achieved (ha)
RM1 | 2045-12-10: 10; 2047-12-10: 45; 2049-12-10: 92; 2051-12-10: 106; 2053-12-10: 117; 2055-12-10: 135; 2057-12-10: 292
RM2 | 2047-12-10: 10; 2049-12-10: 45; 2051-12-10: 92; 2053-12-10: 106; 2055-12-10: 117; 2057-12-10: 135; 2059-12-10: 292
RM5 | 2049-12-10: 10; 2051-12-10: 45; 2053-12-10: 92; 2055-12-10: 106; 2057-12-10: 117; 2059-12-10: 135; 2061-12-10: 292
RM6 | 2051-12-10: 10; 2053-12-10: 45; 2055-12-10: 92; 2057-12-10: 106; 2059-12-10: 117; 2061-12-10: 135; 2063-12-10: 292
RM7 | 2051-12-10: 10; 2053-12-10: 45; 2055-12-10: 92; 2057-12-10: 106; 2059-12-10: 117; 2061-12-10: 135; 2063-12-10: 292
RM8 | 2057-12-10: 10; 2059-12-10: 45; 2061-12-10: 92; 2063-12-10: 106; 2065-12-10: 117; 2067-12-10: 135; 2069-12-10: 292
RM9 | 2063-12-10: 10; 2065-12-10: 45; 2067-12-10: 92; 2069-12-10: 106; 2071-12-10: 117; 2073-12-10: 135; 2075-12-10: 292
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2045-12-10 to 2063-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2045-12-10 to 2063-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2045-12-10 to 2063-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2045-12-10 to 2063-12-10

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Infrastructure Areas (Native Vegetation)
Total rehabilitation area size (ha) |  |  |  | 50
Commencement of first milestone: RM1 |  |  |  | 2042-12-10
PMLU |  |  |  | Native Vegetation
Date area is available | 2042-12-10 | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10
Cumulative area available (ha) | 1 | 6 | 16 | 18 | 37 | 46 | 50
Milestone completed by | 2044-12-10 | 2046-12-10 | 2048-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10 | 2056-12-10 | 2058-12-10 | 2060-12-10 | 2062-12-10 | 2064-12-10 | 2070-12-10 | 2072-12-10 | 2074-12-10 | 2076-12-10 | 2078-12-10 | 2080-12-10 | 2082-12-10
Milestone Reference | 2044-12-10: Cumulative area achieved (ha)
RM1 | 2044-12-10: 1; 2046-12-10: 6; 2048-12-10: 16; 2050-12-10: 18; 2052-12-10: 37; 2054-12-10: 46; 2056-12-10: 50
RM2 | 2046-12-10: 1; 2048-12-10: 6; 2050-12-10: 16; 2052-12-10: 18; 2054-12-10: 37; 2056-12-10: 46; 2058-12-10: 50
RM5 | 2048-12-10: 1; 2050-12-10: 6; 2052-12-10: 16; 2054-12-10: 18; 2056-12-10: 37; 2058-12-10: 46; 2060-12-10: 50
RM6 | 2050-12-10: 1; 2052-12-10: 6; 2054-12-10: 16; 2056-12-10: 18; 2058-12-10: 37; 2060-12-10: 46; 2062-12-10: 50
RM7 | 2050-12-10: 1; 2052-12-10: 6; 2054-12-10: 16; 2056-12-10: 18; 2058-12-10: 37; 2060-12-10: 46; 2062-12-10: 50
RM10 | 2056-12-10: 1; 2058-12-10: 6; 2060-12-10: 16; 2062-12-10: 18; 2064-12-10: 46; 2070-12-10: 50
RM11 | 2072-12-10: 1; 2074-12-10: 6; 2076-12-10: 16; 2078-12-10: 18; 2080-12-10: 46; 2082-12-10: 50
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2044-12-10 to 2062-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2044-12-10 to 2062-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2044-12-10 to 2062-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2044-12-10 to 2062-12-10

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA10
Relevant activities |  |  | Existing Rehabilitation (Native Vegetation)
Total rehabilitation area size (ha) |  |  | 168
Commencement of first milestone: RM10 |  |  | 2024-12-10
PMLU |  |  | Native Vegetation
Date area is available | 2024-12-10
Cumulative area available (ha) | 168
Milestone completed by | 2029-12-10 | 2044-12-10
Milestone Reference | Cumulative area achieved (ha)
RM10 | 168
RM11 |  | 168
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA11
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA11
Relevant activities |  |  |  | Existing Rehabilitation to be re-disturbed (Native Vegetation)
Total rehabilitation area size (ha) |  |  |  | 149
Commencement of first milestone: RM4 |  |  |  | 2031-12-10
PMLU |  |  |  | Native Vegetation
Date area is available | 2031-12-10 | 2033-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10 | 2041-12-10 | 2043-12-10 | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10
Cumulative area available (ha) | 32 | 35 | 35 | 35 | 40 | 40 | 127 | 127 | 127 | 149 | 149 | 149
Milestone completed by | 2033-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10 | 2041-12-10 | 2043-12-10 | 2045-12-10 | 2047-12-10 | 2049-12-10 | 2051-12-10 | 2053-12-10 | 2055-12-10 | 2057-12-10 | 2059-12-10 | 2061-12-10 | 2063-12-10 | 2065-12-10 | 2067-12-10 | 2069-12-10 | 2071-12-10 | 2073-12-10 | 2075-12-10 | 2077-12-10 | 2079-12-10 | 2081-12-10
Milestone Reference | 2033-12-10: Cumulative area achieved (ha)
RM4 | 2033-12-10: 32; 2035-12-10: 35; 2037-12-10: 35; 2039-12-10: 35; 2041-12-10: 40; 2043-12-10: 40; 2045-12-10: 127; 2047-12-10: 127; 2049-12-10: 127; 2051-12-10: 149; 2053-12-10: 149; 2055-12-10: 149
RM5 | 2035-12-10: 32; 2037-12-10: 35; 2039-12-10: 35; 2041-12-10: 35; 2043-12-10: 40; 2045-12-10: 40; 2047-12-10: 127; 2049-12-10: 127; 2051-12-10: 127; 2053-12-10: 149; 2055-12-10: 149; 2057-12-10: 149
RM6 | 2037-12-10: 32; 2039-12-10: 35; 2041-12-10: 35; 2043-12-10: 35; 2045-12-10: 40; 2047-12-10: 40; 2049-12-10: 127; 2051-12-10: 127; 2053-12-10: 127; 2055-12-10: 149; 2057-12-10: 149; 2059-12-10: 149
RM7 | 2037-12-10: 32; 2039-12-10: 35; 2041-12-10: 35; 2043-12-10: 35; 2045-12-10: 40; 2047-12-10: 40; 2049-12-10: 127; 2051-12-10: 127; 2053-12-10: 127; 2055-12-10: 149; 2057-12-10: 149; 2059-12-10: 149
RM10 | 2043-12-10: 32; 2045-12-10: 35; 2047-12-10: 35; 2049-12-10: 35; 2051-12-10: 40; 2053-12-10: 40; 2055-12-10: 127; 2057-12-10: 127; 2059-12-10: 127; 2061-12-10: 149; 2063-12-10: 149; 2065-12-10: 149
RM11 | 2059-12-10: 32; 2061-12-10: 35; 2063-12-10: 35; 2065-12-10: 35; 2067-12-10: 40; 2069-12-10: 40; 2071-12-10: 127; 2073-12-10: 127; 2075-12-10: 127; 2077-12-10: 149; 2079-12-10: 149; 2081-12-10: 149
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2033-12-10 to 2051-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2033-12-10 to 2051-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2033-12-10 to 2051-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2033-12-10 to 2051-12-10

## RA12
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA12
Relevant activities |  |  |  | Existing Rehabilitation to be re-disturbed (Grazing)
Total rehabilitation area size (ha) |  |  |  | 153
Commencement of first milestone: RM5 |  |  |  | 2034-12-10
PMLU |  |  |  | Grazing
Date area is available | 2034-12-10 | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 1948-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10 | 1956-12-10
Cumulative area available (ha) | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
Milestone completed by | 2036-12-10 | 2038-12-10 | 2040-12-10 | 2042-12-10 | 2044-12-10 | 2050-12-10 | 2052-12-10 | 2054-12-10 | 2056-12-10 | 2058-12-10 | 2060-12-10 | 2062-12-10 | 2064-12-10 | 2068-12-10 | 1970-12-10 | 2027-12-10 | 2074-12-10
Milestone Reference | Cumulative area achieved (ha)
RM5 | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
RM6 |  | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
RM7 |  | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
RM8 |  |  |  |  | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
RM9 | [5 empty] | 2 | 2 | 2 | 14 | 55 | 73 | 88 | 129 | 129 | 129 | 129 | 153
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA13
Post-mining land uses (PMLU)
Rehabilitation area |  | RA13
Relevant activities |  | Undisturbed Land
Total rehabilitation area size (ha) |  | 4230
Commencement of first milestone: RM9 |  | 2024-12-10
PMLU |  | Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 4230
Milestone completed by | 2029-12-10
Milestone Reference | Cumulative area achieved (ha)
RM9 | 4230
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Residual Voids
Total size (ha) |  |  |  | 882
Commencement of first milestone: MM1 |  |  |  | 2048-12-10
NUMA |  |  |  | NUMA
Date area is available | 2048-12-10 | 2049-12-10 | 2050-12-10 | 2053-12-10 | 2056-12-10 | 2057-12-10
Cumulative area available (ha) | 143 | 196.5 | 239.23 | 365.54 | 744.97 | 882
Milestone completed by | 2053-12-10 | 2054-12-10 | 2055-12-10 | 2058-12-10 | 2061-12-10 | 2062-12-10 | 2066-12-10 | 2069-12-10 | 2070-12-10
Milestone Reference | 2053-12-10: Cumulative area achieved (ha)
MM1 | 143 | 196.5 | 239.23 | 365.54 | 744.97 | 882
MM2 | 2055-12-10: 143; 2058-12-10: 239; 2061-12-10: 366; 2062-12-10: 745; 2066-12-10: 882
MM3 | 2061-12-10: 143; 2062-12-10: 239; 2066-12-10: 366; 2069-12-10: 745; 2070-12-10: 882
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure Decommissioning and Removal | 1. All services disconnected and decommissioned, unless agreed in writing by landholders and relevant agencies. 2. All built infrastructure demolished and removed, unless agreed in writing by landholders and relevant agencies. 3. All water management infrastructure not required for water management in post-mining landscape decommissioned, unless agreed in writing by landholders and relevant agencies. 4. All roads and access tracks removed, unless agreed in writing by landholders and relevant agencies. 5. All wastes and hazardous materials removed from site and lawfully disposed of. 6. Concrete pads, where not retained by landholder agreement (as approved by relevant agencies), are removed to a depth of 1.5 m below the landform elevation and backfilled to ground level or higher (for settlement).
RM2 | Remediation of Contaminated Land | 1. Contaminated water (e.g. affected by hydrocarbons, metals, etc.) is treated. 2. Contaminated land assessment undertaken by an appropriately qualified person (AQP1). 3. Any contaminated material either remediated in situ, encapsulated, or removed/transported to an approved landfill for disposal, and waste tracking information recorded and submitted. 4. Validation testing confirms that contaminated materials have been removed or remediated. 5. Evidence that all measures required in contaminated land assessments have been implemented. 6. If required, a site investigation report including a site suitability statement prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act. Additional PMLU Criteria for RA6 (Grazing): 1. Contaminated land assessment conducted to verify the proposed use is suitable. 2. No exposed hazardous materials at surface determined by results of site contaminated land investigation including exposure due to erosion. Additional PMLU Criteria for RA5 (Native Vegetation): 1. Contaminated land assessment conducted to verify the proposed use is suitable. 2. No exposed hazardous materials at surface determined by results of site contaminated land investigation including exposure due to erosion. 1AQP: a person who has professional qualifications, training, skills, or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.
RM3 | Installation of Cover System/Capping | 1. Certification from an AQP that tailings have dried and settled prior to capping. 2. Minimum capping layer of 4 m of non-acid forming material. 3. Certification from appropriately qualified person that surface capped with suitable material that has been certified as complying with design requirements.
RM4 | Vegetation Removal | 1. All vegetation is stripped from the landform and lawfully disposed of. 2. Topsoil stripped at a depth of 200 mm and stockpiled in accordance with the topsoil management plan.
RM5 | Landform Development | 1. All major earthworks completed to landform design in accordance with Condition F20 of the EA EPML00844613. 2. Final landform provides flood protection to all residual voids up to and including a 0.1% AEP and, where landform is required to function as permanent flood protection for a residual void, achieves a FoS of 1.2 and meets engineering design. 3. Where required, water management and erosion control structures (e.g. drainage swales and diversion channels) installed per design and certified by an AQP. 4. Geotechnical stability of built landforms confirmed by AQP. 5. Voids are backfilled to ground level or higher (for settlement) and self-draining, according to criteria in Condition F20 of the EA. 6. Spoil is shaped to be sympathetic to and consistent with the surrounding unmined areas, in accordance with Condition F20 of the EA. 7. Records retained of as built drawings to completely backfill void to certify that it is operating in accordance with landform and mine closure design and associated criteria in Condition F20 of the EA. 8. Records retained of reshaping of out-of-pit waste emplacement to certify that it is operating in accordance with landform and mine closure design and associated criteria in Condition F20 of the EA. 9. Water management infrastructure and erosion control structures installed as required.
RM5 Continued | Landform Development | Additional PMLU Criteria for RA1, RA8, RA12 and RA13 (Grazing): 1. Slopes are no greater than 12.5%. 2. Where required, benign Permian spoil cover is spread to a depth of 1 m and rock mulch to a depth of 0.4 m to minimise erosion. Additional PMLU Criteria for RA2, RA9, RA 10 and RA11 (Native Vegetation): 1. Slopes are no greater than 27%. 2. Where required, benign Permian spoil cover is spread to a depth of 1 m and rock mulch to a depth of 1 m to minimise erosion. Additional PMLU Criteria for RA3 (Native Vegetation [Riparian]): 1. Slopes are consistent with Twelve Mile Creek Diversion Functional Design. 2. Certification from an AQP that the diversion is constructed to design. Additional PMLU Criteria for RA4 (Water Storage): 1. Geotechnical stability confirmed by appropriately qualified hydro-geotechnical engineer. 2. Bywash/spillway structures confirmed to have adequate capacity. Additional PMLU Criteria for RA6 (Grazing): 1. Slopes are no greater than 12.5%. 2. Where required, benign Permian spoil cover is spread to a depth of 1 m and rock mulch to a depth of 0.4 m to minimise erosion. 3. A suitability qualified geotechnical engineer certifies that batters are safe and achieves a minimum factor of safety of 2. Additional PMLU Criteria for RA5 (Native Vegetation): 1. Slopes are no greater than 25%. 2. Where required, benign Permian spoil cover is spread to a depth of 1 m and rock mulch to a depth of 1 m to minimise erosion. 3. A suitability qualified geotechnical engineer certifies that batters are safe and achieves a minimum factor of safety of 2.
RM6 | Surface Preparation | 1. Certification that the growth medium has physical properties (e.g. rockiness, depth of soil, wetness and plant available water capacity) are adequate to sustain vegetation growth and chemical properties do not limit its suitability for vegetation growth. 2. Topsoil, or other growth medium such as benign waste rock or subsoil, is spread to a depth of 200 mm (+/- 50 mm). 3. Ameliorate spoil as required to a depth of a minimum of 200 mm to suitably stabilise the landform and promote vegetative establishment. 4. Ameliorants, where required, applied by an appropriately qualified person to achieve the PMLU at the following rates: - 5 t/ha of gypsum; - 50 kg/ha DAP with added zinc; - 100 kg/ha of urea; and - 100 kg/ha of coated (slow release) urea. Additional PMLU Criteria for RA1, RA6, RA8, RA12 and RA13 (Grazing): 1. Soil ripped on the contour.
RM7 | Revegetation | 1. Water management and erosion control structures, where required, are vegetated with stoloniferous grasses or other suitable ground cover. 2. Vegetated with a mix of perennial pasture species (grasses and legumes) and low-density wooded vegetation (for livestock shelter) suited to the reinstated soils, capable of sustaining grazing activities and providing stabilising groundcover. Additional PMLU Criteria for RA1, RA6, RA8, RA12 and RA13 (Grazing): 1. Direct seeding of palatable perennial pasture species seed mix at 1-4 kg/ha. Additional PMLU Criteria for RA2, RA5, RA9, RA 10 and RA11 (Native Vegetation): 1. Seeding of native species at 1-4 kg/ha for grasses, 1-2 kg/ha for legumes, 0.2-1 kg/ha for shrubs and 0.2-1 kg/ha for trees. 2. Planting of native species and/or tubestock at 350 stems per hectare, where required. Additional PMLU Criteria for RA3 (Native Vegetation [Riparian]): 1. Planting of native species and/or tubestock at 350 stems per hectare, where required. 2. Seeding with riparian and riverine vegetation at 1-4 kg/ha for grasses, 1-2 kg/ha for legumes, 0.2-1 kg/ha for shrubs and 0.2-1 kg/ha for trees.
RM8 | Surface Conditions - Grazing | 1. No active rill, piping, or gully erosion. 2. Certification by an AQP that drainage follows appropriate pathways. 3. Vegetation dominated by pasture grass and legume species. 4. Vegetation dominated by >70% palatable perennial pasture cover.
RM9 | Safe, stable and Sustainable Condition – Grazing | 1. Hazard and Safety Assessment completed by an AQP demonstrates hazards are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time. 2. Erosion rates comparable to reference sites as determined by Condition F15 of the EA. 3. Soil nutrient concentrations and nutrient cycling comparable to reference sites as determined by Condition F15 of the EA. 4. Annual monitoring indicates an absence of declared pest and weed species. 5. Evidence of natural recruitment (flowering, germination, viable seed and emergence) of palatable perennial pasture species. 6. Groundcover comprises >70% palatable perennial pasture cover. 7. Water quality in receiving waters does not exceed the limits in EA Table C5. 8. Run-off into receiving waters does not exceed the limits in EA Table C2. 9. Land suitability assessment by an AQP certifies that land has achieved a minimum post-mine land suitability Class of 4, and land is capable of supporting light intensity grazing. 10. Evidence that measures required in site contaminated land investigation report have been implemented. Additional PMLU Criteria for RA6 (Grazing): 1. Final surface is free-draining and includes drainage structures to channel run-off and to minimise erosion and surface water ponding.
RM10 | Surface Conditions – Native Vegetation | 1. No active rill, piping or gully erosion. 2. Certification by an AQP that drainage follows appropriate pathways. 3. Wooded vegetation density achieves a minimum of 350 stems per hectare. 4. Tree, shrub, and grass diversity and cover % are on a demonstrated trajectory towards being comparable to reference sites described in Condition F15 of the EA. 5. A minimum of eight target species per hectare established.
RM11 | Safe, stable and Sustainable Condition – Native Vegetation | 1. Hazard and Safety Assessment completed by an AQP demonstrates hazards are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time. 2. Erosion rates comparable to reference sites as determined by Condition F15 of the EA. 3. Soil nutrient concentrations and nutrient cycling comparable to reference sites as determined by Condition F15 of the EA. 4. Annual monitoring indicates an absence of declared pest and weed species. 5. Evidence of natural recruitment (flowering, germination, viable seed, and emergence) of native trees and shrubs. 6. Pest and weed density comparable to reference site determined by Condition F15 of the EA. 7. Water quality in receiving waters does not exceed the limits in EA Table C5. 8. Run-off into receiving waters does not exceed the limits in EA Table C2. 9. Ground cover comprises >30% living ground cover and >70% overall groundcover (includes live, dead, and non-vegetative). 10. Evidence that measures required in site contaminated land investigation report have been implemented. Additional PMLU Criteria for RA5 (Native Vegetation): 1. Final surface is free-draining and includes drainage structures to channel run-off and to minimise erosion and surface water ponding.
RM12 | Surface Conditions – Native Vegetation (Riparian) | 1. No active rill, piping, or gully erosion. 2. Certification by an appropriately qualified person that drainage follows appropriate pathways. 3. Vegetation dominated by native riparian species. 4. Similar geomorphology to regional ephemeral drainage lines as part of design plan in Condition F20 of the EA.
RM13 | Safe, stable and Sustainable Condition – Native Vegetation (Riparian) | 1. Hazard and Safety Assessment completed by an appropriately qualified person demonstrates hazards are consistent with the type and severity of hazards typical of the creek system in unmined landscape. Remaining hazards are considered to be low risk with no significant increase in risk expected over time. 2. Certification by an AQP that the creek diversion functions as designed, and that the integrity of Twelve Mile Creek and adjoining watercourses will be maintained long-term. 3. Certification by an AQP that the creek diversion and associated structures will maintain equilibrium and functionality and will not require ongoing maintenance. 4. Vegetation dominated by mixed riverine vegetation suitable for sandy clay soils along watercourses. 5. Evidence of natural recruitment. 6. Ground cover comprises >30% living ground cover and >70% overall groundcover (includes live, dead, and non-vegetative). 7. Water quality in receiving waters does not exceed the limits in EA Table C5. 8. Run-off into receiving waters does not exceed the limits in EA Table C2.
RM14 | Safe, stable and Sustainable Condition – Water Storage | 1. Hazard and Safety Assessment completed by an AQP demonstrates hazards are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time. 2. Records of retained of structural integrity of permanent retention of water storage structures, and certification that it is operating in accordance with landform and mine closure design and associated criteria in Condition F20 of the EA EPML00844613. 3. Removal of any contaminated sediments identified by site contaminated land investigation. 4. Water quality in receiving waters does not exceed the limits in EA Table C5. 5. Run-off into receiving waters does not exceed the limits in EA Table C2. 6. Management inputs required to sustain aquatic habitat are comparable to selected reference sites determined by Condition F15. 7. Retained water storage water quality parameters are below the trigger values for livestock drinking water defined in ANZECC and ARMCANZ 2000.
RM15 | Safe, stable and Sustainable Condition – Retained Infrastructure | 1. Hazard and Safety Assessment completed by an AQP demonstrates hazards are consistent with the type and severity of hazards typical of neighbouring equivalent land use. Remaining hazards are considered to be low risk with no significant increase in risk expected over time. 2. All built structures form part of a landholder agreement (as approved by relevant agencies). 3. Audit records demonstrate that areas subject to AS1940:2004 (The Storage and Handling of Flammable and Combustible Liquids) that are retained for use by the post-mining landholder comply with the standard. 4. Where required, diversion drains designed and built to have similar morphology and functionality to regional ephemeral drainage lines. 5. Evidence from an AQP the retained infrastructure is structurally and functionally sound before providing/selling such infrastructure to a future landholder.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | High- and Low Wall Treatment | 1. Highwall slope in competent rock is no greater than 70 degrees. 2. Highwall slope in incompetent rock is no greater than 45 degrees. 3. Low wall slope is no greater than 37 degrees. 4. Battering back, partial backfilling, regrading, and reshaping completed according to table F1 and Condition F20 of the EA. 5. Records retained of as built drawings to completely backfill void to certify that it is operating in accordance with Condition F20 of the EA. Additional Criteria for A-Pit: 1. maximum depth of 113 m; 2. maximum area of 126 ha; and 3. maximum volume of 40 Mm³. Additional Criteria for CE-North: 1. maximum depth of 40 m; 2. maximum area of 53 ha; and 3. maximum volume of 8 Mm³. Additional Criteria for DOM2N: 1. maximum depth of 100 m; 2. maximum area of 103 ha; and 3. maximum volume of 41 Mm³. Additional Criteria for DOM2S: 1. maximum depth of 59 m; 2. maximum area of 45 ha; and 3. maximum volume of 7 Mm³.
MM1 Continued | High- and Low Wall Treatment | Additional Criteria for DOM5: 1. maximum depth of 50 m; 2. maximum area of 133 ha; and 3. maximum volume of 41 Mm³. Additional Criteria for DOM6: 1. maximum depth of 54 m; 2. maximum area of 25 ha; and 3. maximum volume of 10 Mm³. Additional Criteria for YEN-Pit: 1. maximum depth of 129 m; 2. maximum area of 223 ha; and 3. maximum volume of 121 Mm³. Additional Criteria for YES-Pit: 1. maximum depth of 129 m; 2. maximum area of 174 ha; and 3. maximum volume of 87 Mm³.
MM2 | Surface Conditions | 1. Bund wall installed with a minimum height of 2 m, a minimum base of 4 m, and be located at least 10 m beyond the area potentially affected by instability of the pit edge or a fence. 2. Security fencing installed around entire perimeter and up to the highwall. 3. Appropriate signage placed to clearly identify and convey the purpose (e.g. EP Act 1994 Non-Use Management Area No Entry). 4. Any contaminated material either remediated in situ or removed/transported to an approved landfill for disposal, and waste tracking information recorded and submitted. 5. Validation testing confirms that contaminate materials (e.g. PCBs, dioxins, mercury, hydrocarbon contaminate soils) have been removed or remediated. 6. If required, a site investigation report including a site suitability statement prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act.
MM3 | Achievement of Sufficient Improvement | 1. Certification from an AQP that the residual void low walls, highwalls and end walls are safe and achieve a minimum FoS of 2.0. 2. Certification from an AQP that residual voids are internally draining. 3. Certification from an AQP that the residual void is safe to humans and livestock. 4. No exposed hazardous materials at surface determined by the results of site contaminated land investigation including exposure due to erosion. 5. Residual void acts as a groundwater sink in perpetuity. 6. Water balance modelling demonstrates that residual void water is contained with no potential for overflow events. 7. If required, evidence that measures required in site contaminated land investigation report have been implemented.
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## Species Lists
Native Vegetation PMLU - Direct Seeding |  |  | Grazing PMLU - Direct Seeding
Species (scientific) | Species (common) | Application rate | Species (scientific) | Species (common) | Application Rate (kg/ha)
Eucalyptus crebra | Narrow Leaved Ironbark | 0.2 kg/ha | Medicago truncatula | Barrel Medic | 1 kg/ha
Eucalyptus melanophloia | Silver Leaved Ironbark | 0.2 kg/ha | Cynodon dactylon | Bermuda couch | 2 kg/ha
Corymbia tesselaris | Moreton Bay Ash | 0.2 kg/ha | Heteropogon contortus | Black Speargrass | 0.2 kg/ha
Corymbia clarksoniana | Bloodwood | 0.1 kg/ha | Clitoria ternatea | Butterfly pea | 2 kg/ha
Corymbia gummifera | Red Bloodwood | 0.1 kg/ha | Stylosanthes seabrana | Caatinga stylo | 1 kg/ha
Acacia victoriae | Bardi Bush | 0.2 kg/ha | Bothriochloa insculpta | Creeping Bluegrass | 2.5 kg/ha
Atriplex nummularia | Old Man Saltbush | 0.2 kg/ha | Desmanthus virgatus | Desmanthus | 1 kg/ha
Enchylaena tomentosa | Ruby Saltbush | 0.2 kg/ha | Bothriochloa bladhii | Forest Bluegrass | 2.5 kg/ha
Bothriochloa insculpta | Creeping Bluegrass (cultivas Hatch or Bisset) | 2.5 kg/ha | Bothriiochloa pertusa | Indian Bluegrass | 2.5 kg/ha
Bothriochloa bladhii | Forest Bluegrass (cultivas Swann) | 2.5 kg/ha | Corymbia citriodora | Lemon Scented-Gum | 0.03 kg/ha
Digitaria eriantha | Digit Grass (cultivas Premier) | 2 kg/ha | Atriplex nummularia | Old Man Saltbush | 0.3 kg/ha
Bothriochloia pertusa | Indian Bluegrass (cultivas Keppel or Bowen) | 1 kg/ha | Setaria incrassata | Purple Pigeon Grass | 2 kg/ha
Urochloa mosambicensis | Sabi Grass (cultivas Saraji) | 2 kg/ha | Dicanthium sericeum | Queensland Bluegrass | 3 kg/ha
Melinis repens | Red Natal Grass | 1 kg/ha | Chloris gayana | Rhodes grass | 3.5 kg/ha
Cynodon dactylon | Greencouch | 2 kg/ha | Chamaecrista rotundifolia | Round-leafed cassia | 0.5 kg/ha
Bothriochloa ewartiana | Desert Bluegrass | 1 kg/ha | Enchylaena tomentosa | Ruby Saltbush | 0.3 kg/ha
Dichanthium sericeum | Queensland Bluegrass | 1 kg/ha | Urochloa mosambicensis | Sabi Grass | 3.5 kg/ha
Heteropogon contortus | Black Speargrass | 0.2 kg/ha | Stylosanthes scabra | Shrubby stylo | 1 kg/ha
Themeda triandra | Kangaroo Grass | 0.2 kg/ha | Digitaria milanjiana | Tall Finger Grass | 1 kg/ha
Cymbopogon refractus | Barbed Wire Grass | 0.2 kg/ha
Bothriochloa decipiens | Pitted Bluegrass | 0.2 kg/ha
Chloris gayana | Rhodes Grass | 1 kg/ha
Wynn cassia | Round Leaf Cassia | 1 kg/ha
Clitoria ternatea | Butterfly Pea | 1 kg/ha
Native Vegetation PMLU - Tubestock
Species (scientific) | Species (common) | Application rate
Eucalyptus cambageana | Blackbutt | 100 stems/ha
Eucalyptus ochrophloia | Yapunyah | 101 stems/ha
Acacia harpophylla | Brigalow | 102 stems/ha
Corymbia citriodora | Spotted Gum | 103 stems/ha
Eucalyptus argophloia | Chinchilla White Gum | 104 stems/ha
Casuarina cristata | Belah | 105 stems/ha
Cassia brewsteri | Leichardt Bean | 106 stems/ha
Eucalyptus molucanna | Grey Box | 70 stems/ha
Allocasuarina luehmannii | Bulloak | 70 stems/ha
Eucalyptus populnea | Poplar Box | 30 stems/ha
Eremophila mitchellii | False sandalwood | 45 stems/ha
Owenia acidula | Emu Apple | 25 stems/ha
Carissa ovata | Currant Bush | 30 stems/ha
Brachychiton rupestris | Narrow-Leaved Bottle Tree | 30 stems/ha
Brachychiton acerifolius | Illawarra Flame Tree | 3 stems/ha
Geijera parviflora | Wilga | 30 stems/ha