## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | TSF Cell B
Total rehabilitation area size (ha) |  |  |  | 62.4
Commencement of first milestone: RM1 |  |  |  | 2035-12-10
PMLU |  |  |  | Open pasture - grazing
Date area is available | 2035-12-10
Cumulative area available (ha) | 62.4
Milestone completed by | 2037-12-10 | 2044-12-10 | 2054-12-10 | 2064-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 62.4
RM2 | 62.4
RM5 |  | 62.4
RM7 |  | 62.4
RM8 |  | 62.4
RM9 |  |  | 62.4
RM10 |  |  |  | 62.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Heap Leach Pad and associated ponds
Total rehabilitation area size (ha) |  |  |  | 21
Commencement of first milestone: RM1 |  |  |  | 2035-12-10
PMLU |  |  |  | Low hill - pasture grazing
Date area is available | 2035-12-10
Cumulative area available (ha) | 21
Milestone completed by | 2037-12-10 | 2045-12-10 | 2055-12-10 | 2065-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 21
RM2 | 21
RM6 |  | 21
RM7 |  | 21
RM8 |  | 21
RM9 |  |  | 21
RM10 |  |  |  | 21
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Rehabilitated water management structures
Total rehabilitation area size (ha) |  |  |  | 24.8
Commencement of first milestone: RM1 |  |  |  | 2045-12-10
PMLU |  |  |  | Open pasture - grazing
Date area is available | 2045-12-10
Cumulative area available (ha) | 24.8
Milestone completed by | 2049-12-10 | 2059-12-10 | 2069-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 24.8
RM4 | 24.8
RM7 | 24.8
RM8 | 24.8
RM9 |  | 24.8
RM10 |  |  | 24.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure areas
Total rehabilitation area size (ha) |  |  |  | 10.6
Commencement of first milestone: RM1 |  |  |  | 2046-12-10
PMLU |  |  |  | Open pasture - grazing
Date area is available | 2046-12-10
Cumulative area available (ha) | 10.6
Milestone completed by | 2051-12-10 | 2061-12-10 | 2071-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 10.6
RM2 | 10.6
RM3 | 10.6
RM7 | 10.6
RM8 | 10.6
RM9 |  | 10.6
RM10 |  |  | 10.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Maintenance of existing rehabilitation (South Pit, TSF Cell A, Village infrastructure)
Total rehabilitation area size (ha) |  |  |  | 55.7
Commencement of first milestone: RM1 |  |  |  | Prior to 2022
PMLU |  |  |  | Open pasture - grazing
Date area is available | Prior to 2022 |  | 2041-12-10
Cumulative area available (ha) | 54.4 |  | 55.7
Milestone completed by | Prior to 2022 | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2055-12-10 | 2065-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 54.4 |  | 55.7
RM3 | 54.4 |  | 55.7
RM7 | 54.4 |  | 55.7
RM8 | 54.4 |  | 55.7
RM9 |  | 54.4 |  |  | 55.7
RM10 |  |  |  | 54.4 |  | 55.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | ROM Pad
Total rehabilitation area size (ha) |  |  |  | 5.8
Commencement of first milestone: RM1 |  |  |  | 2035-12-10
PMLU |  |  |  | Low hill - pasture grazing
Date area is available | 2035-12-10
Cumulative area available (ha) | 5.8
Milestone completed by | 2039-12-10 | 2049-12-10 | 2059-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 5.8
RM3 | 5.8
RM7 | 5.8
RM8 | 5.8
RM9 |  | 5.8
RM10 |  |  | 5.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Other isolated areas of surface disturbance within approved disturbance extent
Total rehabilitation area size (ha) |  |  |  | 90
Commencement of first milestone: RM1 |  |  |  | 2035-12-10
PMLU |  |  |  | Open pasture - grazing
Date area is available | Prior to 2022 | 2035-12-10 |  | 2043-12-10
Cumulative area available (ha) | 3.9 | 22.6 |  | 90
Milestone completed by | Prior to 2022 | 2039-12-10 | 2040-12-10 | 2047-12-10 | 2049-12-10 | 2050-12-10 | 2057-12-10 | 2059-12-10 | 1967-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 3.9 | 22.6 |  | 90
RM3 | 3.9 | 22.6 |  | 90
RM7 | 3.9 | 22.6 |  | 90
RM8 | 3.9 | 22.6 |  | 90
RM9 |  |  | 3.9 |  | 22.6 |  | 90
RM10 | [5 empty] | 3.9 |  | 22.6 | 90
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Retained water storages
Total rehabilitation area size (ha) |  |  | 52.2
Commencement of first milestone: RM1 |  |  | 2045-12-10
PMLU |  |  | Retained water storage
Date area is available | 2045-12-10
Cumulative area available (ha) | 52.2
Milestone completed by | 2046-12-10 | 2056-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 52.2
RM11 |  | 52.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA9
Relevant activities |  |  | Retained infrastructure
Total rehabilitation area size (ha) |  |  | 45
Commencement of first milestone: RM1 |  |  | 2045-12-10
PMLU |  |  | Retained infrastructure
Date area is available | 2045-12-10
Cumulative area available (ha) | 45
Milestone completed by | 2046-12-10 | 2047-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 45
RM12 |  | 45
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Main Pit Final Void
Total size (ha) |  |  |  | 20.3
Commencement of first milestone: MM1 |  |  |  | 2035-12-10
NUMA |  |  |  | Lake
Date area is available | 2035-12-10
Cumulative area available (ha) | 20.3
Milestone completed by | 2040-12-10 | 2041-12-10 | 2051-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 20.3
MM2 |  | 20.3
MM3 |  |  | 20.3
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## IA2
Non-use management area (NUMA)
Improvement area |  |  |  | IA2
Relevant activities |  |  |  | East Hill Pit Final Void
Total size (ha) |  |  |  | 0.7
Commencement of first milestone: MM1 |  |  |  | 2046-12-10
NUMA |  |  |  | Void
Date area is available | 2046-12-10
Cumulative area available (ha) | 0.7
Milestone completed by | 2051-12-10 | 2052-12-10 | 2062-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 0.7
MM2 |  | 0.7
MM3 |  |  | 0.7
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria | Applicable RA
RM1 | Infrastructure decommissioning and removal | a) All non-required services disconnected and removed. b) All non-required concrete and gravel removed. c) All non-required operational pipelines drained and removed. d) All fencing that is not part of PMLU requirements removed. e) All buildings and footings demolished and/or removed off-site. f) All machinery and equipment removed. g) All non-retained surface water drainage infrastructure removed. h) All rubbish removed. | All
RM2 | Remediation of contaminated land | a) Contaminated material either remediated in-situ or removed/transported to an approved landfill for disposal and waste tracking information recorded and submitted. b) Contaminated land assessment undertaken by an appropriately qualified person1 indicates that no contamination unsuitable for the post mining land use is occurring. If required, a site investigation report including a site suitability statement prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act. | RA1, RA2, RA4
RM3 | Landform development of infrastructure areas | a) All bulk earthworks completed. b) Geotechnical assessment by an appropriately qualified person1 confirming that long-term geotechnical stability has been achieved for each relevant landform. c) Final landform slopes meet design specifications: i. TSF Cell A embankments – i. Maximum slope of 30% subject to geotechnical and erosional stable conditions. | RA4, RA6, RA7, RA5
RM4 | Landform development of water storages | General: a) All earthworks completed. b) Water drainage lines reinstated and stabilised to allow natural flow. Dams: a) Sediment dams cleaned (desilted). b) Where landform incorporates slopes > 17%, geotechnical assessment by an appropriately qualified person1 confirming that long-term geotechnical stability has been achieved. Main Pit water management bund: a) Design plan certified by an appropriately qualified person1 is developed for the final landform. Design plan demonstrates that modification of the levee does not result in potential environmental harm. b) Assessment by an appropriately qualified person to confirm the post-closure regulated status of the water management bunding structure. c) All earthworks completed as per the approved design plan. d) Assessment by an appropriately qualified person1 confirming that long-term geotechnical stability has been achieved.d) Certification from an appropriately qualified person that the area has achieved stable condition. | RA3
RM5 | Landform development of TSF Cell B | a) All bulk earthworks completed. b) Cover system is installed with the appropriate QA/QC measures to: i. Compact tailings surface to form a low permeability layer; ii. Cover tailings with at least 1.0 m of top rock, followed by 0.15 m of growth media. c) Assessment by an appropriately qualified person1 confirming that long-term geotechnical stability has been achieved. d) An assessment by an appropriately qualified person of groundwater monitoring data (collected in accordance with monitoring and maintenance program), confirms cover system is functioning as designed and risk of environmental harm is mitigated. | RA1
RM6 | Landform development of Heap Leach Pad | a) All bulk earthworks completed. b) Cover system is installed with the appropriate QA/QC measures to: a. comprise at least 0.5 m of top rock, followed by 0.15 m of growth media. c) Final slopes meet design specifications: ii. Maximum slope of 25 % subject to geotechnical and erosional stable conditions. d) Assessment by an appropriately qualified person1 confirming that long-term geotechnical stability has been achieved. e) An assessment by an appropriately qualified person of groundwater monitoring data (collected in accordance with monitoring and maintenance program), confirms cover system is functioning as designed and risk of environmental harm is mitigated. | RA2
RM7 | Surface preparation | a) Ripping of soil profile /subsoil profile along the contour of any slope to a depth of at least 200 mm. b) Prior to seeding, assessment of soil health and suitability for target vegetation establishment undertaken by an appropriately qualified person1 and a recommendation made for ameliorants suitable to achieve the post-mining land use revegetation program. c) Ameliorants applied and incorporated into subsoil and/or topsoil if required, as per recommendations of the soil health and suitability assessment. | RA1, RA2, RA3, RA4, RA5, RA6, RA7
RM8 | Revegetation | a) Seeding of target key species completed at a sowing rate of 6 kg/ha drawn from Table 23 Recommended species for revegetation (Yandan Gold Mine Transitional PRCP). b) No later than 12 months from planting, a >50% survival rate for any given perennial species is achieved. | RA1, RA2, RA3, RA4, RA5, RA6, RA7
RM9 | Achievement of surface requirements (open pasture – grazing and low hill – pasture grazing) | a) Total percentage of vegetation groundcover2 is not significantly lower (P<0.05) than that recorded at reference sites. b) Species diversity is not significantly lower (P<0.05) than that recorded at reference sites. c) Species composition not significantly different (P<0.05) to reference sites. d) Total percentage of weed groundcover is not significantly higher (P<0.05) than reference sites. e) Erosion classification3 (per the Rehabilitation Monitoring Program methodology) to be comparable with erosion classifications from reference sites. | RA1, RA2, RA3, RA4, RA5, RA6, RA7
RM10 | Achievement of target post mining land use (open pasture – grazing and Low hill – pasture grazing) | a) Land suitability assessment by an appropriately qualified person1 confirming land has achieved a post-mine land suitability4 of a. 4 for low intensity grazing, or b. 5 for low intensity grazing, supported by an appropriate management regime. b) Demonstration within the final rehabilitation report that vegetation groundcover2, species diversity and species composition in rehabilitation areas is not significantly lower (P<0.05) than reference sites for a minimum of three consecutive years. c) Demonstration within the final rehabilitation report that total percentage of weed groundcover in rehabilitation areas is not significantly higher (P<0.05) than reference sites for a minimum of three consecutive years. d) Evidence of recruitment from rehabilitation monitoring data. e) Erosion classification3 (per the Rehabilitation Monitoring Program methodology) to be comparable with erosion classifications from reference sites for a minimum of three consecutive years. f) Written agreement obtained from the land owner/holder and administering authority that rehabilitation is successful. g) Hazard and Safety Assessment completed by an appropriately qualified person1 demonstrates that hazards in rehabilitation areas are of a similar type and not significantly different to hazards in reference sites. | RA1, RA2, RA3, RA4, RA5, RA6, RA7
RM11 | Achievement of target post-mining land use (retained water storages) | a) Assessment by an appropriately qualified person confirms the structure is not regulated. b) All retained water storages to be assessed and approved as safe and stable by an appropriately1 qualified person. c) Hazard and Safety Assessment completed by an appropriately qualified person1 demonstrates that hazards in retained water storages are of a similar type and not significantly different to hazards in neighbouring unmined water storages subject to similar use d) Retained storage water quality parameters to be below the trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality – Volume 3 Primary Industries — Rationale and Background Information (ANZECC and ARMCANZ 2000). | RA8
RM12 | Achievement of target post-mining land use (retained infrastructure) | a) Final landform survey confirms no built structures remain other than those that form part of a landholder agreement. b) All retained structures and landforms assessed and approved as safe and stable by an appropriately qualified person1. | RA9
Footnotes:
1. Appropriately qualified person means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.
2. Vegetation groundcover incorporates native pasture grass species, exotic pasture grass species, non-pasture grass species, shrubs (woody plant multi-stemmed at base or, if single stemmed, <2 m tall), forbs and other non-grass species.
3. Erosion classification framework:
4. Department of Science, Information Technology and Innovation and Department of Natural Resources and Mines (2015) Guidelines for Agricultural Land Evaluation in Queensland (Second Edition), State of Queensland or later version. (https://www.publications.qld.gov.au/dataset/qld-agricultural-land-evaluation-guidelines/resource/d6591386-08e2-453f-a6fa-dff2a756215f)
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of final landform design | a) Final void high walls comply with maximum safe and stable slope angles as nominated in geotechnical stability assessment.
MM2 | Achievement of surface requirements | a) Standard barbed wire fencing erected around the perimeter of the residual void to prevent access by humans and fauna. b) Warning signage posted every 100 m around the perimeter of the residual void. c) Safety bund constructed around perimeter of the residual void.
MM3 | Achievement of sufficient improvement | a) Assessment by an appropriately qualified person1 that the residual void will not cause environmental harm outside of the relevant tenure boundary. b) Assessment by an appropriately qualified person that the water quality and/or level in the void will not cause environmental harm to the surrounding environment: i. Main Pit – water balance modelling confirms that long-term pit water depth will remain greater than 160 m AHD for the maintenance of a permanent water cover over sulphide material in the pit walls and floor. ii. East Hill Pit - water balance modelling confirms that long-term pit water depth will remain above the sandstone unit within the pit for the prevention of potential groundwater contamination.
Footnotes:
1. Appropriately qualified person means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones