## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | TSF Cell B
Total rehabilitation area size (ha) |  |  |  | 68.3
Commencement of first milestone: RM1 |  |  |  | 2026-06-01
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | 2025-12-10
Cumulative area available (ha) | 68.3
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | 2046-12-10 | 1956-12-10 | 2055-12-10 | 1960-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 68.3
RM2 | 68.3
RM5 |  | 68.3
RM8 |  | 68.3
RM9 |  |  | 68.3 | 68.3
RM10 |  |  |  | 68.3
RM11 |  |  |  |  | 68.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Heap Leach Pad and associated ponds
Total rehabilitation area size (ha) |  |  |  | 20.8
Commencement of first milestone: RM1 |  |  |  | 2036-06-01
PMLU |  |  |  | Low hill - low intensity pasture grazing
Date area is available | 2035-12-10
Cumulative area available (ha) | 20.8
Milestone completed by | 2040-12-10 | 2045-12-10 | 2050-12-10 | 2056-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 20.8
RM2 | 20.8
RM7 |  | 20.8
RM8 |  | 20.8
RM9 |  |  | 20.8
RM10 |  |  |  | 20.8
RM11 |  |  |  | 20.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3a
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3a
Relevant activities |  |  |  | Rehabilitated water management structures
Total rehabilitation area size (ha) |  |  |  | 32.5
Commencement of first milestone: RM1 |  |  |  | 2037-06-01
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | 2036-12-10
Cumulative area available (ha) | 32.5
Milestone completed by | 2041-12-10 | 2046-12-10 | 2056-12-10 | 2066-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 32.5
RM4 | 32.5
RM8 | 32.5
RM9 |  | 32.5
RM10 |  |  | 32.5
RM11 |  |  |  | 32.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3b
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3b
Relevant activities |  |  |  | Rehabilitated water management structures - Main Pit flood bund
Total rehabilitation area size (ha) |  |  |  | 2.7
Commencement of first milestone: RM2 |  |  |  | 2026-06-01
PMLU |  |  |  | Flood protection landform
Date area is available | 2025-12-10
Cumulative area available (ha) | 2.7
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 2.7
RM2 | 2.7
RM4 | 2.7
RM8 | 2.7
RM9 | 2.7
RM14 |  | 2.7
RM15 |  |  | 2.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure areas
Total rehabilitation area size (ha) |  |  |  | 5.9
Commencement of first milestone: RM1 |  |  |  | 2037-06-01
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | 2036-12-10
Cumulative area available (ha) | 5.9
Milestone completed by | 2041-12-10 | 2046-12-10 | 2052-12-10 | 1962-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 5.9
RM2 | 5.9
RM3 | 5.9
RM8 | 5.9
RM9 |  | 5.9
RM10 |  |  | 5.9
RM11 |  |  |  | 5.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5a
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA5a
Relevant activities |  |  | Maintenance of existing rehabilitation (South Pit, Village infrastructure)
Total rehabilitation area size (ha) |  |  | 12.3
Commencement of first milestone: RM1 |  |  | Prior to 2025
PMLU |  |  | Open pasture - low intensity grazing
Date area is available | Prior to 2025
Cumulative area available (ha) | 12.3
Milestone completed by | 2030-12-10 | 2040-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 12.3
RM3 | 12.3
RM8 | 12.3
RM9 | 12.3
RM10 | 12.3
RM11 |  | 12.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5b
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5b
Relevant activities |  |  |  | Maintenance of existing rehabilitation (TSF Cell A)
Total rehabilitation area size (ha) |  |  |  | 41.6
Commencement of first milestone: RM1 |  |  |  | 2026-06-01
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | 2025-12-10
Cumulative area available (ha) | 41.6
Milestone completed by | 1930-12-10 | 2035-12-10 | 2040-12-10 | 2046-12-10 | 2056-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 41.6
RM2 | 41.6
RM6 |  | 41.6
RM8 |  | 41.6
RM9 |  |  | 41.6
RM10 |  |  |  | 41.6
RM11 |  |  |  |  | 41.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6
Relevant activities |  |  | ROM Pad
Total rehabilitation area size (ha) |  |  | 5.8
Commencement of first milestone: RM1 |  |  | Prior to 2025
PMLU |  |  | Low hill - low intensity pasture grazing
Date area is available | Prior 2025
Cumulative area available (ha)
Milestone completed by | 2034-12-10 | 2044-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 5.8
RM3 | 5.8
RM8 | 5.8
RM9 | 5.8
RM10 | 5.8
RM11 |  | 5.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Other isolated areas of surface disturbance within approved disturbance extent
Total rehabilitation area size (ha) |  |  |  | 19.9
Commencement of first milestone: RM1 |  |  |  | Prior 2025
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | Prior to 2025 |  | 1935-12-10
Cumulative area available (ha) | 1.4 |  | 19.9
Milestone completed by | 1930-12-10 | 2035-12-10 | 2040-12-10 | 2045-12-10 | 2051-12-10 | 2061-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 1.4 |  | 19.9
RM3 | 1.4 |  | 19.9
RM8 | 1.4 |  | 19.9
RM9 | 1.4 |  |  | 19.9
RM10 |  | 1.4 | 1.4 |  | 19.9
RM11 |  |  |  | 1.4 | 1.4 | 19.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Retained water storages
Total rehabilitation area size (ha) |  |  | 52.8
Commencement of first milestone: RM1 |  |  | 2047-06-01
PMLU |  |  | Retained water storage
Date area is available | 2046-12-10
Cumulative area available (ha) | 52.8
Milestone completed by | 2047-12-10 | 2056-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 52.38
RM12 |  | 52.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA9
Relevant activities |  |  | Retained infrastructure
Total rehabilitation area size (ha) |  |  | 34.7
Commencement of first milestone: RM1 |  |  | 2047-06-01
PMLU |  |  | Retained infrastructure
Date area is available | 2046-12-20 | 2066-12-10
Cumulative area available (ha) | 0.98 | 34.7
Milestone completed by | 2048-12-10 | 2068-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.98 | 34.7
RM13 | 0.98 | 34.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10
Relevant activities |  |  |  | Borrow pits
Total rehabilitation area size (ha) |  |  |  | 36.6
Commencement of first milestone: RM1 |  |  |  | 2034-06-01
PMLU |  |  |  | Open pasture - low intensity grazing
Date area is available | 1933-12-10
Cumulative area available (ha) | 36.6
Milestone completed by | 1938-12-10 | 2043-12-10 | 2048-12-10 | 2058-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 36.6
RM3 | 36.6
RM8 | 36.6
RM9 |  | 36.6
RM10 |  |  | 36.6
RM11 |  |  |  | 36.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Main Pit Final Void
Total size (ha) |  |  |  | 20.3
Commencement of first milestone: MM1 |  |  |  | 2026-06-01
NUMA |  |  |  | Lake
Date area is available | 2025-12-10
Cumulative area available (ha) | 20.3
Milestone completed by | 2030-12-10 | 2031-12-10 | 2041-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 20.3
MM2 |  | 20.3
MM3 |  |  | 20.3
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## IA2
Non-use management area (NUMA)
Improvement area |  |  |  | IA2
Relevant activities |  |  |  | East Hill Pit Final Void
Total size (ha) |  |  |  | 0.7
Commencement of first milestone: MM1 |  |  |  | 2026-06-01
NUMA |  |  |  | Void
Date area is available | 2025-12-10
Cumulative area available (ha) | 0.7
Milestone completed by | 2030-12-10 | 2031-12-10 | 2041-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 0.7
MM2 |  | 0.7
MM3 |  |  | 0.7
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Rehabilitation milestone | Applicable rehabilitation areas | Milestone criteria
RM1 -Infrastructure decommissioning and removal | All (excluding RA3b) | 1. With the exception of any infrastructure to remain as part of the PMLU (PMLU) or where infrastructure is agreed to be retained by the landholder as evidenced by a signed landholder agreement, the following are complete:
a. All non-required services disconnected and removed.
b. All non-required concrete and gravel removed.
c. All non-required operational pipelines drained and removed.
d. All fencing that is not part of PMLU requirements removed.
e. All buildings and footings demolished and/or removed off-site.
f. All machinery and equipment removed.
g. All non-retained surface water drainage infrastructure removed.
h. All rubbish removed.
RM2 - Remediation of contaminated land (where required) | RA1, RA2, RA3b, RA4 | 1. Preliminary site investigation completed by a suitably qualified person (SQP) 7.
2. Contaminated and hazardous material either remediated in-situ or removed/transported to an approved landfill for disposal and waste tracking information recorded and submitted.
3. Validation testing confirms that contaminated soils have been removed or remediated.
4. Contaminated land assessment undertaken by SQP7 indicates that no contamination unsuitable for the post mining land use is occurring. If required, a site investigation report including a site suitability statement prepared and submitted in accordance with the provisions of Chapter 7, Part 8 of the EP Act.
RM3 - Landform development of infrastructure areas | RA4, RA5a, RA5b, RA7 | 1. All bulk earthworks completed.
2. Geotechnical assessment by an AQP1 confirming that long-term geotechnical stability has been achieved for each relevant landform.
RM4 - Landform development of rehabilitated water management structures | RA3a, RA3b | General:
1. All earthworks completed.
2. Water drainage lines reinstated and stabilised to allow natural flow.
Dams:
3. Sediment dams cleaned (desilted).
4. Where landform incorporates slopes > 9.7° (17%) , geotechnical assessment by an AQP1 confirming that long-term geotechnical stability has been achieved.
Main Pit flood protection bund:
5. Reparation of existing erosion undertaken through either surface repair and/or the application of a gypsum/lime.
6. Assessment by an AQP to confirm the post-closure regulated status of the water management bunding structure.
7. Assessment by an AQP1 confirming that long-term geotechnical stability has been achieved.
RM5 - Landform development of TSF Cell B | RA1 | 1. All bulk earthworks completed.
2. Cover system is installed with the appropriate QA/QC measures to:
a. Compact tailings surface to form a low permeability layer; and
b. Cover tailings with 400 mm – 600 mm of gravelly topsoil material.
3. Assessment by an AQP1 confirming that long-term geotechnical stability (FoS≥1.5) has been achieved.
4. An assessment by an AQP1 of groundwater monitoring data (collected in accordance with monitoring and maintenance program), confirms cover system is functioning as designed and risk of environmental harm is mitigated.
RM6 - Landform reparation activities for Cell A | RA5b | 1. All bulk earthworks completed.
2. Geotechnical assessment by an AQP1 confirming that long-term geotechnical stability (FoS≥1.5) has been achieved.
3. Final landform slopes meet design specifications, TSF Cell A embankments achieves a maximum slope of 16.7° (30%) subject to geotechnical and erosional stable conditions.
RM7 – Landform development of HLP | RA2 | 1. All bulk earthworks completed.
2. Mitigation measures for reducing flood velocities installed to landform, as required.
3. Cover system is installed with the appropriate QA/QC measures to: comprise at least 0.5 m of top rock, followed by 0.15 m of growth media.
4. Final slopes meet design specifications: maximum slope of 25% subject to geotechnical and erosional stable conditions.
5. Assessment by an AQP1 confirming that long-term geotechnical stability (FoS≥1.5) has been achieved.
6. An assessment by an AQP of groundwater monitoring data (collected in accordance with monitoring and maintenance program), confirms cover system is functioning as designed and risk of environmental harm is mitigated.
RM8 – Surface preparation | RA1, RA2, RA3a, RA3b, RA4, RA5a, RA5b, RA6, RA7 | 1. Ripping of soil profile /subsoil profile along the contour of any slope to a depth of at least 200 mm.
2. Topsoiling at a minimum depth of 0.15 m (excluding RA3b & RA1).
3. Prior to seeding, assessment of soil health and suitability for target vegetation establishment undertaken by an AQP1 and a recommendation made for ameliorants suitable to achieve the PMLU revegetation program.
4. Ameliorants applied and incorporated into subsoil and/or topsoil if required, as per recommendations of the soil health and suitability assessment.
5. Gypsum or organic matter applied on slopes greater than 9.7° (17%) at RA1, RA2, RA3b and RA5b.
6. Aglime applied to the surface of RA1 at a rate of 1.8t/m3, where required
RM9 - Revegetation | RA1, RA2, RA3a, RA3b, RA4, RA5a, RA5b, RA6, RA7, RA10 | 1. Cover crops applied at rate of 30 kg/ha on slopes greater than 9.7° (17%) at RA1, RA2 and RA5b.
2. Seeding of target key species completed at a sowing rate of 6 kg/ha drawn from the table below.
|  | Vegetation type | Target Species
|  | Groundcover | Aristida latifolia (Feathertop wiregrass) (Native)
Chloris truncata (Windmill grass) (Native)
Dactylon radulans (Button Grass) (Native)
Cynodon dactylon (Green Couch) (Native)
Panicum effusum (Native Millet) (Native)
Urochloa mosambicensis (Sabi Grass) (Exotic)
Cenchrus ciliaris (Buffel Grass) (Exotic)
Bothriochloa pertusa (Indian Bluegrass) (Exotic)
|  | Shrub | Carrissa spinarum (Currant Bush)
Capparis lasiantha (Nipan)
Stylosanthes scabra (Shrubby stylo)
Acacia salicina (Sally wattle)
RM10 - Achievement of revegetation criteria (open pasture – grazing and low hill – pasture grazing) | RA1, RA2, RA3a, RA4, RA5a, RA5b, RA6, RA7, RA10 | 1. Total percentage of vegetation groundcover2:
a. is not significantly lower (P<0.05) than that recorded at reference sites4 or
b. For slopes >9.7° (17%) at RA1, RA2 and RA5b is 70%.
2. Species diversity is not significantly lower (P<0.05) than that recorded at reference sites4.
3. Species composition not significantly different (P<0.05) to reference sites4.
4. Weed8 presence is a maximum of 10% of total vegetative groundcover confirmed by an AQP1 in annual monitoring. Weed management recommendations to be provided in annual reports
5. No evidence of erosion classified as ‘moderate’ or ‘severe’ 3 .
RM11 - Achievement of PMLU to stable condition (open pasture – grazing and Low hill – pasture grazing) | RA1, RA2, RA3a, RA4, RA5a, RA5b, RA6, RA7, RA10 | 1. Land suitability assessment by an AQP1 confirming land has achieved a post-mine land suitability5 of
a. 4 for low intensity grazing for Clayey soils, or
b. 5 for low intensity grazing for Sandy soils, supported by an appropriate management regime.
2. Demonstration within the final rehabilitation report that vegetation groundcover2, species diversity and species composition in rehabilitation areas is not significantly lower (P<0.05) than reference sites for a minimum of three consecutive years.
3. Demonstration within the final rehabilitation report that total percentage of weed groundcover in rehabilitation areas is not significantly higher (P<0.05) than reference sites for a minimum of three consecutive years.
4. No evidence of erosion classified as ‘moderate’ or ‘severe’ 3 for three consecutive years.
5. Hazard and Safety Assessment completed by an AQP1 demonstrates that hazards in rehabilitation areas are of a similar type and not significantly different to hazards in reference sites. As defined in AS/NZS ISO 31000:2018 Risk Management.
6. Surface water quality monitoring undertaken through the life of the mine (as required by the EA), has indicated no potential impacts to any surface water values including aquatic ecology, resulting from the rehabilitated landforms.
7. Groundwater quality monitoring undertaken through the life of the mine and through the period of rehabilitation establishment (as required by the EA), has indicated no potential impacts to any groundwater values resulting from the rehabilitated landforms.
RM12 - Achievement of PMLU to stable condition (retained water storages) | RA8 | 1. Assessment by an AQP1 confirms the structure is not regulated.
2. Mine Water Dam de-silted and sediment removed to an average depth of 0.25 m.
3. All retained water storages to be assessed and approved as safe and stable6 by an appropriately1 qualified person: where,
a. no ‘moderate’ or ‘Severe’ erosion4 and drainage follows appropriate paths;
b. for slopes of banks and spillways >9.7° (17%) , geotechnical assessment confirms slopes achieve a FoS of >1.5.
4. Hazard and Safety Assessment completed by an AQP1 demonstrates that hazards in retained water storages are of a similar type and not significantly different to hazards in neighbouring unmined water storages subject to similar use. As defined in AS/NZS ISO 31000:2018 Risk Management.
5. Retained storage water quality parameters to be below the trigger values for livestock drinking water defined in Environmental Protection (Water and Wetland Biodiversity) Policy 2019 Suttor River Sub-basin Environmental Values and Water Quality Objectives (EPPD & DES 2022).
6. Transfer of ownership agreements in place for all infrastructure to be retained.
RM13 - Achievement of PMLU to stable condition (retained infrastructure) | RA9 | 7. Transfer of ownership agreements in place for all infrastructure to be retained.
8. Final landform survey confirms no built structures remain other than those that form part of a landholder agreement.
9. All retained structures and landforms assessed and approved as safe and stable6 by an AQP1. As defined in AS/NZS ISO 31000:2018 Risk Management.
RM14 – Achievement of target revegetation criteria (Flood management landform) | RA3b | 1. Total groundcover (vegetation, rock, erosion matting etc) ≥70%.
2. No “moderate: or “severe” erosion as per the Erosion classification3.
3. Exclusion of Stock – Standard barbed wire fencing, with four barbed wire stands and the use of strainers as required have been erected around the perimeter of the East Hill Pit void to prevent access by humans and fauna.
RM15 - Achievement of PMLU to stable condition (Flood management landform) | RA3b | 1. Total groundcover (vegetation, rock, erosion matting etc) ≥70% on three consecutive monitoring occasions.
2. No evidence of erosion classified as ‘moderate’ or ‘severe’ 3 on three consecutive occasions.
3. Certification from AQP1 that the area has achieved stable condition, which includes:
a. flood management bund achieves a FoS ≥1.5.
b. Hazard and safety assessment completed in accordance with AS/NZS ISO 31000:2018 Risk Management.
1. Appropriately qualified person means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.
2. Vegetation groundcover incorporates native pasture grass species, exotic pasture grass species, non-pasture grass species, shrubs (woody plant multi-stemmed at base or, if single stemmed, <2 m tall), forbs and other non-grass species.
3. Erosion classification framework:
Erosion classification | Minor | Moderate | Severe
Sheet erosion | Shallow soil deposits downslope | Partial exposure of roots; moderate soil deposits downslope, etc | Loss of surface horizon; root exposure, etc
Rill/gully erosion | <15 rills and <0.3m deep | 15-30 rills and <0.3m deep | >30 rills and/or any >0.3m deep.
Tunnel erosion | Absent | Absent | Present
Mass movement | Absent | Absent | Present
*Gully: highly visible form of soil erosion, with steep-sided, incised drainage lines greater than 30 cm deep.
4. Vegetation reference monitoring locations:
Site name | Easting | Northing | Location | Year established
R1 | 501535 | 7644552 | South of the village infrastructure | 2014
R2 | 500605 | 7644748 | South of the village infrastructure | 2014
R3 | 499022 | 7645610 | East of rehabilitated infrastructure | 2014
5. Department of Science, Information Technology and Innovation and Department of Natural Resources and Mines (2015) Guidelines for Agricultural Land Evaluation in Queensland (Second Edition), State of Queensland or later version. (https://www.publications.qld.gov.au/dataset/qld-agricultural-land-evaluation-guidelines/resource/d6591386-08e2-453f-a6fa-dff2a756215f).
6. Stable as defined in section 111A of the Environmental Protection Act 1994: 111A Meaning of stable condition Land is in a stable condition if— (a) the land is safe and structurally stable; and (b) there is no environmental harm being caused by anything on or in the land; and (c) the land can sustain a PMLU.
7. A suitably qualified person must have qualifications and experience relevant to the work being undertaken and must be a current member of a professional organisation prescribed under Schedule 14 of the Environmental Protection Regulation 2008.
8. Weeds are defined by the Biosecurity Act 2014.

## Improvement Area Milestones
Management milestone | Applicable improvement areas | Milestone criteria
MM1 - Achievement of final landform design | IA1, IA2 | 1. Final void high walls comply with maximum safe and stable slope angles as nominated in geotechnical stability assessment, where:
a. slopes achieve a FoS ≥1.5.
b. Pit high walls achieve a slope ≤70° in competent rock and ≤50° in the weathered horizon.
MM2 - Achievement of surface requirements | IA1, IA2 | 1. Safety bunding constructed around perimeter of the East Hill Pit, with a minimum height of 2 m and constructed of non-dispersive material, or by placing hard barriers .Standard barbed wire fencing, with four barbed wire stands and the use of strainers as required have been erected around the perimeter of the East Hill Pit void to prevent access by humans and livestock.
2. Standard barbed wire fencing, with four barbed wire stands and the use of strainers as required have been erected around the perimeter of the flood protection landform to prevent access to main pit by humans and livestock.
3. Warning signage posted every 100 m around the perimeter of the residual void.
MM3 – Achievement of sufficient improvement | IA1, IA2 | 1. Assessment by an AQP that the water quality and/or level in the void will not cause environmental harm to the surrounding environment:
a. Main Pit – water balance modelling confirms that long-term pit water depth will remain greater than 160 m AHD for the maintenance of a permanent water cover over sulphide material in the pit walls and floor.
b. Main Pit – water quality monitoring downstream of the void:
i. meets the aquatic ecosystem water quality objectives for the Suttor River Sub-basin on three consecutive monitoring occasions; or
ii. where monitoring parameters have exceeded the aquatic ecosystem water quality objectives for the Suttor River Sub-basin, a comparison with water quality at upstream monitoring locations demonstrate that exceedances are not a result of the void water.
c. Main Pit – Groundwater quality monitoring undertaken through the period of rehabilitation establishment (as required by the EA), has indicated no potential impacts to any groundwater values resulting from the void.
d. East Hill Pit – review of the groundwater surface, evaporation rates and groundwater quality monitoring data indicate that there is low risk of environmental harm to groundwater quality values of the Project
2. Hazard and Safety Assessment completed by an AQP1 demonstrates that hazards relating to fencing are of a similar type and not significantly different to hazards in reference sites. As defined in AS/NZS ISO 31000:2018 Risk Management.
3. Assessment by a geotechnical professional concludes that NUMAs are geotechnically stable.
1. Appropriately qualified person means a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods, or literature.