## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Open Cut Pit Areas (Deep Lead Pit)
Total rehabilitation area size (ha) |  |  |  | 18.09
Commencement of first milestone: <insert milestone reference> |  |  |  | 2033-12-31
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2026-12-31 | 2029-01-01 | 2031-01-01 | 2034-01-01 | 2039-01-01
Cumulative area available (ha) | 18.09 | 18.09 | 18.09 | 18.09 | 18.09
Milestone completed by | 2028-12-31 | 2030-12-31 | 2033-12-31 | 2038-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 18.09
RM3 | 18.09
RM8 |  | 18.09
RM9 |  |  | 18.09
RM10 |  |  |  | 18.09
RM11 |  |  |  |  | 18.09

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Waste Rock Dumps
Total rehabilitation area size (ha) |  |  |  | 40.54
Commencement of first milestone: <insert milestone reference> |  |  |  | 2028-12-31
PMLU |  |  |  | Low intensity grazing on native pasture
Date area is available | 2028-12-31 | 2031-01-01 | 2034-01-01 | 2039-01-01
Cumulative area available (ha) | 40.54 | 40.54 | 40.54 | 40.54
Milestone completed by | 2030-12-31 | 2033-12-31 | 2038-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 4.85
RM4 | 4.85
RM8 | 4.85
RM9 |  | 4.85
RM10 |  |  | 4.85
RM11 |  |  |  | 4.85

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Run Of Mine
Total rehabilitation area size (ha) |  |  |  | 2.46
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-31
PMLU |  |  |  | Low intensity grazing
Date area is available | 2026-12-31 | 2029-01-01 | 2032-01-01 | 2037-01-01
Cumulative area available (ha) | 2.46 | 2.46 | 2.46 | 2.46
Milestone completed by | 2028-12-31 | 2031-12-31 | 2036-12-31 | 1941-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 2.46
RM2 | 2.46
RM5 | 2.46
RM8 |  | 2.46
RM9 |  | 2.46
RM10 |  |  | 2.46
RM11 |  |  |  | 2.46

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure Area
Total rehabilitation area size (ha) |  |  |  | 19.33
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-31
PMLU |  |  |  | Low intensity grazing
Date area is available | 2026-12-31 | 2029-01-01 | 2032-01-01 | 2037-01-01 | 2042-01-01 | 2045-01-01 | 2050-01-01
Cumulative area available (ha) | 19.33 | 11.68 | 11.68 | 11.68 | 7.65 | 7.65 | 7.65
Milestone completed by | 2028-12-31 | 2031-12-31 | 2036-12-31 | 1941-12-31 | 2044-12-31 | 2049-12-31 | 2054-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 19.33
RM2 | 19.33
RM5 | 19.33
RM8 |  | 11.68 |  |  | 7.65
RM9 |  | 11.68 |  |  | 7.65
RM10 |  |  | 11.68 |  |  | 7.65
RM11 |  |  |  | 11.68 |  |  | 7.65

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Storages (RAW Dam)
Total rehabilitation area size (ha) |  |  |  | 0.45
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-31
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2026-12-31 | 2031-01-01 | 2036-01-01 | 2041-01-01
Cumulative area available (ha) | 0.45 | 0.45 | 0.45 | 0.45
Milestone completed by | 2030-12-31 | 2035-12-31 | 2040-12-31 | 2045-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.45
RM2 | 0.45
RM6 |  | 0.45
RM8 |  | 0.45
RM9 |  | 0.45
RM10 |  |  | 0.45
RM11 |  |  |  | 0.45

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA6
Relevant activities |  |  | Run Off Dam
Total rehabilitation area size (ha) |  |  | 8.54
Commencement of first milestone: <insert milestone reference> |  |  | 2026-12-31
PMLU |  |  | Water Storage
Date area is available | 2026-12-31 | 2031-01-01
Cumulative area available (ha) | 8.54 | 8.54
Milestone completed by | 2030-12-31 | 2034-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 8.54
RM2 | 8.54
RM12 |  | 8.54

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Tailings Storage Facility
Total rehabilitation area size (ha) |  |  |  | 72.21
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-31
PMLU |  |  |  | Low intensity grazing
Date area is available | 2026-12-31 | 2029-01-01 | 2035-01-01 | 2040-01-01
Cumulative area available (ha) | 72.21 | 72.21 | 72.21 | 72.21
Milestone completed by | 2028-12-31 | 2034-12-31 | 2039-12-31 | 2044-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 72.21
RM7 |  | 72.21
RM8 |  | 72.21
RM9 |  | 72.21
RM10 |  |  | 72.21
RM11 |  |  |  | 72.21

## IA1
Non-use management area (NUMA)
Improvement area |  |  | IA1
Relevant activities |  |  | Open Cut Pit Areas (Pit A, Pit B, and North Pit)
Total size (ha) |  |  | 16.26
Commencement of first milestone: <insert milestone reference> |  |  | 2033-12-31
NUMA |  |  | Residual Void/Non-use management areas
Date area is available | 2026-12-31 | 2031-01-01
Cumulative area available (ha) | 16.26 | 16.26
Milestone completed by | 2030-12-31 | 2035-12-31
Milestone Reference | Cumulative area achieved (ha)
MM1 | 16.26
MM2 | 16.26
MM3 |  | 16.26

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | • All services disconnected • All buildings and associated infrastructure dismantled and removed offsite • All hardstand and concrete areas demolished and removed • Pipelines removed • Waste removed and disposed of within the WRDs or offsite at a licenced waste facility • All road materials removed • All stockpiled material not a part of the PMLU removed • Machinery / equipment not required for rehabilitation removed from site
RM2 | Remediation of contaminated land/sediment | • Contaminated land assessment is completed by a suitably qualified person • Identified contaminated material removed from the mine domain and disposed of either within the TSF or offsite at a licenced facility. • Validation sampling determines that contaminant removal has been successful.
RM3 | Backfill of Deep Lead Pit | • Deep Lead Pit is backfilled with waste rock material to surface level • Landform is shaped to pre-mining landform • Domain is certified by geotechnical engineer to be a safe and stable landform
RM4 | Landform development and reshaping (RA2) | • Landform is shaped to encourage natural drainage and limit erosion. • Target slopes of <70 % are achieved • Maximum of 10 m high lifts • Benches at every 10 m and 10 m wide • <3 % slope on benches. • Domain is certified by geotechnical engineer to be a safe and stable landform
RM5 | Landform development and reshaping (RA3, RA4) | • Landform is shaped to pre-mining landform • Re-establish natural drainage pathways • Landform ripped parallel to landform • Ensure land is free draining Land is free draining
RM6 | Landform development and reshaping (RA6) | • Water removed from dam through evaporation or use on site • Dam walls pushed in and reprofiled to be gently sloping • Landform is shaped to encourage natural drainage and limit erosion • Domain is certified by geotechnical engineer to be a safe and stable landform
RM7 | Landform development and reshaping (RA7) | • Water is removed from TSF through evaporation or other mechanical methods • Waste rock is layered over TSF to 1.0 m thickness • Landform is graded to be free draining, directing water to existing spillway • Topsoil is applied to 0.15 m thickness • Domain is certified by geotechnical engineer to be a safe and stable landform
RM8 | Surface preparation | • Existing soil erosion, rills and gullies repaired prior to seeding • No active gullies >1.0 m depth • Any gullies <1.0 m >0.3m have shown progressive stabilisation (i.e., have become partly stabilised or stabilised) over successive annual monitoring events • A soil health and suitability assessment completed by a SQP and confirms that the soil is suitable for target vegetation establishment or whether there are any requirements for amelioration. • Topsoil placement of a minimum 15 cm • Application of ameliorant where required in the soil health and suitability assessment. • Compacted soil ripped to at least 300 mm
RM9 | Revegetation | • Revegetation strikes creates a groundcover >30% of analogue sites • Seeding rate of 6 – 8 kg/ha achieved (if natural revegetation unsuccessful).
RM10 | Achievement of surface requirements | • Weed species in densities less than 10 % total coverage • Vegetation percentage cover is 50 % of the ground surface area or >70 % of the rehabilitation reference sites for 3 consecutive years. • Groundcover biomass and tree density is equal to, or greater than, 50 % of reference sites for three consecutive years • Species richness is equal to, or greater than, 50% of reference sites for three consecutive years • No active gullies >1.0 m depth • Any gullies <1.0 m >0.3m have shown progressive stabilisation (i.e., have become partly stabilised or stabilised) over successive annual monitoring events • Surface water sites complies with ANZECC/ARMCANZ (2000) livestock drinking water • Stream sediment sites complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low • Groundwater monitoring complies with ANZECC/ARMCANZ (2000) livestock drinking water
RM11 | Achievement of PMLU to a stable condition | • RA has maintained a stable, safe condition. • Vegetation percentage cover is 50 % of the ground surface area or >70 % of the rehabilitation reference sites. • Surface water quality measured at Environmental Authority EPML00557513 surface water sites (Schedule C - Table 1) complies with ANZECC/ARMCANZ (2000) for Livestock Drinking Water Quality for a consecutive two years • Stream sediment at Environmental Authority EPML00557513 sites complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low for a consecutive two years • Groundwater monitoring complies with ANZECC/ARMCANZ (2000) Livestock Drinking Water Quality for a consecutive two years
RM12 | Achievement of PMLU to a stable condition (water storage) | • Dam meets ANZECC/ARMCANZ (2000) for Livestock Drinking Water Quality during biannual sampling events for a consecutive two years.

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Highwall treatment | • IA is certified as safe and stable by a suitably qualified person.
MM2 | Achievement of surface requirements | • All services disconnected • Water management infrastructure removed (i.e., pumps) • Safety bund constructed at 1m high • Fencing of 2m high is erected around the perimeter of the residual void • Warning signage posted every 10m of the perimeter
MM3 | Achievement of sufficient improvement | • IA is certified as safe and stable by a suitably qualified person. • Pit water quality sampling complies with ANZECC/ARMCANZ (2000) for Livestock Drinking Water Quality • Groundwater water quality measured at EA sites complies with ANZECC/ARMCANZ (2000) for Livestock Drinking Water Quality
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones