{"text_format":"2","workbook":"xlsx","n_sheets":9,"sheets":["Instructions","RA1","RA2","RA3","RA4","RA5","RA6","Rehabilitation Area Milestones","RA map"],"not_rendered":{"charts":0,"images":7,"macros":0,"external_links":0,"defined_names":7,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Instructions","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"RA1","index":1,"n_rows":26,"n_cols":21,"rows_kept":26,"cut":false,"hidden":false,"merged":[[0,0,0,10],[2,4,2,10],[3,4,3,10],[4,4,4,10],[5,4,5,10],[4,0,4,3],[5,0,5,3],[1,0,1,3],[1,4,1,10],[2,0,2,3],[3,0,3,3],[9,1,9,10],[25,0,25,10],[22,0,22,10],[23,0,23,10],[24,0,24,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA1"]
["Relevant activities",null,null,null,"Reshaped final landform"]
["Total rehabilitation area size (ha)",null,null,null,266.37]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2024\nRM1"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10"]
["Cumulative area available (ha)",null,8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963,266.37021181721963]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1"]
["RM2"]
["RM3",null,8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963]
["RM4",null,null,8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963]
["RM5",null,null,8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963]
["RM6",{"$nulls":5},8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963]
["RM7",{"$nulls":9},8.8339948879199905,32.559856228239994,78.184017343099995,153.5128569434998,214.5904596638797,261.03572560066664,261.03572560066664,261.03572560066664,261.36794455317965,263.86909167757966,266.37021181721963]
[]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA2","index":2,"n_rows":26,"n_cols":22,"rows_kept":26,"cut":false,"hidden":false,"merged":[[23,0,23,10],[24,0,24,10],[25,0,25,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[22,0,22,10],[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA2"]
["Relevant activities",null,null,null,"Mine Infrastructure"]
["Total rehabilitation area size (ha)",null,null,null,70]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2026\nRM2"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10"]
["Cumulative area available (ha)",null,null,null,0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913,70.012505133548913]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10","2044-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",null,null,null,0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM2",null,null,null,0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM3",null,null,null,0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM4",{"$nulls":4},0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM5",{"$nulls":4},0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM6",{"$nulls":7},0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
["RM7",{"$nulls":11},0.40685893523599997,10.636150094307,32.112789586202005,49.394402273980006,51.657791878799998,57.026180452819439,60.576301908895935,69.318811429987917,69.318811429987917,70.012505133548913]
[]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA3","index":3,"n_rows":26,"n_cols":21,"rows_kept":26,"cut":false,"hidden":false,"merged":[[23,0,23,10],[24,0,24,10],[25,0,25,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[22,0,22,10],[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA3"]
["Relevant activities",null,null,null,"Water Infrastructure"]
["Total rehabilitation area size (ha)",null,null,null,22.1]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2026\nRM1"]
["PMLU",null,null,null,"Retained infrastructure supporting grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10"]
["Cumulative area available (ha)",null,null,null,0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707,22.0996697831707]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",null,null,null,0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM2",null,null,null,0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM3",null,null,null,0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM4",{"$nulls":4},0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM5",{"$nulls":4},0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM6",{"$nulls":7},0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
["RM7",{"$nulls":11},0.91863183301200002,8.3782374848887002,8.3782374848887002,9.3018939947756998,9.3018939947756998,12.7844480872057,17.249746614234699,20.415484686274699,22.0996697831707]
[]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA4","index":4,"n_rows":26,"n_cols":22,"rows_kept":26,"cut":false,"hidden":false,"merged":[[23,0,23,10],[24,0,24,10],[25,0,25,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[22,0,22,10],[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA4"]
["Relevant activities",null,null,null,"Roads and access tracks"]
["Total rehabilitation area size (ha)",null,null,null,30.8]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2027\nRM1"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10"]
["Cumulative area available (ha)",{"$nulls":4},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505,30.834587558875505]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10","2044-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",{"$nulls":4},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM2",{"$nulls":4},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM3",{"$nulls":4},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM4",{"$nulls":5},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM5",{"$nulls":5},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM6",{"$nulls":8},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
["RM7",{"$nulls":12},2.1406645791300001,13.709797138184999,15.497903417370999,16.080354869061001,16.080354869061001,16.080354869061001,16.080354869061001,19.504023755101002,30.834587558875505]
[]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA5","index":5,"n_rows":26,"n_cols":12,"rows_kept":26,"cut":false,"hidden":false,"merged":[[23,0,23,10],[24,0,24,10],[25,0,25,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[22,0,22,10],[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA5"]
["Relevant activities",null,null,null,"Exploration"]
["Total rehabilitation area size (ha)",null,null,null,1.6]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2025\nRM1"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10"]
["Cumulative area available (ha)",null,null,1.57763990733,1.57763990733,1.57763990733,1.57763990733,1.57763990733,1.57763990733,1.57763990733,1.57763990733,1.57763990733]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",null,null,1.57763990733]
["RM2",null,null,1.57763990733]
["RM3",null,null,1.57763990733]
["RM4",null,null,null,1.57763990733]
["RM5",null,null,null,1.57763990733]
["RM6",{"$nulls":6},1.57763990733]
["RM7",{"$nulls":10},1.57763990733]
[]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA6","index":6,"n_rows":26,"n_cols":22,"rows_kept":26,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[23,0,23,10],[24,0,24,10],[25,0,25,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[22,0,22,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA6"]
["Relevant activities",null,null,null,"Southern Void Water Storage"]
["Total rehabilitation area size (ha)",null,null,null,31]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"10/12/2035\nRM1"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","2023-12-10","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10"]
["Cumulative area available (ha)",{"$nulls":12},31,31,31,31,31,31,31,31,31]
["Milestone completed by","2024-12-10","2025-12-10","2026-12-10","2027-12-10","2028-12-10","2029-12-10","2030-12-10","2031-12-10","2032-12-10","2033-12-10","2034-12-10","2035-12-10","2036-12-10","2037-12-10","2038-12-10","2039-12-10","2040-12-10","2041-12-10","2042-12-10","2043-12-10","2044-12-10"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",{"$nulls":12},31]
["RM2",{"$nulls":12},31]
["RM3",{"$nulls":12},31]
["RM4",{"$nulls":13},31]
["RM5",{"$nulls":13},31]
["RM6",{"$nulls":16},31]
["RM7",{"$nulls":20},31]
["RM8",{"$nulls":20},31]
[]
[]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"Rehabilitation Area Milestones","index":7,"n_rows":13,"n_cols":3,"rows_kept":13,"cut":false,"hidden":false,"merged":[[10,0,10,2],[11,0,11,2],[12,0,12,2]]}
["Milestone reference","Rehabilitation milestone","Milestone criteria"]
["RM1","Infrastructure Decommissioning and Removal","a) All services disconnected \nb) All buildings demolished and removed\n"]
["RM2","Remediation of Contaminated Land","a) An AQP has completed a contaminated land investigation.\nb) Contaminated materials removed and appropriately disposed of.  \nc) Onsite remediation of hydrocarbon contaminated soils completed.\nd) Certification from an AQP that all measures required by the contaminated land investigation report(s) are implemented."]
["RM3","Landform Development and Reshaping/Reprofiling","Out of Pit Dumps:\na)\tAll major earthworks completed. \nb)\tGeotechnical adequacy with 1.5 Factor of Safety\nc)\tThe installation of contour or graded drains as per construction design has been certified by an appropriately qualified person. \nd)\tBack-filled pits assessed as geotechnically stable by a suitably qualified geotechnical engineer.\n\ne)\tOuter slopes: \n▪ 15% as per landform design. \n▪ Vertical distance between berms: 20 m \n▪ Berm width: 5 m \n▪ Drainage outward away from void towards original topo drainage paths.\n\nf)\tInner slopes (into full backfill area): \n▪ 12% as per landform design. \n▪ Vertical distance between berms: 20 m \n▪ Berm width: 5 m \n▪ Drainage outward away from void towards original topo drainage paths. \n\nSouthern Void Water Storage:\n▪ Overall slope: 15% \n▪ Vertical distance between berms: 20 m \n▪ Berm width: 5 m \n▪ Final pit walls (Competent material): 70 degrees \n▪ Final pit walls (Incompetent material): 45 degrees \n▪ Underwater slopes: Angle of repose 37 degrees \n▪ Void maximum surface area (31 ha).\n▪ Void maximum depth (105 m). \n▪ Maximum Void lake equilibrium level will not reach 300 m AHD. \n▪ Drainage direction: into the void \n▪ Backfill above the groundwater level (water level based on conceptual modelling).\n▪ Safety bund constructed at 2 m high, base width of 5 m from unweathered, freely draining, end-dumped rockfill at a minimum 20 m offset from the pit perimeter as per the closure plan.\n ▪ Minimised void area and volume based on economic, engineering, geotechnical, geochemical, surface water and groundwater technical reporting outcomes (Condition G8).\n▪ Pit waters are contained such that they do not impact or interact surface or groundwater.\n▪ Design the void as per the void closure plan. "]
["RM4","Surface Preparation (topsoil)","a) Placement of 300 mm of topsoil. \nb) An assessment of soil health and suitability has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment."]
["RM5","Revegetation (grazing)","a) Native or introduced pasture grass seed species used to control erosion at 20 - 25 kg/ha.\nb) Groundcover is 60% perennial pasture biomass for consecutive years."]
["RM6","Achievement of Surface Requirements","a) Soil nutrient concentrations, nutrient cycling and vegetation diversity and cover comparable to reference sites. \nb) Establishment of a mix of perennial grasses suitable for grazing in the area."]
["RM7","Achievement of PMLU to a stable condition (grazing)","a)\tCertification from an appropriately qualified person that the area has achieved stable condition.\nb)\tMaximum erosion rate of <5 t/ha/yr and 10.0 t/ha/yr as determined by landform design. \nc)\tGroundcover is 70% perennial pasture biomass.\nd)\tSurface water quality from the receiving environment is at or below:\n • pH between 6.5 – 8.5\n• Electrical conductivity 720 µS/cm\n• high flow <250 µS/cm\n• Turbidity - 50 NTU\n• Arsenic – 13 µg/L\n• Molybdenum – 0.15mg/L\n• Selenium – 5 µg/L\n• Sulfate - 25 mg/L\n• Suspended Solids - 55 mg/L\ne)\tGroundwater aquifers maintain their pre-mining or reference bore water quality. \nf)\tGroundwater quality as per the water management plan.\ng)\tA contaminated land survey carried out by an appropriately qualified person indicates that no contamination unsuitable for the post-mining land use is occurring. \nh)\tLand Class 4 for grazing. \ni)\t Less than 5% of declared weeds (excluding Parthenium weed- Parthenium hysterophorus)."]
["RM8","Achievement of PMLU to a stable condition (water storage for livestock watering)","a) Water Quality meets the relevant Water Quality Objectives (WQO) Guidelines.\nb) Certification from an appropriately qualified person that the area has achieved stable condition."]
[]
["1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project"]
["2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form."]
["3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones"]

{"sheet":"RA map","index":8,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}