## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## Rehabilitation Area Milestones
PRCP Schedule - Tab 1 Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria | Advice from Progressive Mine and Rehabilitation Closure Planning: Best Practices of Relevance to Mining in Queensland by KBR 2018
RM1 | Infrastructure decommissioning and removal | a) Redundant services (water, electricity, gas, etc.) disconnected b) Asbestos and other hazardous materials removed c) Redundant buildings demolished and removed d) Redundant pipelines decommissioned e) Redundant fencing removed f) Redundant roads decommissioned g) Redundant boreholes decommissioned | Decommissioning (where infrastructure is not required for a future use) should generally be completed within 12 months of becoming available.
RM2 | Infrastructure retention for handover | a) Transfer of ownership agreements in place where infrastructure to be retained
RM3 | Identification and remediation of contaminated land | a) Preliminary site investigation (PSI) completed by an appropriately qualified person (AQP) b) If required, detailed site investigation (DSI) completed by an AQP c) If required, remediation or management of identified contaminated land d) Auditor signoff as per Environmental Protection Act 1994 (EP Act) (Qld), to confirm all contaminated materials have been remediated, or removed and disposed of. e) Removal of land from Contaminated Land Register f) Removal of land from Environmental Management Land Register if feasible
RM4 | Bulk earthworks and general reshaping | a) Construction of landforms completed to achieve design intent as follows: (i) At CM, tri-linear batters (30%, 20% and 10%) used, with 15m lifts above natural surface and 20m lifts below ground where safe and practicable; (ii) At CH and TLO, contemporary slopes less than 20% applied as safe and practicable; (iii) Where exposed coal presents a spontaneous combustion risk as identified by an AQP, it has been managed as per AQP recommendations; and (iv) Reactive material to be placed in line with the site's reactive waste placement strategy (as defined and outlined in the site's most recent Mineral Waste Management Plan). (b) Drainage established to provide erosion and sediment control and create free draining landforms: (i) Bench drains between areas of tri-linear batters; and (ii) Rock lined chutes directing flow from bench drains to receiving environment and/ or final void. (c) Construction verified through survey by an AQP | Landform establishment should generally occur within 12 months of becoming available (or decommissioning, whichever is later) Re-contouring of areas should generally be completed within 12 months of areas becoming available for rehabilitation.
RM5 | Placement of topsoil/growth medium | a) Landform trim completed b) Topsoil/ growth medium placed at a minimum depth of 100mm c) An assessment of soil health and suitability has been completed by an AQP to confirm soil is suitable for target vegetation establishment d) Any amelioration/ fertilisation recommended as a result of the soil assessment have been applied at the recommended rates e) Contour ripping completed after topsoil placement, between 100mm and 500mm | Growth medium development would generally continue over many decades but if this is interpreted to mean only the application of topsoil and initial fertilisation and application of growth medium ameliorants, this should generally occur within 12 months of landform establishment provided that suitable weather and soil moisture conditions are available (in Queensland there are regularly periods of several years in which topsoil application should be delayed due to drought conditions).
RM6 | Seeding | a) Seed mix constitutes target flora species for each PMLU (as described in the site's Revegetation Plan found in Appendix 4.12 of the PRCP), noting a rapidly establishing cover crop species may also be included to act as an effective short term ground cover and bulking agent b) Seed mix applied at a minimum rate of 7kg/ha | Areas should be seeded/planted and fertilised within 12 months of being recontoured provided that suitable weather and soil moisture conditions are available (in Queensland there are regularly periods of several years in which seeding/planting should be delayed due to drought conditions. Note that in these conditions it is preferable that topsoil not be applied to the recontoured landform until shortly before seeding/planting). Areas with a final land use of native grasslands, grazing, agricultural, residential, industrial and some recreation areas should generally be sustainably revegetated within 10 years. Areas with a final land use of forestry or wildlife habitat (including non-grassland native ecosystems) are likely to take at least several decades to achieve a sustainable condition.
RM7 | Water management in the final landform | a) Regulated structures decommissioned b) Dams and diversions decommissioned, relinquished, or licensed where retained c) An AQP has certified that works completed for diversions being retained in the landform have achieved the following objectives: (i) Developing geomorphic and riparian vegetation features similar to those in the local landscape; (ii) Maintaining a sediment transport regime that does not directly impact on upstream and downstream reaches; and (iii) Maintaining equilibrium and functionality that does not require ongoing maintenance
RM8 | Installation of cap on tailings | a) Geotechnical analysis completed by an AQP b) Design review of encapsulation concept, as outlined in the site's most recent Mineral Waste Management Plan, completed by an AQP c) Construction of waste encapsulation completed as per design intent outlined in the site's most recent Mineral Waste Management Plan d) Survey of construction of waste encapsulation completed by AQP e) Shaping of final landform completed
RM9 | Achievement of PMLU to a safe, stable, non-polluting, and self-sustaining condition | a) Monitoring and maintenance program implemented as per the Manual and GCAA Completion Criteria and Rehabilitation Monitoring Procedure (the Procedure) with results meeting the completion criteria outlined in the site’s Rehabilitation Management Plan and Rehabilitation Report Card process. b) Certification from an AQP that the area has achieved stable condition, as defined by the Environmental Protection Act 1994 (EP Act) (Qld) c) Groundwater modelling completed by an AQP to confirm the final void is acting as a sink, and understand steady state groundwater level rebound d) Certification from an AQP that the groundwater quality will not cause environmental harm to the surrounding environment e) Seepage assessment completed for the tailings areas to confirm if any seepage is being generated, and if seepage is occurring it is moving towards and contained in the final void (i.e., not being transported to, and accumulating in, the receiving environment) f) Certification from an AQP that surface water quality will not cause environmental harm to the surrounding environment g) Certification from an AQP that adequate vegetation has established and is both healthy and appropriate for the PMLU, as per the completion criteria outlined in the site’s Rehabilitation Management Plan, and weed/pest species abundance in rehabilitated areas is no greater than that found at appropriate reference sites.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones
There's a SMART way to write management goals and objectives, and the criteria should reflect how the goals/ objectives are SMART. Importantly, it should be understood that not every objective writtten will have all five criteria, particularly for long term goals, as being SMART lacks flexibility. It is the combination of the objective and its action plan that is really important. However focus on these areas will help improve the chances of successfully achieving a goal/ objective.
Specific | What are you trying to do and why? Target a specific area for improvement
Measurable | How will you measure what you are doing? Quantify (or at least suggest) an indicator of progress
Attainable | With the tools/ resources you have can you reach the goal/ objective? Specify who will do it
Realistic | Can you actually meet the goals you are setting forth? State what results can be realistically achieved given available resources
Timely | What is the timeline to meet your goals. Specify when the result can be achieved
Evaluated | Appraisal of a goal to assess the extent to which it has been achieved
Reviewed | Reflection and adjustment of your approach or behaviour to reach a goal
The last two items have been included in later years, and are addressed through the development and implementation of a monitoring and maintenance program for the Schedule
Note on D2: ***: Think we also need to highlight/ be clear on what evidence will be suitable for demonstrating milestone criteria are met - and try and link back into existing processes (i.e. RRC) THIS LAST COLUMN TO BE REMOVED FROM FINAL DOCUMENT (I.E. FOR DRAFT SUBMISSION)

## Improvement Area Milestones
PRCP Schedule - Tab 2 Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Highwall treatment | a) Low wall treatment completed, including: (i) Low wall reshaped to 20m high tri-linear slope design; (ii) Bench drains are constructed and established between tri-linear slopes; and (iii) Rock lined chutes direct flow from bench drains to void floor. (b) Western wall treatments completed, including lay back of weathered zone on upper wall as advised by RPEQ (c) Western, eastern and southern wall buttressed with rock if advised by RPEQ; (d) Southern landform has Gowrie Creek levee bulked out to create permanent land form with final void flood immunity for events up to 0.1%AEP.
MM2 | Achievement of surface requirements | a) Warning signage around the final void rim placed to warn of the void related risks and deter public access b) An abandonment bund constructed and established on western wall and at high-risk locations.
MM3 | Achievement of sufficient improvement | a) Certification by AQP that void will: (i) Continue to act as a sink; (ii) Not cause harm outside of tenure boundaries; and (iii) Vegetation is established on reshaped spoil where practicable
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1 - Residual Void NUMA
Relevant activities |  |  |  | Open cut mining/ Void
Total size (ha) |  |  |  | 400 ha
Commencement of first milestone: MM1 |  |  |  | 2028-12-31
NUMA |  |  |  | Residual Void
Date area is available | 2028-12-31 | 2029-12-31 | 2030-12-31
Cumulative area available (ha) | 150 | 300 | 400
Milestone completed by | 2029-12-31 | 2030-12-31 | 2031-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
MM1 | 150 | 300 | 400
MM2 | 150 | 300 | 400
MM3 |  |  |  | 400
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 - Waste Rock Dump (WRD) Includes: All North West (NW) WRD (360 dump) and southern face of NWRD, South West (SW) WRD, South East (SE) WRD at CM, and WRD and tailings area requiring earthworks/rehabilitation at Cement Hill.
Relevant activities |  |  |  | Rehabilitation of out-of-pit waste rock dump areas.
Total rehabilitation area size (ha) |  |  |  | 1101.07ha (501.77 ha of existing rehabilitation)
Commencement of first milestone: RM1 |  |  |  | 2022-07-31
PMLU |  |  |  | Woodland and Light Grazing
Date area is available | 2022-07-31 | 2023-07-31 | 2025-07-31 | 2026-07-31 | 2027-07-31 | 2027-12-31 | 2029-12-31 | 2030-12-31 | 2031-12-31 | 2032-12-31 | 2033-12-31
Cumulative area available (ha) | 584.765 | 584.765 | 634.765 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065 | 1101.065
Milestone completed by | 2022-12-31 | 2023-12-31 | 2025-12-31 | 2026-12-31 | 2027-12-31 | 2028-12-31 | 2030-12-31 | 2031-12-31 | 2032-12-31 | 2033-12-31 | 2034-12-31 | 2043-12-31
Milestone Reference | 2022-12-31: Cumulative area achieved (ha)
RM1 | 584.765 | 584.765 | 634.77 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065 | 1101.065
RM4 | 584.765 | 584.765 | 634.765 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065 | 1101.065
RM5 | 534.765 | 584.765 | 584.765 | 584.765 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065
RM6 | 534.765 | 584.765 | 584.765 | 584.765 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065
RM7 | 534.765 | 584.765 | 584.765 | 584.765 | 684.765 | 792.235 | 792.235 | 893.155 | 1027.335 | 1027.335 | 1101.065
RM9 | 2043-12-31: 1101.065
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2022-12-31 to 2033-12-31
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2022-12-31 to 2033-12-31
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2022-12-31 to 2033-12-31
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2022-12-31 to 2033-12-31

## CCO List of RAs & IAs (hidden)
Location | Site Feature | Schedule ID | PMLU | Area Description | Area (Ha)
CM | Northern Waste Rock Dump | RA1 | Woodland Habitat | Northern WRD - Slopes | 303.2589
CM | Northern Waste Rock Dump | RA1 | Woodland Habitat | NWRD - Southern Face Trilinear | 52.9579
CM | Northern Waste Rock Dump | RA2 | Woodland Habitat & Light Grazing | 360 Plateau | 197.4922
CM | Megacell Area | RA3 | Woodland Habitat | Megacells | 51.5345
CM | South-West Rock Dump | RA4 | Woodland Habitat | SWRD Slopes (& Surrounds) | 55.9698
CM | South-West Rock Dump | RA4 | Woodland Habitat | SWRD Slopes (& Surrounds) | 42.6985
CM | South-West Rock Dump | RA5 | Woodland Habitat & Light Grazing | SWRD Top/Plateau | 16.8685
CM | South-East Waste Rock Dump | RA6 | Woodland Habitat | SEWRD - Slopes (no top due to spine design, also check western footprint) | 36.7332
CM | Natural Surface Interface | RA7 | Woodland Habitat & Light Grazing | OOPWRD - Natural Surface Interface | 107.1063
CM | Natural Surface Interface | RA7 | Woodland Habitat & Light Grazing | Decomm Infrastructure? - ROM Pad area | 18.8944
CM | In-Pit Slopes | RA8 | Woodland Habitat | In Pit Slope - Aligned to Max Void Footprint for PRCP | 267.5408
CM | Residual Void | IA1 | No Use | Anticipated Maximum "Void" Footprint for PRCP | 306.7752
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infra - Brine Pond | 3.4327
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infra - Main access tracks & car park | 26.0066
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infra - Powerlines | 11.013
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Buildings (Admin, Warehouse, Production) | 5.8283
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - CHPP, ROM & Surrounds | 12.0603
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Dirty water chamber of IAD | 5.4315
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Fuel Bay & Surrounds | 6.0254
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - CM Mine Water Dam | 22.4933
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Mob Workshop & Laydown | 2.7603
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Process Water Dam & Surrounds | 7.2108
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Striker Crusher Pad? & Laydown area | 10.5324
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - SWRD Sed Dam | 10.4194
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Village | 10.6429
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrastructure - Workshop & Surrounds (Tyre, Wash Bay etc) | 6.2898
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Decomm Infrstructure - Raw Water Dam & Surrounds | 3.1576
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Minor Disturbance - HV Truck Parkup | 7.0116
CM | Infrastructure Areas | RA9 | Woodland Habitat & Light Grazing | Minor Disturbance - CM Laydown Area (Pump Crew) | 6.0659
CM | Infrastructure Areas | RA10 | Water Management | Decomm Infrastructure - Western Diversion Drain | 31.2583
CM | Infrastructure Areas | RA10 | Water Management | Retained Infrastructure - Gowrie Ck Diversion | 71.0867
CM | Infrastructure Areas | RA10 | Water Management | Decomm Infrastructure - Eastern Diversion Drain | 43.9529
CM | Infrastructure Areas | RA10 | Water Management | Retained Infrastructure - Gowrie Ck Diversion | 48.0839
CM | Infrastructure Areas | RA10 | Water Management | Decomm/Retained Infrastructure? - Clean water bypass for IAD | 2.9962
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastrcture - Road (Highway) within OLC ML | 0.73584
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastrcture - Road (Highway) | 0.23787
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastructure - Road (Highway) | 13.7471
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastructure - Road (Highway) | 19.0087
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastructure - Road (Highway) | 23.4134
CM | Infrastructure Areas | RA11 | Retained Infrastructure | Retained Infrastrcture - Wolfang Homestead | 6.3512
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 9.7265
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 16.6041
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 0.30675
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 17.2226
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 56.7911
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 34.8216
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 17.8249
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 22.1359
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM | 24.4334
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed - CM & TS Stockpile | 112.6575
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed/Minor Disturbance - CM & TS Stockpile | 44.9783
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed/Minor Disturbance - CM - Road | 37.4624
CM | Undisturbed Areas/ Vegetation | RA12 | Woodland Habitat & Light Grazing | Undisturbed/Minor Disturbance - CM - Tracks etc | 16.3037
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 136.6147
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 159.3223
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 28.4123
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 4.1627
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 61.5141
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 74.849
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 116.8715
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed - CM | 96.9318
CM | Undisturbed Areas/ Vegetation | RA13 | Woodland Habitat | Undisturbed/Minor Disturbance - CM Laydown areas (contam??) | 36.5514
CM | Offset Areas | RA14 | Nature Conservation | BCP Area | 24.7805
CM | Offset Areas | RA14 | Nature Conservation | BCP Area | 7.1631
CM | Offset Areas | RA14 | Nature Conservation | Bluegrass Offset Area | 43.3529
CM | Offset Areas | RA14 | Nature Conservation | Bluegrass Offset Area | 79.899
CM | Overland Conveyor | RA15 | Woodland Habitat & Light Grazing | Decomm Infrastructure - OLC within CM ML | 10.9514
CM | Overland Conveyor | RA15 | Woodland Habitat & Light Grazing | Decomm Infrastructure - OLC | 24.7027
CM | Overland Conveyor | RA15 | Woodland Habitat & Light Grazing | Decomm Infrastructure - OLC within TLO ML | 14.9509
CH
TLO
TOTAL OF 109 ROWS

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 - CM Tailings
Relevant activities |  |  |  | Rehabilitation of tailings areas including Megacell area and Settling Cells at CM
Total rehabilitation area size (ha) |  |  |  | 59.94ha
Commencement of first milestone: RM1 |  |  |  | 2027-12-31
PMLU |  |  |  | Woodland & Light Grazing
Date area is available | 2027-07-31 | 2027-12-31 | 2034-12-31
Cumulative area available (ha) | 42.53 | 42.53 | 59.94
Milestone completed by | 2027-12-31 | 2028-12-31 | 2035-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 42.53 | 42.53 | 59.94
RM4 | 42.53 | 42.53 | 59.94
RM8 | 42.53 | 42.53 | 59.94
RM5 |  | 42.53 | 59.94
RM6 |  | 42.53 | 59.94
RM7 |  | 42.53 | 59.94
RM9 |  |  |  | 59.94
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 - Infrastructure to be removed
Relevant activities |  |  |  | All Infrastructure Removed
Total rehabilitation area size (ha) |  |  |  | 568.47 (29.04 ha of existing rehabilitation)
Commencement of first milestone: RM1 |  |  |  | 2022-12-31
PMLU |  |  |  | Woodland & Light Grazing
Date area is available | 2022-12-31 | 2023-12-31 | 2030-12-31 | 2031-12-31 | 2032-12-31 | 2033-12-31 | 2034-12-31
Cumulative area available (ha) | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47 | 568.47
Milestone completed by | 2023-12-31 | 2024-12-31 | 2031-12-31 | 2032-12-31 | 2033-12-31 | 2034-12-31 | 2035-12-31 | 2043-12-31
Milestone Reference | 2023-12-31: Cumulative area achieved (ha)
RM1 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47 | 568.47
RM3 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47 | 568.47
RM4 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47 | 568.47
RM5 | 29.04 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47
RM6 | 29.04 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47
RM7 | 29.04 | 79.04 | 79.04 | 144.86 | 264.99 | 373.85 | 568.47
RM9 | 2043-12-31: 568.47
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 - Water Management Areas
Relevant activities |  |  |  | Gowrie Creek Diversion (CM), Residual Void (CH), West Dam, Northern Boundary and Eastern Diversions (TLO)
Total rehabilitation area size (ha) |  |  |  | 148.18
Commencement of first milestone: RM1 |  |  |  | 2021-12-31
PMLU |  |  |  | Water Management
Date area is available | 2021-12-31 | 2024-12-31 | 2032-12-31
Cumulative area available (ha) | 7 | 97 | 148.18
Milestone completed by | 2022-12-31 | 2025-12-31 | 2033-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
RM1 | 7.28 | 97 | 148.18
RM2 | 7.28 | 97 | 148.18
RM4 | 7.28 | 97 | 148.18
RM5 | 7.28 | 97 | 148.18
RM6 | 7.28 | 97 | 148.18
RM7 | 7.28 | 97 | 148.18
RM9 |  |  |  | 148.18
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA5 - TLO Waste Rock Dumps (WRDs)
Relevant activities |  |  | Historic BA/TLO - Rehabilitation completed from 1980s to 2000s
Total rehabilitation area size (ha) |  |  | 141.06ha (112.37 ha of existing rehabilitation )
Commencement of first milestone: RM1 |  |  | 2032-12-31
PMLU |  |  | Woodland & Light Grazing
Date area is available | 2032-12-31
Cumulative area available (ha) | 141.06
Milestone completed by | 2033-12-31 | 2043-12-31
Milestone Reference | Cumulative area achieved (ha)
RM4 | 141.06
RM5 | 141.06
RM6 | 141.06
RM7 | 141.06
RM9 |  | 141.06
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA1- PY (hidden)
All anticipated disturbance areas to require rehab methodology including earthworks. Including all mining areas plus ancillary disturbance which is not just infrastructure removal, decomm
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 26 | Woodland & Light Grazing | RA1 | Historic tailings cells - CH | 8.063
| 27 | Woodland & Light Grazing | RA1 | Western Side of Highwall - CH | 3.5924
| 28 | Woodland & Light Grazing | RA1 | Historic Southern Out of Pit Dumps - CH | 9.1988
| 29 | Woodland & Light Grazing | RA1 | Southern Out of Pit Dumps - Small Satellite Dump - CH | 0.74047
| 49 | Woodland & Light Grazing | RA1 | In-pit slope to east - CM | 20.1113
| 50 | Woodland & Light Grazing | RA1 | In-pit slopes to the north - CM | 140.851
| 52 | Woodland & Light Grazing | RA1 | 360 Plateau - CM | 207.4396
| 53 | Woodland & Light Grazing | RA1 | OOPWRD - IPCC Module Laydown Area (Incorporate into southern landform) | 11.4646
| 65 | Woodland & Light Grazing | RA1 | SWRD Slopes (& Surrounds) - CM | 108.6226
| 66 | Woodland & Light Grazing | RA1 | SWRD Plateau - CM | 11.5533
| 86 | Woodland & Light Grazing | RA1 | Northern Waste Rock Dump - Eastern Slope & Decomm Infrastructure - Easrtern GO Line - CM | 5.613
| 87 | Woodland & Light Grazing | RA1 | Northern Waste Rock Dump - Eastern Slope - CM | 295.4967
| 88 | Woodland & Light Grazing | RA1 | Northern Waste Rock Dump - Eastern Slope & Decomm/ Retained? Infrastructure - Truck Dump Hopper - CM | 17.2419
| 90 | Woodland & Light Grazing | RA1 | OOPWRD - Southern Levee/ Landorm - CM | 18.2997
| 111 | Woodland & Light Grazing | RA1 | NWRD - Southern Face Trilinear (need to check alignment with final landform) - CM | 50.8648
| 112 | Woodland & Light Grazing | RA1 | OOPWRD - Natural Surface Interface - CM | 109.9969
| 114 | Woodland & Light Grazing | RA1 | SEWRD - Slopes (no top due to spine design, also check western footprint) - CM | 36.4485
|  |  |  | Total | 1055.5986

## RA2 - PY (hidden)
RA2 - Tailings areas including megacell
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 22 | Woodland & Light Grazing | RA2 | Decomm Infrastructure - Tailings Storage/ Drying Cells | 5.8638
| 25 | Woodland & Light Grazing | RA2 | Megacells | 42.6844
|  |  |  | Total | 48.5481

## RA3 - PY (hidden)
RA3 - All infrastructure removed
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 0 | Woodland & Light Grazing | RA3 | Minor Disturbance - TS Stockpile - CM | 45.1565
| 13 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Village - CM | 12.5283
| 14 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Main access tracks & car park - CM | 14.8892
| 15 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Western Diversion Drain - CM | 25.7932
| 16 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Raw Water Dam & Surrounds - CM | 4.6611
| 17 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Buildings (Admin, Warehouse, Production) - CM | 6.2921
| 18 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Process Water Dam & Surrounds - CM | 4.7014
| 21 | Woodland & Light Grazing | RA3 | Decomm/Retained Infrastructure? - Clean water bypass for IAD - CM | 1.8483
| 22 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - CHPP, ROM & Surrounds - CM | 10.643
| 23 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - ROM Pad area - CM | 24.4793
| 25 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - CH Mine Infrastructure Area - CM | 6.5359
| 32 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Stockpile Facilities - TLO | 23.2952
| 33 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Laydown Area - TLO | 3.4408
| 42 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Main Access Road - TLO | 13.1499
| 48 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - OLC - CM | 7.4341
| 54 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Heavy Equipment Laydown Area - CM | 3.2116
| 55 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Mob Workshop & Laydown - CM | 3.2264
| 57 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Fuel Bay & Surrounds - CM | 2.442
| 59 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Mine Water Dam - CM | 23.3907
| 60 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - CHPP Workshop - CM | 1.5106
| 61 | Woodland & Light Grazing | RA3 | Decomm infrastructure - HV Truck Parkup - CM | 5.6503
| 62 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Workshop & Surrounds (Tyre, Wash Bay etc) - CM | 6.3519
| 63 | Woodland & Light Grazing | RA3 | DEcomm Infrastructure - Laydown Area (Pump Crew) - CM | 3.5311
| 64 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Brine Pond - CM | 4.4378
| 67 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Powerlines - CM | 9.2283
| 68 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - SWRD Sed Dam - CM | 14.7301
| 70 | Woodland & Light Grazing | RA3 | Decomission Infrastructure - Powerline - CM | 19.7565
| 78 | Woodland & Light Grazing | RA3 | Minor Disturbance - TS Stockpile - CM | 43.5266
| 82 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Henwha explovies yard - CM | 1.2654
| 83 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Henwha magazine - CM | 1.4006
| 84 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Light Vehicle Fuelbay and Washdown - CM | 1.0632
| 85 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - TS Stockpile - CM | 1.4749
| 89 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - TS Stockpile - CM | 16.3905
| 91 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Laydown Area - CM | 9.5394
| 95 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Spoil Access Road - TLO | 5.2166
| 96 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Load Plant - TLO | 3.0133
| 97 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - ROM - TLO | 1.3119
| 98 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Buildings, Water Fill Point, Conveyor - TLO | 11.3868
| 99 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Water Treatment Plant - TLO | 2.3209
| 101 | Woodland & Light Grazing | RA3 | Loading Yard - TLO | 1.0542
| 102 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Sediment Dam - CM | 13.4373
| 103 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Old Rail and Pipeline - TLO | 2.3542
| 104 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - OLC | 25.5709
| 105 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Western/Rail Loop Diversion - TLO | 5.6861
| 106 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - TLO | 9.9875
| 109 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - OLC - TLO | 15.4398
| 116 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Eastern Diversion Drain - CM | 31.1737
| 119 | Woodland & Light Grazing | RA3 | Laydown areas - CM | 7.0181
| 120 | Woodland & Light Grazing | RA3 | Geology Laydown Area - CM | 6.7417
| 121 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Dirty water chanmber of IAD - CM | 5.3503
| 122 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Old Peaks Down Highway - CM | 2.5313
| 123 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Access Tracks - TLO | 4.2659
| 124 | Woodland & Light Grazing | RA3 | Decomm Infrastructure - Powerlines/ tracks/ borrow pit | 1.8241
532.6607

## RA4 - PY (hidden)
RA4 - All Infrastructure to be Retained
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 35 | Water Management | RA4 | Retained Infrastructure - West Dam (Clean Water) - TLO | 26.5068
| 40 | Water Management | RA4 | Retained Infrastructure - Eastern Diversion Drain - TLO | 9.2938
| 75 | Water Management | RA4 | Retained Water Management - Gowrie Creek Diversion - CM | 90.1619 | *Difference in polygons PMLU and ARCP Layer
| 118 | Water Management | RA4 | Residual Void & Surrounds - CH | 6.6194
|  |  |  | Total | 132.5818

## RA5 - PY (hidden)
RA10 - Historical Rehabilitation Areas
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 101 | Woodland & Light Grazing | RA5 | Historic BA/TLO - Rehabilitation completed from 1980S to 2000s | 139.2875

## RA6 - PY (hidden)
FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
6 | Retained Infrastructure | RA6 | retained Historical Area - Wolfang Homestead - CM | 10.9612
19 | Retained Infrastructure | RA6 | Retained Infrastructure - Road (Highway) - CM | 16.4084
69 | Retained Infrastructure | RA6 | Retained Infrastructure - Powerline Easement - CM | 2.185
71 | Retained Infrastructure | RA6 | Retained Infrastructure - Road (Highway) - CM | 12.3383
72 | Retained Infrastructure | RA6 | Retained Infrastructure - Powerline Easement - CM | 7.5329
77 | Retained Infrastructure | RA6 | Retained Infrastructure - Road (Highway) - CM | 29.8866
92 | Retained Infrastructure | RA6 | Undisturbed - Old Mining Shafts (with 20m buffer) - CM | 5.7571
107 | Retained Infrastructure | RA4 | Retained Infrastructure - Rail Loop (Handover to Aurizon, check if actually within ML or not??) - TLO | 22.6486 | moved from RA4
107.718

## R7 - PY (hidden)
FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
94 | Grazing & Cropping | RA7 | Decomm Infrastructure - TS Stockpile - TLO | 4.3039
4.3039

## RA8 - PY (hidden)
RA8 - Nature Conservation
| FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
| 8 | Nature Conservation | RA8 | Undisturbed - BCP Area - CM | 8.5233
| 76 | Nature Conservation | RA8 | Bluegrass Offset Area - CM | 144.7496
|  |  |  | Total | 153.2729

## RA9 - PY (hidden)
FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
41 | Retained Infrastructure | RA9 | Retained Infrastructure - Rail Line - TLO | 2.1052

## RA10 - PY (hidden)
FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
47 | Woodland & Light Grazing | RA10 | Earthworks - West Dam Landform Bulking - TLO (does this need to be retained?) | 3.9492

## Undisturbed - PY (hidden)
FID | PMLU_Type | Area_ID | Descriptio | Area__ha_
1 | Woodland & Light Grazing |  | Undisturbed - Wolfang - CM | 69.9284
2 | Woodland & Light Grazing |  | Undisturbed/Minor Disturbance - Highway - CM | 7.1311
3 | Woodland & Light Grazing |  | Undisturbed - CM | 34.1371
4 | Woodland & Light Grazing |  | Undisturbed - CM | 34.9614
5 | Woodland |  | Undisturbed - CM | 223.3269
7 | Woodland & Light Grazing |  | Undisturbed/ Minor Disturbance - BCP Area - CM | 26.1074
9 | Woodland & Light Grazing |  | Undisturbed - CM | 10.7416
10 | Woodland & Light Grazing |  | Undisturbed - CM | 85.3011
11 | Woodland |  | Undisturbed - CM | 71.1687
12 | Woodland |  | Undisturbed - CM | 97.3029
30 | Woodland & Light Grazing |  | Undisturbed - Existing Drainage Channel - CH | 0.66162
31 | Grazing & Cropping |  | Undisturbed - TLO | 5.8621
34 | Woodland |  | Historic West Dam Catchment (Bath Creek?) - TLO | 31.7964
36 | Woodland |  | Undisturbed - TLO | 57.7307
37 | Woodland |  | Undisturbed - TLO | 6.6827
38 | Woodland |  | Undisturbed - TLO | 71.3517
39 | Grazing & Cropping |  | Undisturbed - TLO | 2.4802
43 | Woodland & Light Grazing |  | Undisturbed - TLO | 10.1266
44 | Woodland |  | Undisturbed - TLO | 76.9088
45 | Woodland |  | Undisturbed - TLO | 22.7923
46 | Woodland |  | Undisturbed - TLO | 13.3297
51 | Woodland & Light Grazing |  | Undisturbed - Gowrie Ck (old channel, original flowpath) - CM | 5.4592
56 | Woodland & Light Grazing |  | Undisturbed/ Minor Disturbance - Laydown areas - CM | 29.7814
58 | Woodland & Light Grazing |  | Undisturbed - CM | 13.8859
73 | Retained Infrastructure |  | Minor Disturbance/ Retained Infrastructure - Stock Route - CM | 44.9356
74 | Woodland |  | Undisturbed - CM | 28.8375
79 | Retained Infrastructure |  | Undisturbed - Stock Route and Water Tanks - CM | 2.4258
80 | Woodland |  | Undisturbed - CM | 1.1427
81 | Woodland |  | Undisturbed - Grave Ste - CM | 0.38051
93 | Woodland |  | Undisturbed - CM | 119.8172
108 | Woodland & Light Grazing |  | Undisturbed/ Minor Disturbance only (Tracks) - TLO | 47.3241
110 | Woodland & Light Grazing |  | Undisturbed - CM | 22.2482
115 | Woodland & Light Grazing |  | Undisturbed - CM | 35.795
117 | Woodland & Light Grazing |  | Undisturbed - CM | 22.8126
1334.6752