## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Mining and Mine Dump Areas
Total rehabilitation area size (ha) |  |  |  | 4314.5916
Commencement of first milestone: RM1 |  |  |  | 2023
PMLU |  |  |  | Grazing
Date area is available | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078
Cumulative area available (ha) | 745.518 | 1151.479 | 1151.479 | 1151.479 | 1229.138 | 1537.697 | 1786.782 | 1786.782 | 2212.299 | 2775.694 | 4269.226 | 4314.59 | 4314.59 | 4314.59 | 4314.59 | 4314.59
Milestone completed by | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078
Milestone Reference | Cumulative area achieved (ha)
RM1 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM2 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM3 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM5 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM6 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM9 | 745.518 | 842.6606 | 942.7917 | 1032.6891 | 1085.054 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916 | 4314.5916
RM12 | [5 empty] | 745.518 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979 | 4314.5916 | 4314.5916 | 4314.5916
RM15 | [8 empty] | 745.518 | 1145.1687 | 1451.9642 | 1786.7832 | 2212.2993 | 2775.6942 | 3440.9929 | 3884.6979
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activtiies |  |  |  | Creek diversions & levees
Total rehabilitation area size (ha) |  |  |  | 137.146
Commencement of first milestone: RM1 |  |  |  | 2023
PMLU |  |  |  | Watercourse
Date area is available | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068
Cumultive area available (ha) | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
Milestone completed by | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068
Milestone reference | Cumulative area achieved (ha)
RM1 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM2 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM3 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM5 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM7 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM10 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM13 | [5 empty] | 137.1453 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146 | 137.146
RM16 | [9 empty] | 137.146 | 137.146 | 137.146 | 137.146 | 137.146

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activtiies |  |  |  | Mine Infrastructure
Total rehabilitation area size (ha) |  |  |  | 547.698
Commencement of first milestone: RM1 |  |  |  | 2038
PMLU |  |  |  | Grazing
Date area is available | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113
Cumultive area available (ha) | 0 | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
Milestone completed by | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098
Milestone reference | Cumulative area achieved (ha)
RM1 |  | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM2 |  | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM3 |  | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM6 |  | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM9 |  | 219.302 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM12 |  |  | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
RM15 |  |  |  |  | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698 | 547.698
`

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activtiies |  |  |  | Mineral residue areas
Total rehabilitation area size (ha) |  |  |  | 198.958
Commencement of first milestone: RM1 |  |  |  | 2048
PMLU |  |  |  | Cattle Grazing
Date area is available | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108
Cumultive area available (ha) |  | 56.551 | 161.688 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
Milestone completed by | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108
Milestone reference | Cumulative area achieved (ha)
RM1 |  | 56.551 | 161.688 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM3 |  |  | 57 | 162 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM4 |  |  |  | 57 | 162 | 199 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM6 |  |  |  |  | 57 | 162 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM9 |  |  |  |  | 57 | 162 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM12 | [5 empty] | 57 | 162 | 162 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958 | 198.958
RM15 | [7 empty] | 57 | 162 | 199 | 199 | 198.958 | 198.958 | 198.958

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activtiies |  |  |  | Native ecosystem corridor
Total rehabilitation area size (ha) |  |  |  | 35.079
Commencement of first milestone: RM1 |  |  |  | 2028
PMLU |  |  |  | Native ecosystem
Date area is available | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093
Cumultive area available (ha) | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
Milestone completed by | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093
Milestone reference | Cumulative area achieved (ha)
RM1 | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM2 | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM3 | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM8 | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM11 | 17 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM14 |  |  | 17.373 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079 | 35.079
RM17 |  |  |  |  | 17.373 | 17.373 | 17.373 | 17.373 | 17.373 | 17.373 | 35.079 | 35.079 | 35.079 | 35.079

## IA1
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA1 (Far South)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 53.997
Commencement of first milestone: MM1 |  |  |  | 2033
PMLU |  |  |  | NUMA
Date area is available | 2024 | 2025 | 2026 | 2027 | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073
Cumultive area available (ha) | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997
Milestone completed by | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997
MM2 |  |  | 54 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997
MM3 |  |  |  | 53.997 | 54 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997 | 53.997

## IA2
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA2 (Carlo Creek)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 45.797
Commencement of first milestone: MM1 |  |  |  | 2033
PMLU |  |  |  | NUMA
Date area is available | 2024 | 2029 | 2034 | 2039 | 2044 | 2049 | 2054 | 2059 | 2064 | 2069 | 2074 | 2079 | 2084 | 2089
Cumultive area available (ha) | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797
Milestone completed by | 2028 | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797
MM2 |  |  | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797
MM3 |  |  |  | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797 | 45.797

## IA3
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA3 (One Tree)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 93.796
Commencement of first milestone: MM1 |  |  |  | 2038
PMLU |  |  |  | NUMA
Date area is available | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098
Cumultive area available (ha) | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796
Milestone completed by | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796
MM2 |  |  | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796
MM3 |  |  |  | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796 | 93.796

## IA4
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA4 (Pipeline)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 89.296
Commencement of first milestone: MM1 |  |  |  | 2038
PMLU |  |  |  | NUMA
Date area is available | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098
Cumultive area available (ha) | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296
Milestone completed by | 2033 | 2038 | 2043 | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296
MM2 |  |  | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296
MM3 |  |  |  | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296 | 89.296

## IA5
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA5 (Fox Plains)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 185.499
Commencement of first milestone: MM1 |  |  |  | 2053
PMLU |  |  |  | NUMA
Date area is available | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113
Cumultive area available (ha) | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499
Milestone completed by | 2048 | 2053 | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499
MM2 |  |  | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499
MM3 |  |  |  | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499 | 185.499

## IA6
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA6 (Eagles Nest)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 187.302
Commencement of first milestone: MM1 |  |  |  | 2053
PMLU |  |  |  | NUMA
Date area is available | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113 | 2118 | 2123
Cumultive area available (ha) | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302
Milestone completed by | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113 | 2118 | 2123
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302
MM2 |  |  | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302
MM3 |  |  |  | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302 | 187.302

## IA7
Non-use management area (NUMA)
Rehabilitation area |  |  |  | IA7 (WC Pit)
Relevant activtiies |  |  |  | Open cut mining / void
Total rehabilitation area size (ha) |  |  |  | 75
Commencement of first milestone: MM1 |  |  |  | 2063
PMLU |  |  |  | NUMA
Date area is available | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113 | 2118 | 2123
Cumultive area available (ha) | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597
Milestone completed by | 2058 | 2063 | 2068 | 2073 | 2078 | 2083 | 2088 | 2093 | 2098 | 2103 | 2108 | 2113 | 2118 | 2123
Milestone reference | Cumulative area achieved (ha)
MM1 |  | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597
MM2 |  |  | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597
MM3 |  |  |  | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597 | 74.597

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) All services disconnected. Underground services remain buried and surface points sealed. b) All buildings either demolished and removed or relocated off the mining leases. c) Concrete slabs and footings removed or buried within overburden dump final rehabilitation areas. d) Sumps or dams that do not form part of final landform as sediment control structures dewatered and where applicable contaminated silt removed for licensed disposal. e) Sealed asphalt roads, car parks and hardstand areas will have the asphalt removed for reuse off the mining leases or removed for licensed disposal. f) Mine water dams are decommissioned. g) Watercourse crossings and culverts removed.
RM2 | Remediation and/or management of contaminated land | a) Hydrocarbon and chemical storage areas removed and/or remediated by on-site treatment, if required. b) Contaminated Land Investigation Document completed in accordance with the Environmental Protection Act 1994, including: c) Site Suitability Statement confirming the suitability of the property for the PMLUs d) Audit Certification e) Contaminated Land Investigation Document including a Site Investigation Report and, where required, a Validation Report and/or a draft Site Management Plan
RM3 | Landform development and reshaping | a) Landforms reshaped maximum 10% slopes (coarse reject) (RA4) b) Landforms requiring reshaping are reshaped to be free-draining with maximum 17% slopes (RA1, RA3; RA5) c) Disturbed natural watercourse bed and banks returned to a profile similar to the pre-disturbance condition (RA2)
RM4 | Installing Cover Systems/Capping | if required, removal of residual water from facility Tailing Storage Facility (TSF) a) Low clay content NAF spoil will be used for an initial 2m layer in contact with tailings to create the bulk landform shape. The spoil will have minimal compaction to limit moisture suction potential; Course Reject and Tailing: b) 1m minimum thickness layer of selected weathered Permian and/or Tertiary spoil, will be spread and worked so as to be more than ten times less permeable than spoil above it. The surface will be shaped to shed any deep infiltration out of the landform; c) 2m minimum thickness of more permeable material such as gravelly fresh Permian spoil will be placed over the low permeability layer. The thickness may be greater than 2m as needed to maintain separation between the vegetation rooting zone and the low permeability layer, and to provide a final ground surface that will shed rainfall without ponding with slopes not greater than those on rehabilitated spoil emplacement areas; d) Topsoil and erosion management practices consistent with those on rehabilitated spoil emplacement areas. Noting an additional avoidance of deep rooted tree species is not to be used within this PMLU *a minimum of 10 years is required for settlement form the end of use of the TSF to installation of the cover.
RM5 | Existing rehabilitation landform remediation | a) Landforms requiring maintenance or remediation that are existing historical rehabilitation landforms are reshaped to maximum 17% slopes. b) Where appropriate, addition of rock and/or natural materials (logs) cover to assist erosion resistance of eventual vegetative ground cover. c) Topsoil placed at minimum depth of 150 mm d) Addition of growth media and ameliorants to ensure no bare areas greater than 100m2. e) Cultivation and keying of topsoil to subsoil with suitable multi-type ripper and performed parallel to slope contours. f) Where appropriate, addition of rock and/or natural materials (logs) cover to assist erosion resistance of eventual vegetative ground cover.
RM6 | Surface preparation (cattle grazing) | a) Topsoil placed at minimum depth of 150 mm b) Addition of growth media and ameliorants to ensure no bare areas greater than 100m2. c) Cultivation and keying of topsoil to subsoil with suitable multi-type ripper and performed parallel to slope contours. d) Where appropriate, addition of rock and/or natural materials (logs) cover to assist erosion resistance of eventual vegetative ground cover.
RM7 | Surface preparation (watercourse) | a) Topsoil placed at minimum depth of 150 mm b) Addition of growth media and ameliorants to ensure no bare areas greater than 100m2. c) Where appropriate, cultivation and keying of topsoil to subsoil with suitable multi-type ripper and performed parallel to slope contours. d) Where appropriate, addition of rock and/or natural materials (logs) cover to assist erosion resistance of eventual vegetative ground cover.
RM8 | Surface preparation (native ecosystem) | a) Topsoil placed at minimum depth of 150 mm b) Addition of growth media and ameliorants to ensure no bare areas greater than 100m2. c) Where appropriate, cultivation and keying of topsoil to subsoil with suitable multi-type ripper and performed parallel to slope contours. d) Where appropriate, addition of rock and/or natural materials (logs) cover to assist erosion resistance of eventual vegetative ground cover.
RM9 | Revegetation (cattle grazing) | a) Completed seeding of target pasture species across areas with a suitable species mix for the agreed final land use of grazing.
RM10 | Revegetation (watercourse) | a) Completed seeding of target species across areas with a suitable species mix for the agreed final land use of grazing or native ecosystem.
RM11 | Revegetation (native ecosystem corridor) | a) Completed seeding of target species across areas with a suitable species mix for the agreed final land use of native ecosystem.
RM12 | Achievement of surface requirements (cattle grazing) | a) Vegetation established across areas with a suitable species mix for the agreed final land use of grazing. b) Areas where agricultural land use applies, have pasture grass species present and provide stock with nutritional requirements, as well as being capable of setting viable seed and flowering similar to reference sites in the Middlemount area and/or with a land suitability class (grazing) of 4. c) >60% of the area has a vegetative groundcover² achieved. d) No new invasive plants² and infestation density of invasive plants within the area are contained or reduced and consistent with reference sites. e) Water control structures are either removed or free of active erosion and integrated into permanent landforms. f) No erosion classifications of ‘Severe’ or 'Extreme' (>30 rills/gullies and any are >0.3 m deep) and no active erosion present as demonstrated by no increase in erosion over time ²Groundcover: anything in contact with the soil surface, for example, live cover, standing dry cover, organic littler (including leaves, hay, coarse woody debris) or rocks
RM13 | Achievement of surface requirements (watercourse) | a) Vegetation established across areas with a suitable species mix for the agreed final land use of grazing or native ecosystem. b) Riparian vegetation index score: greater than or equal to upstream or downstream values (RARC methodᶟ) c) No new invasive plantsᶟ and infestation density of invasive plants within the area are contained or reduced and consistent with reference sites. d) Water control structures are either removed or free of active erosion and integrated into permanent landforms. e) No erosion classifications of ‘Severe’ or 'Extreme' (>30 rills/gullies and any are >0.3 m deep) and no active erosion present as demonstrated by no increase in erosion over time f) Evidence of fauna habitat features for invertebrate and vertebrate species (e.g. logs, rock piles). ᶟRehabilitated watercourse - Modified RARC method with a reduced number of monitoring points within each reach
RM14 | Achievement of surface requirements (native ecosystem) | a) Vegetation established across areas with a suitable species mix for the agreed final land use of native ecosystem. b) No new invasive plants² and infestation density of invasive plants within the area are contained or reduced and consistent with reference sites. c) Water control structures are either removed or free of active erosion and integrated into permanent landforms. d) No erosion classifications of ‘Severe’ or 'Extreme' (>30 rills/gullies and any are >0.3 m deep) and no active erosion present as demonstrated by no increase in erosion over time ᶟGroundcover: anything in contact with the soil surface, for example, live cover, standing dry cover, organic littler (including leaves, hay, coarse woody debris) or rocks
RM15 | Achievement of post-mining land use to a stable condition (cattle grazing) | a) Provide a final rehabilitation report including monitoring records b) Assessment of carrying capacity by an AQP¹ demonstrates a sustainable grazing outcome has been achieved c) >75% of groundcover vegetation comprises of species density and diversity consistent with the agreed final land use of grazing. d) If deemed required, either LiDAR or ground survey to confirm settlement levels <10 mm/annum; e) Erosion classification to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable sites f) No erosion classifications of ‘Severe’ or 'Extreme' (>30 rills/gullies and any are >0.3 m deep) and no active erosion present as demonstrated by no increase in erosion over time g) Hazard assessment completed by an AQP¹ to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use h) Water quality in retained structures will meet livestock drinking water criteria as defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZG 2018) i) Water quality from direct rainfall runoff or surface seepage from rehabilitated spoil has: i. pH 6.5–9.0; and ii. EC <2,000 μS/cm.
RM16 | Achievement of post-mining land use to a stable condition (watercourse) | a) Hazard assessment completed by an AQP¹ to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use b) Rainfall runoff from rehabilitated areas is not significantly different to upstream values for the following: pH, EC and turbidity. c) Riparian vegetation index score: greater than or equal to upstream or downstream values (modified RARC method) d) Erosion classification to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue site
RM17 | Achievement of post-mining land use to a stable condition (native ecosystem) | a) Provide a final rehabilitation report including monitoring records b) assessment of carrying capacity by an AQP¹ demonstrates a sustainable grazing outcome has been achieved c) >75% of groundcover vegetation comprises of species density and diversity consistent with the agreed final land use of native ecosystem. d) If deemed required, either LiDAR or ground survey to confirm settlement levels <10 mm/annum; e) Erosion classification to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable site; f) No erosion classifications of ‘Severe’ or 'Extreme' (>30 rills/gullies and any are >0.3 m deep) and no active erosion present as demonstrated by no increase in erosion over time g) Hazard assessment completed by an AQP¹ to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use h) Water quality from direct rainfall runoff or surface seepage from rehabilitated spoil has: i. pH 6.5–9.0; and ii. EC <2,000 μS/cm.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of structural stability | a) Highwall crest battered back where required to achieve a stable slope angle as specified by an AQP¹ (geotechnical engineer)
MM2 | Achievement of landform design and surface requirements | a) Highwall as mined weathered average slope angle of 1V and 1.7H (30°) and low wall as backfilled at angle of repose at 1V:0.8H (50°). b) Abandonment safety bund setback distance is in accordance with calculated geotechnical factor of safety determined at MM1. c) Abandonment safety bund constructed of competent rock and to geometry specified (height = 2m, width top = 2m, batters = 1V:3H, width base = 14m) to prevent traversing by vehicles. d) Certification from an AQP¹ that the residual void is sufficiently protected from probable maximum flood levels e) Abandonment safety bund is revegetated with pasture seed. f) Pit lake water level is stabilise. Safety bund (minimum 2m height and 4m base width) is constructed, where required, at the geotechnical set-back distance. Fencing erected around perimeter of safety bund, where required. Appropriate signage placed to clearly identify and convey the purpose (e.g., EP Act 1994 Non-Use Management Area No Entry).
MM3 | Achievement of sufficient improvement not to cause environmental harm and that will be safe and structurally stable | a) Access to highwall, low wall and ramp batter is restricted by physical barriers. Fencing erected on the outside of the abandonment safety bund to specification (five strand barbed stock fencing) b) Safety signage designed in accordance with Australian Standard is erected at 100m intervals along the fence line c) Certification from an AQP¹ that the residual void will not cause environmental harm outside of the relevant tenure boundary d) Residual void acts as a groundwater sink to the receiving environment into perpetuity e) Groundwater monitoring confirms modelling of no contamination evidence over five (5) year monitoring program f) Certification from an AQP¹ that the residual void is safe to humans and livestock g) Final void walls confirmed to drain internally to the final void
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones