{"text_format":"2","workbook":"xlsx","n_sheets":6,"sheets":["Instructions","RA1 (expl and surface inf)","RA2 (potential subsidence)","IA1","Rehabilitation Area Milestones","Improvement Area Milestones"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Instructions","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"RA1 (expl and surface inf)","index":1,"n_rows":21,"n_cols":11,"rows_kept":21,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[18,0,18,10],[19,0,19,10],[20,0,20,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[17,0,17,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA1"]
["Relevant activities",null,null,null,"Exploration areas and surface infrastructure"]
["Total rehabilitation area size (ha)",null,null,null,6]
["Commencement of first milestone:\nRM1",null,null,null,"2023-12-10"]
["PMLU",null,null,null,"Preclearing native vegetation community"]
["Date area is available","2023-12-10","10 Dec xxxx   + 5 years","10 Dec xxxx   + 6 years","10 Dec xxxx   + 11 years","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",0.5,6,6,6]
["Milestone completed by","2024-12-10","10 Dec xxxx   + 6 years","10 Dec xxxx   + 11 years","10 Dec xxxx   + 21 years","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",0.5,6]
["RM2",0.5,6]
["RM3",0.5,6]
["RM4",null,null,6]
["RM5",null,null,null,6]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA2 (potential subsidence)","index":2,"n_rows":21,"n_cols":11,"rows_kept":21,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[18,0,18,10],[19,0,19,10],[20,0,20,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[17,0,17,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA2"]
["Relevant activities",null,null,null,"Potential subsidence areas"]
["Total rehabilitation area size (ha)",null,null,null,95.4]
["Commencement of first milestone:\nRM2",null,null,null,"10 December XXXX"]
["PMLU",null,null,null,"Preclearing native vegetation community"]
["Date area is available","10 Dec xxxx + 5 years","10 Dec xxxx   + 6 years","10 Dec xxxx   + 11 years","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",95.4,95.4,95.4]
["Milestone completed by","10 Dec xxxx   + 6 years","10 Dec xxxx   + 11 years","10 Dec xxxx   + 21 years","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1"]
["RM2",95.4,95.4,95.4]
["RM3",95.4,95.4,95.4]
["RM4",95.4,95.4,95.4]
["RM5",95.4,95.4,95.4]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"IA1","index":3,"n_rows":21,"n_cols":11,"rows_kept":21,"cut":false,"hidden":false,"merged":[[20,0,20,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[3,0,3,3],[3,4,3,10],[17,0,17,10],[18,0,18,10],[19,0,19,10],[9,1,9,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10]]}
["Non-use management area (NUMA)"]
["Improvement area",null,null,null,"IA1"]
["Relevant activities"]
["Total size (ha)"]
["Commencement of first milestone: \n<insert milestone reference>"]
["NUMA"]
["Date area is available","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)"]
["Milestone completed by","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["MM"]
["MM"]
["MM"]
["MM"]
["MM"]
[]
[]
["1) Insert new columns to the yellow table to include further management milestone dates."]
["2) Insert new columns to the blue table to match management milestone dates."]
["3) Insert new rows to the blue table to include additional management milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. MM1)."]

{"sheet":"Rehabilitation Area Milestones","index":4,"n_rows":16,"n_cols":3,"rows_kept":16,"cut":false,"hidden":false,"merged":[]}
["Milestone reference","Rehabilitation milestone","Milestone criteria"]
["RM1","Infrastructure decommissioning and removal","a.\tAll drillholes, sumps, exploration tracks and gridlines decommissioned in accordance with the requirements specified in the Code of Environmental Compliance for Exploration and Mineral Development Projects (the Code) (DEHP 2014).\n\nb.\tAll bores decommissioned in accordance with the Minimum Construction Requirements for Water Bores in Australia (National Uniform Drillers Licensing Committee 2020).\n\nc.\tAll infrastructure is removed unless a written landholder agreement with the subsequent landholder is in place."]
["RM2","Surface preparation","a.\tNo areas of active subsidence or gully erosion\n\nb.\tShallow rip or scarify any surface cracking\n\nc.\tRework surface material to fill cracks and hollows\n\nd.\tReshape surface to avoid ponding\n\ne.\tPlacement of 200 mm topsoil (SIS and drill pads only)"]
["RM3","Revegetation (preclearing native vegetation community)","a.\tRipping to a minimum depth of 0.4 m along the contour\n\nb.\tCompleted seeding of target species consistent with Table 32 in the Rehabilitation Planning Part (revegetation plan) for a preclearing native vegetation community PMLU. Additional native species may be used where they are consistent with the technical description of the relevant REs."]
["RM4","Achievement of surface requirements (preclearing native vegetation community)","a.\tNo areas of active subsidence or gully erosion\n\nb.\tPreclearing native vegetation communities must achieve 20% of values from benchmark criteria (Table 30 of the Rehabilitation Planning Part) using the BioCondition Assessment methodology by an AQP."]
["RM5","Achievement of the PMLU to a stable condition (preclearing native vegetation community)","a.\tCertification from an AQP that the area has achieved a stable condition\n\nb.\tNo areas of active subsidence or gully erosion\n\nc.\tInvasive plants (as defined in the Biosecurity Act) comprise of less than 5% of vegetation groundcover\n\nd.\tPreclearing native vegetation communities must achieve 60% of values from benchmark criteria (Table 30 of the Rehabilitation Planning Part) using the BioCondition Assessment methodology by an AQP\n\ne.\tCertification from an AQP that surface water quality is within 10% of the results of baseline monitoring results, or when baseline is not available, upstream reference sites which have not been impacted by mining activities\n\nf.\tCertification from an AQP that groundwater quality is within 10% of the results of baseline monitoring results, or when baseline is not available, reference bores which have not been impacted by mining activities\n\ng.\tCertification from an AQP that Humbug Gully is safe and stable and flow conditions are consistent with pre-mining conditions"]
{"$rows_empty":7}
["1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project"]
["2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form."]
["3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones"]

{"sheet":"Improvement Area Milestones","index":5,"n_rows":16,"n_cols":3,"rows_kept":16,"cut":false,"hidden":false,"merged":[[13,0,13,2],[14,0,14,2],[15,0,15,2]]}
["Milestone reference","Management milestone","Milestone criteria"]
["MM1"]
["MM2"]
["MM3"]
["MM4"]
["MM5"]
["MM6"]
["MM7"]
["MM8"]
["MM9"]
["MM10"]
[]
[]
["1) Insert new rows below the table to record more Improvement Area Milestones for the project"]
["2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form."]
["3) See the PRCP guideline before developing site-specific Improvement Area Milestones"]