## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Product Stockpiles - Limestone
Total rehabilitation area size (ha) |  |  |  | 0.05 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA1_RM1 10/12/2031
PMLU |  |  |  | Low intensity grazing
Date area is available | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10
Cumulative area available (ha) | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
Milestone completed by | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RA1_RM 1 | 0.05
PS_RM 2 |  | 0.05
PS_RM 3 |  |  | 0.05
PS_RM 4 |  |  | 0.05
PS_RM 5 |  |  |  | 0.05
PS_RM 6 |  |  |  |  | 0.05
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Product Stockpiles - Coal
Total rehabilitation area size (ha) |  |  |  | 0.01 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA2_RM1 10/12/2031
PMLU |  |  |  | Low intensity grazing
Date area is available | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10
Cumulative area available (ha) | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
Milestone completed by | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10
Milestone Reference | Cumulative area achieved (ha)
RA2_RM 1 | 0.01
PS_RM 2 |  | 0.01
PS_RM 3 |  |  | 0.01
PS_RM 4 |  |  | 0.01
PS_RM 5 |  |  |  | 0.01
PS_RM 6 |  |  |  |  | 0.01
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Infrastructure - Buildings and sheds, Tanks (other) and weighbridge
Total rehabilitation area size (ha) |  |  |  | 0.07 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA3_RM1 10/12/2030
PMLU |  |  |  | Low intensity grazing
Date area is available | 2030-12-10 | 2034-12-10 | 2035-12-10 | 2036-12-10 | 1941-12-10
Cumulative area available (ha) | 0.07 | 0.07 | 0.07 | 0.07 | 0.07
Milestone completed by | 2034-12-10 | 2035-12-10 | 2036-12-10 | 1941-12-10 | 1944-12-10
Milestone Reference | Cumulative area achieved (ha)
RA3_RM 1 | 0.07
RA3_RM 2 |  | 0.07
I_RM 4 |  |  | 0.07
I_RM 5 |  |  | 0.07
I_RM 6 |  |  |  | 0.07
I_RM 7 |  |  |  |  | 0.07
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure - Workshop, Process plant and equipment and Tanks (hydrocarbons)
Total rehabilitation area size (ha) |  |  |  | 0.28 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA4_RM1 10/12/2030
PMLU |  |  |  | Low intensity grazing
Date area is available | 2030-12-10 | 2031-12-10 | 2034-12-10 | 2035-12-10 | 2036-12-10 | 1941-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.28 | 0.28 | 0.28 | 0.28 | 0.28 | 0.28
Milestone completed by | 2031-12-10 | 2034-12-10 | 2035-12-10 | 2036-12-10 | 1941-12-10 | 1944-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA4_RM 1 | 0.28
RA4_RM 2 |  | 0.28
RA4_RM 3 |  |  | 0.28
I_RM 4 |  |  |  | 0.28
I_RM 5 |  |  |  | 0.28
I_RM 6 |  |  |  |  | 0.28
I_RM 7 | [5 empty] | 0.28
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Infrastructure - Sediment pond
Total rehabilitation area size (ha) |  |  |  | 0.11 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA5_RM1 10/12/2034
PMLU |  |  |  | Low intensity grazing
Date area is available | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2041-12-10
Cumulative area available (ha) | 0.11 | 0.11 | 0.11 | 0.11
Milestone completed by | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2044-12-10
Milestone Reference | Cumulative area achieved (ha)
RA5_RM 1 | 0.11
I_RM4 |  | 0.11
I_RM5 |  | 0.11
I_RM6 |  |  | 0.11
I_RM7 |  |  |  | 0.11
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Infrastructure - ROM pad trafficked areas
Total rehabilitation area size (ha) |  |  |  | 0.77 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA6_RM1 10/12/2032
PMLU |  |  |  | Low intensity grazing
Date area is available | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.77 | 0.77 | 0.77 | 0.77
Milestone completed by | 2033-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA6_RM 1 | 0.77
RA6_RM 2 | 0.77
I_RM 4 |  | 0.77
I_RM 5 |  | 0.77
I_RM 6 |  |  | 0.77
I_RM 7 |  |  |  | 0.77
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: add when finalised

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Infrastructure - Laydown (Northern area)
Total rehabilitation area size (ha) |  |  |  | 0.25 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA7_RM1 10/12/2032
PMLU |  |  |  | Low intensity grazing
Date area is available | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.25 | 0.25 | 0.25 | 0.25
Milestone completed by | 2033-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA7_RM 1 | 0.25
RA7_RM 2 | 0.25
I_RM 4 |  | 0.25
I_RM 5 |  | 0.25
I_RM 6 |  |  | 0.25
I_RM 7 |  |  |  | 0.25
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Infrastructure - Laydown (Southern Areas)
Total rehabilitation area size (ha) |  |  |  | 1.68 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA8 RM1 10/12/2034 (1.41 ha), 10/12/2036 (0.26 ha)
PMLU |  |  |  | Low intensity grazing
Date area is available | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2044-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.41 | 1.41 | 1.68 | 1.68 | 1.68 | 1.68
Milestone completed by | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2044-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA8_RM 1 | 1.41 |  | 1.68
RA8_RM 2 | 1.41 |  | 1.68
I_RM 4 |  | 1.41 | 1.68
I_RM 5 |  | 1.41 | 1.68
I_RM 6 |  |  | 1.41 |  | 1.68
I_RM 7 |  |  |  | 1.41 |  | 1.68
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Infrastructure - Vegetated areas
Total rehabilitation area size (ha) |  |  |  | 0.54 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA9_RM1 10/12/2033
PMLU |  |  |  | Low intensity grazing
Date area is available | 2033-12-10 | 2034-12-10 | 2039-12-10 |  | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.54 | 0.54 | 0.54
Milestone completed by | 2034-12-10 | 2039-12-10 | 2042-12-10 |  | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA9_RM 1 | 0.54
I_RM6 |  | 0.54
I_RM7 |  |  | 0.54
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10
Relevant activities |  |  |  | Roads and Tracks - Tracks (earthen)
Total rehabilitation area size (ha) |  |  |  | 0.40 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RT_RM2 10/12/2034
PMLU |  |  |  | Low intensity grazing
Date area is available | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2041-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.4 | 0.4 | 0.4 | 0.4
Milestone completed by | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2044-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RT_RM 2 | 0.4
RT_RM 3 |  | 0.4
RT_RM 4 |  | 0.4
RT_RM 5 |  |  | 0.4
RT_RM 6 |  |  |  | 0.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA11
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA11
Relevant activities |  |  |  | Roads and Tracks - Tracks (gravel)
Total rehabilitation area size (ha) |  |  |  | 0.32 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA11_RM1 10/12/2038
PMLU |  |  |  | Low intensity grazing
Date area is available | 2038-12-10 | 2039-12-10 | 2041-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.32 | 0.32 | 0.32 | 0.32
Milestone completed by | 2039-12-10 | 2041-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA11_RM 1 | 0.32
RT_RM 2 | 0.32
RT_RM 3 |  | 0.32
RT_RM 4 |  | 0.32
RT_RM 5 |  |  | 0.32
RT_RM 6 |  |  |  | 0.32
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA12
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA12
Relevant activities |  |  |  | Roads and Tracks - Sealed road (bitumen sealed site entrance)
Total rehabilitation area size (ha) |  |  |  | 0.02 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA12_RM1 10/12/2038
PMLU |  |  |  | Low intensity grazing
Date area is available | 2038-12-10 | 2039-12-10 | 2041-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.02 | 0.02 | 0.02 | 0.02
Milestone completed by | 2039-12-10 | 2041-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA12_RM 1 | 0.02
RT_RM 2 | 0.02
RT_RM 3 |  | 0.02
RT_RM 4 |  | 0.02
RT_RM 5 |  |  | 0.02
RT_RM 6 |  |  |  | 0.02
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA13
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA13
Relevant activities |  |  |  | Topsoil Stockpile
Total rehabilitation area size (ha) |  |  |  | 0.46 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA13_RM1 10/12/2033 (0.24 ha), 10/12/35 (0.21 ha)
PMLU |  |  |  | Low intensity grazing
Date area is available | 2033-12-10 | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10 | 1945-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.24 | 0.46 | 0.46 | 0.46 | 0.46 | 0.46
Milestone completed by | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2042-12-10 | 1945-12-10 | 1946-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA13_RM 1 | 0.24 | 0.46
RA13_RM 2 | 0.24 | 0.46
RA13_RM 3 | 0.24 | 0.46
RA13_RM 4 |  |  | 0.24 | 0.46
RA13_RM 5 |  |  |  |  | 0.24 | 0.46
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA14
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA14
Relevant activities |  |  |  | Residual Void - Cut back and benched area
Total rehabilitation area size (ha) |  |  |  | 1.32 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA14_RM1 10/12/2014
PMLU |  |  |  | Water Storage
Date area is available | 2014-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.32 | 1.32 | 1.32 | 1.32 | 1.32
Milestone completed by | 2015-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA14_RM 1 | 1.32
RV_RM4 |  | 1.32
RV_RM5 |  |  | 1.32
RV_RM6 |  |  | 1.32
RV_RM7 |  |  |  | 1.32
RV_RM8 |  |  |  |  | 1.32
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA15
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA15
Relevant activities |  |  |  | Residual Void - Northwest Batter
Total rehabilitation area size (ha) |  |  |  | 1.67 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA15_RM1 10/12/2036
PMLU |  |  |  | Water Storage
Date area is available | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.67 | 1.67 | 1.67 | 1.67
Milestone completed by | 2037-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA15_RM 1 | 1.67
RV_RM4 | 1.67
RV_RM5 |  | 1.67
RV_RM6 |  | 1.67
RV_RM7 |  |  | 1.67
RV_RM8 |  |  |  | 1.67
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA16
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA16
Relevant activities |  |  |  | Residual Void - Minor Disturbance
Total rehabilitation area size (ha) |  |  |  | 0.46 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RV_RM4 10/12/2036
PMLU |  |  |  | Water Storage
Date area is available | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.05 | 0.05 | 0.05 | 0.05
Milestone completed by | 2037-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RV_RM4 | 0.05
RV_RM6 |  | 0.05
RV_RM7 |  |  | 0.05
RV_RM8 |  |  |  | 0.05
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA17
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA17
Relevant activities |  |  |  | Residual Void - Water Storage
Total rehabilitation area size (ha) |  |  |  | 2.67 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RV_RM4 10/12/2030
PMLU |  |  |  | Water Storage
Date area is available | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 2.67 | 2.67 | 2.67 | 2.67
Milestone completed by | 2037-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RV_RM4 | 2.67
RV_RM5 |  | 2.67
RV_RM6 |  | 2.67*
RV_RM7 |  |  | 2.67
RV_RM8 |  |  |  | 2.67
* will not include the approximately 0.41 ha of void waterbody
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA18
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA18
Relevant activities |  |  |  | Residual Void - Mixed kiln dust, reject limestone and coal ash in void
Total rehabilitation area size (ha) |  |  |  | 1.02 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA18_RM1 10/12/2031
PMLU |  |  |  | Water Storage
Date area is available | 2031-12-10 | 2032-12-10 | 1936-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02
Milestone completed by | 2032-12-10 | 2033-12-10 | 1937-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA18_RM 1 | 1.02
RA18_RM 2 |  | 1.02
RA18_RM 3 |  |  | 1.02
RV_RM4 |  |  | 1.02
RV_RM5 |  |  |  | 1.02
RV_RM6 |  |  |  | 1.02
RV_RM7 |  |  |  |  | 1.02
RV_RM8 | [5 empty] | 1.02
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA19
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA19
Relevant activities |  |  |  | Residual Void - Void Floor
Total rehabilitation area size (ha) |  |  |  | 0.12 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA19_RM1 10/12/2032
PMLU |  |  |  | Water Storage
Date area is available | 2032-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.12 | 0.12 | 0.12 | 0.12 | 0.12
Milestone completed by | 2038-12-10 | 2037-12-10 | 2038-12-10 | 2046-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA19_RM 1 | 0.12
RV_RM4 |  | 0.12
RV_RM5 |  |  | 0.12
RV_RM6 |  |  | 0.12
RV_RM7 |  |  |  | 0.12
RV_RM8 |  |  |  |  | 0.12
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA20
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA20
Relevant activities |  |  |  | Waste and Reject Stockpiles - Mixed kiln dust, reject limestone and coal ash stockpiles (ex-void)
Total rehabilitation area size (ha) |  |  |  | 0.55 ha
Commencement of first milestone: <insert milestone reference> |  |  |  | RA20_RM1 10/12/2031
PMLU |  |  |  | Low intensity grazing
Date area is available | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.55 | 0.55 | 0.55 | 0.55 | 0.55
Milestone completed by | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RA20_RM 1 | 0.55
RA20_RM 2 |  | 0.55
RA20_RM 3 |  |  | 0.55
RA20_RM 4 |  |  | 0.55
RA20_RM 5 |  |  |  | 0.55
RA20_RM 6 |  |  |  |  | 0.55
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RA1_RM1 | Removal of stockpiled mined limestone and placement back in the void (at RA19) | • All excess limestone feed stock has been removed and placed back in the void (see footnote +) • No equipment or built structures remain in the rehabilitation area
RA2_RM1 | Removal of stockpiled coal fuel and disposed off-site | • All coal has been removed and disposed of at an appropriately licenced waste • No equipment or built structures remain in the rehabilitation area
PS_RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface water management Section of the PRCPFinalise engineering and design plans
PS_RM3 | Topsoiling and surface preparation | • Ripping completed to specifications (depth of 500 mm at 500 – 800 mm spacings) • An assessment of stockpiled soil quality and suitability for rehabilitation has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment • Topsoil placed to an average depth of 150 mm • If imported topsoil is required, it will be analysed prior to delivery and suitability for rehabilitation will be assessed by an appropriately qualified person to confirm it is suitable for target vegetation establishment • If used, imported topsoil stone content does not exceed 20% by volume • If used, imported topsoil is electrical conductivity (salinity as ECe) <4 dS/m • If used, imported topsoil has a pH range 5.5 to 8.0 • If used, imported topsoil is stable, with low dispersion risk characterised by - non-sodic properties (exchangeable sodium percentage <6%) - Emerson Aggregate Test Classes result of 3 (2), 3 (1), 4, 5, 6, 7 or 8
PS_RM4 | Revegetation | • • For stockpiled topsoil, amelioration has been applied according to the Site preparation and topsoiling Section of the PRCP • For imported topsoil, amelioration has been applied according to the recommendations of an appropriately qualified person based on soil analytical results • The pasture species used and the seeding rate applied are consistent with the Revegetation Section of the PRCP
PS_RM5 | Achievement of PMLU to stable condition (grazing) | • Rehabilitation reference sites have been established • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Monitoring shows that no declared pest plants are recorded in the rehabilitation domain (or if present the % cover of declared pest plant species is no more than in the surrounding vegetation and is not increasing relative to reference conditions) • Within 24 months of revegetation, average standing biomass of established pasture is no less than 1000 kg/ha at the end of the dry season or no less than 70% of that at the reference sites established on unmined areas within the lease whichever is lower • The ground cover will, on average, be dominated by native and introduced grass, legume and herb/forb species recognised as pasture species or known to be palatable and provide forage for livestock • Average groundcover is greater than or equal to 50% • No evidence of persistent surface ponding and waterlogging affecting pasture health • An appropriate carrying capacity has been calculated that will allow for sustainable long-term grazing • Certification from an appropriately qualified person that the area has achieved stable condition • No active gully erosion (i.e., >0.3m deep) is present in the rehabilitated areas • All water management structures are stable and functioning as per the design • Erosion repair works have been conducted where monitoring has identified a deviation from the required performance • Vegetation maintenance and or additional soil amelioration has been undertaken where groundcover or standing biomass does not meet the milestone criteria and is not on a desired trajectory • Rehabilitation repair works and weed control have been undertaken where rehabilitation does not meet the milestone criteria and is not on a desired trajectory
PS_RM6 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
RA3_RM1 | Decommissioning : • Disconnect services • Demolish and or remove buildings and tanks from site • Break up and remove concrete pads and footings | • All services have been disconnected • Bore decommissioned according to the preferred practices nominated in the Minimum Construction Requirements for Water Bores in Australia • Hazardous building materials have been identified, and managed and removed by appropriately licenced contractors • All infrastructure assets have been demolished and demolition waste removed to an appropriately licenced waste facility
RA3_RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface water management Section of the PRCPAll major earthworks have been completed
RA4_RM1 | Decommissioning : • Disconnect services • Demolish and or remove buildings and tanks from site • Break up and remove concrete pads and footings | • All services have been disconnected • Hazardous building materials have been identified, and managed and removed by appropriately licenced contractors • All infrastructure assets have been demolished and demolition waste removed to an appropriately licenced waste facility
RA4_RM2 | Remediation of contaminated land | • Site Investigation Report prepared and certified by an appropriately qualified person • If required, remediation is carried out and validated sampling has been complete • Site removed from Contaminated Land Register by the registrar; or • A Site Management Plan: - is prepared and certified by an appropriately qualified person and - includes a statement by the underlying landholder accepting responsibility to implement the Site Management Plan
RA4_RM3 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface Water Management Section of this PRCPAll major earthworks have been completed
RA5_RM1 | Landform development | • Sediment tested for contaminants • If contaminated, sediment removed to an appropriately licenced waste facility • Sediment dam bund pushed onto sediment dam and area levelled • All major earthworks have been completed • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water
RA6_RM1, RA7_RM1 and RA8_RM1 | Removal of surface aggregate/road base from laydown areas and use as soil forming material for rehabilitation of the void floor | • No equipment or built structures remain in the rehabilitation area • Surface aggregate removed to 300 mm • Aggregate placed on RA19 and RA18
RA6_RM2 and RA8 RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface water management Section of the PRCPAll major earthworks have been completed
RA7_RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Average slope does not exceed 15% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface water management Section of the PRCPAll major earthworks have been completed
RA9_RM1 | Supplementary seeding (revegetation) | • Existing ground cover vegetation composition and condition reviewed for suitability with respect to PMLU • Where required, weed management conducted • Where required overseeding conducted with pasture species consistent with the revegetation plan included in the PRCP
I_RM4 | Topsoiling and surface preparation | • Ripping completed to specifications (depth of 500 mm at 500 – 800 mm spacings) • An assessment of stockpiled soil quality and suitability for rehabilitation has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment • Topsoil placed to an average depth of 150 mm • If imported topsoil is required, it will be analysed prior to delivery and suitability for rehabilitation will be assessed by an appropriately qualified person to confirm it is suitable for target vegetation establishment • If used, imported topsoil stone content does not exceed 20% by volume • If used, imported topsoil is electrical conductivity (salinity as ECe) <4 dS/m • If used, imported topsoil has a pH range 5.5 to 8.0 • If used, imported topsoil is stable, with low dispersion risk characterised by - non-sodic properties (exchangeable sodium percentage <6%) - Emerson Aggregate Test Classes result of 3 (2), 3 (1), 4, 5, 6, 7 or 8
I_RM5 | Revegetation | • For stockpiled topsoil, amelioration has been applied according to the Site preparation and topsoiling Section of the PRCP • For imported topsoil, amelioration has been applied according to the recommendations of an appropriately qualified person based on soil analytical results • The pasture species used and the seeding rate applied are consistent with the Revegetation Section of the PRCP For stockpiled topsoil, amelioration has been applied according to the revegetation plan included in the PRCP
I_RM6 | Achievement of PMLU to stable condition (grazing) | • Rehabilitation reference sites have been established • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Monitoring shows that no declared pest plants are recorded in the rehabilitation domain (or if present the % cover of declared pest plant species is no more than in the surrounding vegetation and is not increasing relative to reference conditions) • Within 24 months of revegetation, average standing biomass of established pasture is no less than 1000 kg/ha at the end of the dry season or no less than 70% of that at the reference sites established on unmined areas within the lease whichever is lower • The ground cover will, on average, be dominated by native and introduced grass, legume and herb/forb species recognised as pasture species or known to be palatable and provide forage for livestock • Average groundcover is greater than or equal to 50% • No evidence of persistent surface ponding and waterlogging affecting pasture health • An appropriate carrying capacity has been calculated that will allow for sustainable long-term grazing • Certification from an appropriately qualified person that the area has achieved stable condition • No active gully erosion (i.e., >0.3m deep) is present in the rehabilitated areas • All water management structures are stable and functioning as per the design • Erosion repair works have been conducted where monitoring has identified a deviation from the required performance • Vegetation maintenance and or additional soil amelioration has been undertaken where groundcover or standing biomass does not meet the milestone criteria and is not on a desired trajectory • Rehabilitation repair works and weed control have been undertaken where rehabilitation does not meet the milestone criteria and is not on a desired trajectory
I_RM7 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
RA11_RM1 | Removal of surface aggregate/road base from laydown areas and use as soil forming material for rehabilitation of the void floor | • No equipment or built structures remain in the rehabilitation area • Surface aggregate removed to 300 mm • Aggregate placed on RA19 and RA18
RA12_RM1 | Break up, remove and off-site disposal of bitumen | • Bitumen has been removed and disposed of at a licenced waste facility • No equipment or built structures remain in the rehabilitation area
RT_RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed in accordance with the final engineering and design plan • Roads and tracks are graded to conform to the surrounding landforms • Final landform does not contain any low points that may pond water
RT_RM3 | Topsoiling and surface preparation | • Ripping completed to specifications (depth of 500 mm at 500 – 800 mm spacings) • An assessment of stockpiled soil quality and suitability for rehabilitation has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment • Topsoil placed to an average depth of 150 mm • If imported topsoil is required, it will be analysed prior to delivery and suitability for rehabilitation will be assessed by an appropriately qualified person to confirm it is suitable for target vegetation establishment • If used, imported topsoil stone content does not exceed 20% by volume • If used, imported topsoil is electrical conductivity (salinity as ECe) <4 dS/m • If used, imported topsoil has a pH range 5.5 to 8.0 • If used, imported topsoil is stable, with low dispersion risk characterised by - non-sodic properties (exchangeable sodium percentage <6%) - Emerson Aggregate Test Classes result of 3 (2), 3 (1), 4, 5, 6, 7 or 8
RT_RM4 | Revegetation | • For stockpiled topsoil, amelioration has been applied according to the Site preparation and topsoiling Section of the PRCP • For imported topsoil, amelioration has been applied according to the recommendations of an appropriately qualified person based on soil analytical results • The pasture species used and the seeding rate applied are consistent with the Revegetation Section of the PRCP
RT_RM5 | Achievement of PMLU to stable condition (grazing) | • Rehabilitation reference sites have been established • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Monitoring shows that no declared pest plants are recorded in the rehabilitation domain (or if present the % cover of declared pest plant species is no more than in the surrounding vegetation and is not increasing relative to reference conditions) • Within 24 months of revegetation, average standing biomass of established pasture is no less than 1000 kg/ha at the end of the dry season or no less than 70% of that at the reference sites established on unmined areas within the lease whichever is lower • The ground cover will, on average, be dominated by native and introduced grass, legume and herb/forb species recognised as pasture species or known to be palatable and provide forage for livestock • Average groundcover is greater than or equal to 50% • No evidence of persistent surface ponding and waterlogging affecting pasture health • An appropriate carrying capacity has been calculated that will allow for sustainable long-term grazing • Certification from an appropriately qualified person that the area has achieved stable condition • No active gully erosion (i.e., >0.3m deep) is present in the rehabilitated areas • All water management structures are stable and functioning as per the design • Erosion repair works have been conducted where monitoring has identified a deviation from the required performance • Vegetation maintenance and or additional soil amelioration has been undertaken where groundcover or standing biomass does not meet the milestone criteria and is not on a desired trajectory • Rehabilitation repair works and weed control have been undertaken where rehabilitation does not meet the milestone criteria and is not on a desired trajectory
RT_RM6 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
RA13_RM1 | Landform development | • Topsoil stockpile removed and re-used for rehabilitation on-site. • No equipment or built structures remain in the rehabilitation area • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface Water Management section of the PRCP
RA13_RM2 | Topsoiling and surface preparation | • Ripping completed to specifications (depth of 500 mm at 500 – 800 mm spacings) • An assessment of stockpiled soil quality and suitability for rehabilitation has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment • Topsoil placed to an average depth of 150 mm
RA13_RM3 | Revegetation | • For stockpiled topsoil, amelioration has been applied according to the Site preparation and topsoiling Section of the PRCP • The pasture species used and the seeding rate applied are consistent with the Revegetation Section of the PRCP
RA13_RM4 | Achievement of PMLU to stable condition (grazing) | • Rehabilitation reference sites have been established • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Monitoring shows that no declared pest plants are recorded in the rehabilitation domain (or if present the % cover of declared pest plant species is no more than in the surrounding vegetation and is not increasing relative to reference conditions) • Within 24 months of revegetation, average standing biomass of established pasture is no less than 1000 kg/ha at the end of the dry season or no less than 70% of that at the reference sites established on unmined areas within the lease whichever is lower • The ground cover will, on average, be dominated by native and introduced grass, legume and herb/forb species recognised as pasture species or known to be palatable and provide forage for livestock • Average groundcover is greater than or equal to 50% • No evidence of persistent surface ponding and waterlogging affecting pasture health • An appropriate carrying capacity has been calculated that will allow for sustainable long-term grazing • Certification from an appropriately qualified person that the area has achieved stable condition • No active gully erosion (i.e., >0.3m deep) is present in the rehabilitated areas • All water management structures are stable and functioning as per the design • Erosion repair works have been conducted where monitoring has identified a deviation from the required performance • Vegetation maintenance and or additional soil amelioration has been undertaken where groundcover or standing biomass does not meet the milestone criteria and is not on a desired trajectory • Rehabilitation repair works and weed control have been undertaken where rehabilitation does not meet the milestone criteria and is not on a desired trajectory
RA13_RM5 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
RA14_RM1 | Landform development | • Finalise engineering and final design plan so that - Bench heights up to 20 m - Berm widths no less than 10 m - Batter angles not exceeding 53o (133%) • All major earthworks have been completed in accordance with the final engineering and design plan • Final landform drains to the residual void • Certification from an appropriately qualified person that the area has achieved stable condition
RA15_RM1 | Landform development | • Finalise engineering and final design plan so that batters of RA15 will be battered back to no more than 40o (83%) • Assess microbat usage of the adit in the void and develop and implement an appropriate mitigation and closure strategy • Final landform drains to the residual void • All major earthworks have been completed in accordance with the final engineering and design plan • Certification from an appropriately qualified person that the area has achieved stable condition
RA18_RM1 | Removal of kiln dust, reject limestone and coal ash from the void and disposal off-site | • Waste has been classified prior to removal and disposal at an appropriately licensed waste management facility • All waste materials are removed from the void • Sampling undertaken to validate waste removal All waste materials are removed from the void • Sampling undertaken to validate waste removal • Waste has been classified prior to removal and disposal at an appropriately licensed waste management facility
RA18_RM2 | Landform development | • Finalise engineering and final design plan so that batters of RA15 will be battered back to no more than 40o (83%) • Final landform drains to the residual void • All major earthworks have been completed in accordance with the final engineering and design plan • Certification from an appropriately qualified person that the area has achieved stable condition
RA18_RM3 | Surface preparation | • Remaining accessible void floor areas have been ripped (to the maximum practical depth to 500 mm or scarified where ripping is impractical • Soil forming material (recovered surface aggregate from RA6, RA7, RA8 and RA11) placed in accessible locations
RA19_RM1 | Surface preparation | • Remaining accessible void floor areas have been ripped (to the maximum practical depth to 500 mm or scarified where ripping is impractical • Soil forming material (recovered surface aggregate from RA6, RA7, RA8 and RA11) placed in accessible locations
RV_RM4 | Install safety bund /fencing around void | The void is bunded and or fenced and warning signage erected according to the specifications in the Void Closure section of the PRCP
RV_RM5 | Break up remaining tracks in void | Ripping of remaining tracks within the void is completed to specifications (depth of 500 mm at 500 – 800 mm spacings)
RV_RM6 | Revegetation (excludes water body in residual void) | • Aerial seeding has been undertaken using appropriate methods and native species mix determined through research trials
RV_RM7 | Achievement of PMLU to stable condition (water storage) | • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Water quality meets the Australian Water Quality Guidelines for Primary Industries – Stock (cattle) water use • The established vegetation communities contain native species with a range of growth forms and structural elements • The established vegetation communities contain natives species that are characteristic of the vegetation communities mapped in the surrounding landscape • Rehabilitation repair works undertaken where rehabilitation consistently does not meet completion criteria and is not on a desired trajectory
RV_RM8 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
RMA20_RM1 | Removal of kiln dust, reject limestone and coal ash from stockpile locations and disposal off-site | • Waste has been classified prior to removal and disposal at an appropriately licensed waste management facility • All waste materials are removed from the stockpiles • Sampling undertaken to validate waste removal
RMA20_RM2 | Landform development | • Finalise engineering and final design plans • All major earthworks have been completed • Average slope does not exceed 8% • Final landform does not contain any low points that may pond water • Installation of water management structures have been certified by an appropriately qualified person as conforming to the design standard specified in the Surface water management Section of the PRCP
RMA20_RM3 | Topsoiling and surface preparation | • Ripping completed to specifications (depth of 500 mm at 500 – 800 mm spacings) • An assessment of stockpiled soil quality and suitability for rehabilitation has been completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment • Topsoil placed to an average depth of 150 mm • If imported topsoil is required, it will be analysed prior to delivery and suitability for rehabilitation will be assessed by an appropriately qualified person to confirm it is suitable for target vegetation establishment • If used, imported topsoil stone content does not exceed 20% by volume • If used, imported topsoil is electrical conductivity (salinity as ECe) <4 dS/m • If used, imported topsoil has a pH range 5.5 to 8.0 • If used, imported topsoil is stable, with low dispersion risk characterised by - non-sodic properties (exchangeable sodium percentage <6%) - Emerson Aggregate Test Classes result of 3 (2), 3 (1), 4, 5, 6, 7 or 8
RMA20_RM4 | Revegetation | • For stockpiled topsoil, amelioration has been applied according to the Site preparation and topsoiling Section of the PRCP • For imported topsoil, amelioration has been applied according to the recommendations of an appropriately qualified person based on soil analytical results • The pasture species used and the seeding rate applied are consistent with the Revegetation Section of the PRCP
RMA20_RM5 | Achievement of PMLU to stable condition (grazing) | • Rehabilitation reference sites have been established • Rehabilitation monitoring has been undertaken at the frequency specified in the PRCP • Rehabilitation monitoring has been undertaken using the methods specified in the PRCP • Monitoring shows that no declared pest plants are recorded in the rehabilitation domain (or if present the % cover of declared pest plant species is no more than in the surrounding vegetation and is not increasing relative to reference conditions) • Within 24 months of revegetation, average standing biomass of established pasture is no less than 1000 kg/ha at the end of the dry season or no less than 70% of that at the reference sites established on unmined areas within the lease whichever is lower • The ground cover will, on average, be dominated by native and introduced grass, legume and herb/forb species recognised as pasture species or known to be palatable and provide forage for livestock • Average groundcover is greater than or equal to 50% • No evidence of persistent surface ponding and waterlogging affecting pasture health • An appropriate carrying capacity has been calculated that will allow for sustainable long-term grazing • Certification from an appropriately qualified person that the area has achieved stable condition • No active gully erosion (i.e., >0.3m deep) is present in the rehabilitated areas • All water management structures are stable and functioning as per the design • Erosion repair works have been conducted where monitoring has identified a deviation from the required performance • Vegetation maintenance and or additional soil amelioration has been undertaken where groundcover or standing biomass does not meet the milestone criteria and is not on a desired trajectory • Rehabilitation repair works and weed control have been undertaken where rehabilitation does not meet the milestone criteria and is not on a desired trajectory
RMA20_RM6 | Sustainable achievement of PMLU | All completion criteria have been met on at least three consecutive monitoring events conducted no more frequently than once annually
+ Some limestone will be used as rock protection for surface water management during rehabilitation.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones