## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | B Pit and Q Pit back-filled voids, waste rock dumps and haul roads
Total rehabilitation area size (ha) |  |  |  | 86.84
Commencement of first milestone: <insert milestone reference> |  |  |  | First rehabilitation milestone completed for part of RA prior to PRCP transition
PMLU |  |  |  | Grazing Pasture
Date area is available | 2021-12-10 | 2024-12-10 | 2026-12-10 | 2037-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 46 | 46 | 46 | 86.84
Milestone completed by | 2024-12-10 | 2026-12-10 | 2027-12-10 | 2043-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 46 | 46 | 46 | 86.84
RM2 | 46 | 46 | 46 | 86.84
RM3 | 19 | 46 | 46 | 86.84
RM4 |  |  | 46 | 86.84
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Western Diversion Drain
Total rehabilitation area size (ha) |  |  |  | 0.28
Commencement of first milestone: <insert milestone reference> |  |  |  | First rehabilitation milestone completed for RA prior to PRCP transition
PMLU |  |  |  | Grazing Pasture
Date area is available | 2021-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.28
Milestone completed by | 2026-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM5 | 0.28
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities
Total size (ha)
Commencement of first milestone: <insert milestone reference>
NUMA
Date area is available | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha)
Milestone completed by | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
MM
MM
MM
MM
MM
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Landform development, shaping and profiling | a) Undertake contaminated land assessment if required (as per the PRC Plan - Rehabilitation Planning Part) and if necessary undertake remedial activities (supervised by a suitably qualified person) b) All major earthworks completed c) 20% (11.5°) maximum slope achieved on dump batters (unless an alternate slope is recommended by an RPEQ), confirmed by survey d) Drainage works within rehabilitation areas completed, confirmed by survey e) Where present, structures within drainage lines (e.g. culverts, bed level sheeted crossings) removed and bed and banks reinstated to tie into upstream/downstream reaches
RM2 | Surface preparation | a) Ripping of compacted surfaces as required b) Placement of a minimum of 100 mm of topsoil
RM3 | Achievement of surface requirements (grazing pasture) | a) Germination monitoring undertaken within 12 months of completion of RM2 to identify areas where the natural seedbank has proven to be unsuccessful in establishing vegetation b) Seeding undertaken where natural seedbank has been identified to be unsuccessful in establishing vegetation c) No significant slope failure or erosion features present in the rehabilitated area, and any historical significant slope failure or erosion features have been appropriately remediated. d) ≥70% of the productivity (carrying capacity) of grazed reference sites e) Mean groundcover ≥50% or > the grazed reference site mean minus one standard deviation f) Proportion of non-preferred species not increasing g) Proportion class of non-preferred species not more than one class greater than the grazed reference sites (see Table 11 of the QNH RMP for class descriptions) h) Proportion of declared plant* pest species not increasing i) Proportion class of declared plant* pest species not more than one class greater than the grazed reference sites (see Table 11 of the QNH RMP for class descriptions) j) Soil testing undertaken 5 yearly (or a lesser period if required) indicates the following parameters are met: - Plant Available Water Capacity (PAWC) >50 mm - Bicarbonate P ≥4ppm - Electrical Conductivity (1:5 dilution) <1.2 mS/cm or Chloride (1:5 dilution) <1,500 ppm in the root zone (60 cm depth) - Rockiness <100% (% coarse fragments at soil surface) - Soil pH <10 and >4 as measured at any part of the root zone - Exchangeable Sodium Percentage (ESP %) <30% (0-10 cm depth) *Per the superceded Land Protection (Pest and Stock Route Management) Act 2002
RM4 | Achievement of post-mining land use to stable condition (grazing pasture) | Each of the below listed criteria is certified as having been achieved by a person who is appropritaely qualified to assess that criteria, with the combined certifications confirming that the rehabilitiation achives the PMLU and is stable (as defined in the EP Act): a) Soil testing undertaken 5 yearly (or a lesser period if required) indicates the following parameters are met: - Plant Available Water Capacity (PAWC) >50 mm - Bicarbonate P ≥4ppm - Electrical Conductivity (1:5 dilution) <1.2 mS/cm or Chloride (1:5 dilution) <1,500 ppm in the root zone (60 cm depth) - Rockiness <100% (% coarse fragments at soil surface) - Soil pH <10 and >4 as measured at any part of the root zone - Exchangeable Sodium Percentage (ESP %) <30% (0-10 cm depth) b) ≥70% of the productivity (carrying capacity) of grazed reference sites c) Mean groundcover ≥50% or > the grazed reference site mean minus one standard deviation d) Proportion of non-preferred species not increasing e) Proportion class of non-preferred species not more than one class greater than the grazed reference sites (see Table 11 of the QNH RMP for class descriptions) f) Proportion of declared plant* pest species not increasing g) Proportion class of declared plant* pest species not more than one class greater than the grazed reference sites (see Table 11 of the QNH RMP for class descriptions) h) Conformance of the final landform to the design criteria. i) No contamination causing the land to be unsuitable for the use is present j) Removal of land from the Environmental Management Register or implementation of a Site Management Plan (SMP) where required j) Groundwater monitoring undertaken through the operational life of the CCM and through the full period of rehabilitation establishment (as required by the CCM EA), has indicated no potential impacts to any groundwater values resulting from the rehabilitated landforms. k) Surface water and aquatic ecology monitoring undertaken through the operational life of the CCM and through the period of rehabilitation establishment (as required by the CCM EA), has indicated no potential impacts to any surface water values including aquatic ecology, resulting from the rehabilitated landforms. l) Results of grazing trials within rehabilitated areas at the QNH confirming carrying capacity** *Per the superceded Land Protection (Pest and Stock Route Management) Act 2002 **Grazing trials will not be undertaken within the CCM due to access and spatial limitations.
RM5 | Drainage structure stabilised and fit for purpose (ephemeral drainage channel within grazing pasture | a) Earthworks completed b) Mean groundcover* ≥50% or > the grazed reference site mean minus one standard deviation *Groundcover includes preferred/intermediate species and/or drainage rock contributing to the stabilisation of the channel
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1
MM2
MM3
MM4
MM5
MM6
MM7
MM8
MM9
MM10
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones