{"text_format":"2","workbook":"xlsx","n_sheets":12,"sheets":["Instructions","RA1","RA2","RA3","RA4","RA5","RA6","RA7","RA8","RA9","Rehabilitation Area Milestones","Improvement Area Milestones"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Instructions","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"RA1","index":1,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[0,0,0,10],[2,4,2,10],[3,4,3,10],[4,4,4,10],[5,4,5,10],[4,0,4,3],[5,0,5,3],[1,0,1,3],[1,4,1,10],[2,0,2,3],[3,0,3,3],[9,1,9,10],[18,0,18,10],[15,0,15,10],[16,0,16,10],[17,0,17,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA1"]
["Relevant activities",null,null,null,"Retained infrastructure"]
["Total rehabilitation area size (ha)",null,null,null,2]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Retained infrastructure"]
["Date area is available","Pre-2021","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",2]
["Milestone completed by","2032-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1"]
["RM2",2]
["RM3",2]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA2","index":2,"n_rows":25,"n_cols":11,"rows_kept":25,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA2"]
["Relevant activities",null,null,null,"Water Management Structures"]
["Total rehabilitation area size (ha)",null,null,null,7.8]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Sediment and water supply dams"]
["Date area is available","Pre-2021","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",7.8]
["Milestone completed by","2032-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1"]
["RM2",7.8]
["RM3",7.8]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]
[]
[null,"RM2 @ 2022"]
["West",5.1428379299999998]
["North_East (a)",0.78692446999999999]
["Normanton",1.1323849500000001]
["Total",{"$f":"SUM(B22:B24)","v":7.06214735}]

{"sheet":"RA3","index":3,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA3"]
["Relevant activities",null,null,null,"In-pit Spoil"]
["Total rehabilitation area size (ha)",null,null,null,112.7]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,"10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",112.7]
["Milestone completed by","2026-12-10","2032-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",112.7]
["RM2",112.7]
["RM3",null,112.7]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA4","index":4,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA4"]
["Relevant activities",null,null,null,"Tailings Dam"]
["Total rehabilitation area size (ha)",null,null,null,4.5]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,"xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Cumulative area available (ha)",4.5]
["Milestone completed by","2027-12-10","2036-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",4.5]
["RM2",4.5]
["RM3",null,4.5]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA5","index":5,"n_rows":21,"n_cols":11,"rows_kept":21,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA-5"]
["Relevant activities",null,null,null,"North Highwall"]
["Total rehabilitation area size (ha)",null,null,null,2]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,"xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Cumulative area available (ha)",2]
["Milestone completed by","2030-12-10","2035-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",2]
["RM2",2]
["RM3",null,2]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]
[]
[null,null,3]

{"sheet":"RA6","index":6,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA6"]
["Relevant activities",null,null,null,"Eastern Drain"]
["Total rehabilitation area size (ha)",null,null,null,34.299999999999997]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,null,"10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",34.299999999999997]
["Milestone completed by","2027-12-10","2032-12-10","2036-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",34.299999999999997]
["RM2",null,34.299999999999997]
["RM3",null,null,34.299999999999997]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA7","index":7,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA7"]
["Relevant activities",null,null,null,"Normanton Mine Disturbance"]
["Total rehabilitation area size (ha)",null,null,null,36]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,"xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Cumulative area available (ha)",36]
["Milestone completed by","2027-12-10","2032-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",36]
["RM2",36]
["RM3",null,36]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA8","index":8,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA8"]
["Relevant activities",null,null,null,"Native Ecosystem Rehabilitation Area"]
["Total rehabilitation area size (ha)",null,null,null,30.2]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Native ecosystem"]
["Date area is available","Pre-2021",null,null,null,"10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx","10/12/xxxx"]
["Cumulative area available (ha)",30.2]
["Milestone completed by","2027-12-10","2030-12-10","2032-12-10","2057-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",30.2]
["RM2",null,15.1,30.2]
["RM3",null,null,null,30.2]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"RA9","index":9,"n_rows":19,"n_cols":11,"rows_kept":19,"cut":false,"hidden":false,"merged":[[3,0,3,3],[3,4,3,10],[0,0,0,10],[1,0,1,3],[1,4,1,10],[2,0,2,3],[2,4,2,10],[16,0,16,10],[17,0,17,10],[18,0,18,10],[4,0,4,3],[4,4,4,10],[5,0,5,3],[5,4,5,10],[9,1,9,10],[15,0,15,10]]}
["Post-mining land uses (PMLU)"]
["Rehabilitation area",null,null,null,"RA9"]
["Relevant activities",null,null,null,"North Mine Disturbance"]
["Total rehabilitation area size (ha)",null,null,null,48.4]
["Commencement of first milestone:\n<insert milestone reference>",null,null,null,"Commenced prior to PRCP implementation"]
["PMLU",null,null,null,"Grazing"]
["Date area is available","Pre-2021",null,"xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Cumulative area available (ha)",48.4]
["Milestone completed by","2026-12-10","2032-12-10","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx","xx/xx/xxxx"]
["Milestone Reference","Cumulative area achieved (ha)"]
["RM1",48.4]
["RM2",48.4]
["RM3",null,48.4]
[]
[]
["1) Insert new columns to the yellow table to include further rehabilitation milestone dates."]
["2) Insert new columns to the blue table to match rehabilitation milestone dates."]
["3) Insert new rows to the blue table to include additional rehabilitation milestone references."]
["4) Insert the relevant number in the \"Milestone reference\" column (i.e. RM1)."]

{"sheet":"Rehabilitation Area Milestones","index":10,"n_rows":18,"n_cols":3,"rows_kept":18,"cut":false,"hidden":false,"merged":[[15,0,15,2],[16,0,16,2],[17,0,17,2]]}
["Milestone reference","Rehabilitation milestone","Milestone criteria"]
["RM1","Rehabilitated","Absence of mine infrastructure equipment and materials not required for the PMLU:\n•\tAll non-required services disconnected and removed\n•\tall non-required concrete, bitumen and gravel removed\n•\tall non-required operational pipelines drained and removed\n•\tall fencing that is not part of PMLU requirements removed\n•\tall non-required buildings demolished and/or removed\n•\tall machinery and equipment removed\n•\tall non retained surface water drainage infrastructure removed\n•\tall rubbish removed\n\nAbsence of contaminating materials/ contaminants\n•\tWhere required or applicable, contamination is remediated or removed\n\nEvidence of appropriate landform surface preparation (contour ripping, presence of topdressing, application of amelioration materials where required). Only applicable to rehabilitation post 2021.\n•\tAll bulk earthworks and landform works completed\n•\tSufficient topdressing     material (topsoil or a suitable topsoil substitute) spread over reshaped surfaces\n•\tameliorants have been applied where required to improve soil quality characteristics\n•\tvisible evidence of ripping/discing along the contour (not applicable to historical rehabilitation areas)\n\nRevegetation (seeding, planting or acceptable natural recruitment); seed germination and development of groundcover establishment\n•\tRecords of seeding/planting at design rates/densities\n•\trehabilitation monitoring data demonstrating successful revegetation\n•\tEvidence of target germination rates, planting success and recruitment from initial monitoring"]
["RM2","Stable","Stable landform development through acceptable final landform slopes (i.e. as designed); geotechnical study completed by a suitably qualified person assessing the factor of safety for all final landforms; and drainage design by suitably qualified person\n•\t90% of the final landform achieves slope gradients of 30% or less; and 80% of the final landform achieves slope gradients of 20% or less\n•\tlandform construction of north highwall area (RA5) meets design criteria of slopes <40% with the exception of slopes in area A, which may exceed 40%\n•\tRA5 north highwall area vegetated and assessed by a suitably qualified person as stable with a minimum FOS of 1.5\n•\tconstructed landform in the eastern drainage works area (RA6) meets design criteria of maximum slope gradient of 20%\n•\tRA4 Tailings Dams assessed by a suitably qualified person as stable\n"]
["RM2 (continued)","Stable (Grazing PMLU)","•\tVegetation groundcover exceeds the 70th percentile of reference sites\n•\terosion classification (per the Monitoring and Maintenance Plan (MM Plan)) to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable sites\n•\tno recorded erosion classifications of ‘Severe’ or ‘Extreme’, or areas requiring continuous maintenance\n•\tRetained storage water quality parameters (as defined in the MM Plan) to be below the ‘low risk’ trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZECC/ARMCANZ 2000) with the exception of TDS measured at Urry Road dam (OW21). At this water storage the livestock ‘high risk’ trigger values for TDS will apply, unless sufficient data is available and demonstrates that Urry Road water quality has no detrimental impact on the TDS values of the Bremer River as measured at Station 143107A"]
["RM2 (continued)","Stable (Native Ecosystem  PMLU)","•\tMonitoring shows key species are present including Crows ash (Flindersia australis), Brigalow (Acacia harpophylla) and Whitewood (Atalaya salicifolia)\n•\t≥ 35% of Foliage Projective Cover (FPC) (T1 canopy cover) at analogue site(s)\n•\tlandform is deemed safe for fauna\n•\tlandform construction achieves suitable slope gradients of 30% or less\n•\terosion classification (per the MM Plan) to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable sites\n•\tno recorded erosion classifications of ‘Severe’ or ‘Extreme’, or areas requiring continuous maintenance"]
["RM2 (continued)","Stable (Water Storage PMLU)","•\tSurface water overflows from retained storage, Urry Road dam (OW21) meet the following criteria:\npH: 6.5-9.0; and\nTDS: 10,000 mg/L; or\no\tsurface water quality data demonstrates Urry Road dam water quality has no detrimental impact on the pH and TDS values of the Bremer River as measured at Station 143107A\n•\tSurface water overflows from all other retained storages meet the following criteria:\npH: 6.5-9.0; and\nTDS: 4,000 mg/L\n•\tRetained storage water quality for other parameters (per the MM Plan (Appendix F)) to be below the ‘low risk’ trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZECC/ARMCANZ 2000)."]
["RM2 (continued)","Stable (Retained Infrastructure PMLU)","•\tNo recorded erosion classifications of ‘Severe’ or ‘Extreme’, or areas requiring continuous maintenance\n•\tlandform construction achieves slope gradients of ≤20% with the exception of slopes constructed in excess of 33% to achieve synergy with surrounding topography"]
["RM3","Achievement of target PMLU (sustainable)","Vegetation cover and diversity based on data acquired through the Rehabilitation Monitoring and Maintenance Plan; Land suitability assessment by an appropriately qualified and experienced person; Erosion classification determined based on data acquired through the Rehabilitation Monitoring and Maintenance Plan; Acceptable surface water quality based on water quality monitoring program; Hazard and Safety Assessment by suitably qualified person; Contaminated land assessment to demonstrate no residual contamination"]
["RM3 (continued)","Achievement of target PMLU (sustainable) (Grazing PMLU)","•\tprovide a final rehabilitation report including monitoring records\n•\tassessment of carrying capacity by suitably qualified person demonstrates a sustainable grazing outcome has been achieved\n•\t> 75% of groundcover vegetation comprises recognised pasture species;\n•\trelevant land capability class III / VIII achieved\n•\terosion classification (per the MM Plan (Appendix F)) to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable sites\n•\tno recorded erosion classifications of ‘Severe’ or ‘Extreme’, or areas requiring continuous maintenance"]
["RM3 (continued)","Achievement of target PMLU (sustainable) (Native Ecosystem PMLU)","•\tKey species present including Crows ash (Flindersia australis), Brigalow (Acacia harpophylla), Whitewood (Atalaya salicifolia)\n•\t≥ 50% of number of native flora species/ha as present at analogue sites\n•\t≥ 70% of the T1 canopy height at analogue site(s)\n•\t≥ 50% of FPC (T1 canopy cover) at analogue site(s)\n•\tlandform is deemed safe for fauna\n•\tevidence of low risk of land contamination via a contaminated land assessment report\n•\terosion classification (per the MM Plan (Appendix F)) to be comparable with erosion classifications from nearby equivalent land uses with similar landform parameters to be determined by establishing analogue sites at suitable comparable sites\n•\tno recorded erosion classifications of ‘Severe’ or ‘Extreme’, or areas requiring continuous maintenance"]
["RM3 (continued)","Achievement of target PMLU (sustainable) (Water Storage PMLU)","•\tNo regulated structures to be retained\n•\tall retained water storages (banks and spillways) to be assessed for safety and function by an appropriately qualified person\n•\tSurface water overflows from retained storage, Urry Road dam (OW21) meet the following criteria:\npH: 6.5-9.0; and\nTDS: 10,000 mg/L; or\no\tsurface water quality data demonstrates Urry Road dam water quality has no detrimental impact on the pH and TDS values of the Bremer River as measured at Station 143107A\n•\tSurface water overflows from all other retained storages meet the following criteria:\npH: 6.5-9.0; and\nTDS: 4000 mg/L\n•\tRetained storage water quality for other parameters (per the MM Plan (Appendix F)) to be below the ‘low risk’ trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZECC/ARMCANZ 2000)"]
["RM3 (continued)","Achievement of target PMLU (sustainable) (Retained Infrastructure PMLU","•\tFinal landform survey confirms no built structures remain other than those that form part of a landholder agreement\n•\tno recorded erosion classifications of ‘Severe’ or ‘Extreme’\n•\tlandform construction typically achieves slope gradients of ≤20%, with the exception of slopes constructed in excess of 33% to achieve synergy with surrounding natural topography"]
["RM3 (continued)","Achievement of target PMLU (sustainable) (all PMLUs)","•\tHazard and Safety Assessment demonstrates hazards in rehabilitation areas are of a similar type and not significantly different to hazards in neighbouring similar PMLUs (i.e. low risk)"]
[]
[]
["1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project"]
["2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form."]
["3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones"]

{"sheet":"Improvement Area Milestones","index":11,"n_rows":16,"n_cols":3,"rows_kept":16,"cut":false,"hidden":false,"merged":[[13,0,13,2],[14,0,14,2],[15,0,15,2]]}
["Milestone reference","Management milestone","Milestone criteria"]
["MM1"]
["MM2"]
["MM3"]
["MM4"]
["MM5"]
["MM6"]
["MM7"]
["MM8"]
["MM9"]
["MM10"]
[]
[]
["1) Insert new rows below the table to record more Improvement Area Milestones for the project"]
["2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form."]
["3) See the PRCP guideline before developing site-specific Improvement Area Milestones"]