## Instructions (hidden)
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1; in-pit and out-of-pit waste rock emplacements
Relevant activities |  |  |  | Reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 433.6
Commencement of first milestone: <insert milestone reference> |  |  |  | 2022
PMLU |  |  |  | Light grazing
Date area is available | 2022-12-10 | 2027-12-10 | 1932-12-10 | 1937-12-10 | 1942-12-10 | 1947-12-10 | 1952-12-10 | 2057-12-10 | 2062-12-10 | 10/12/xxxx
Cumulative area available (ha) | 30.2 | 124.1 | 229.7 | 330.3 | 433.6
Milestone completed by | 1927-12-10 | 1932-12-10 | 1937-12-10 | 1942-12-10 | 1947-12-10 | 1952-12-10 | 2057-12-10 | 1962-12-10 | 1967-12-10 | 10/12/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4 | 20.4 | 30.2 | 124.2 | 229.7 | 433.6
RM5 | 20.4 | 30.2 | 124.2 | 229.7 | 433.6
RM6 | 20.4 | 30.2 | 124.2 | 229.7 | 433.6
RM7 |  |  | 20.4 | 30.2 |  | 229.7 | 433.6
RM8 |  |  |  |  | 20.4 | 30.2 |  | 229.7 | 433.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2; Water management infrastructure
Relevant activities |  |  |  | Infrastructure decomissioning (RM2), determine contaminated land status (RM3), reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 41.9
Commencement of first milestone: <insert milestone reference> |  |  |  | 2022
PMLU |  |  |  | Water storage and fauna habitat
Date area is available | Prior to 2022 | 2022-12-10 | 1927-12-10 | 1947-12-10 | 1952-12-10 | 1957-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 4.6 |  |  | 41.9
Milestone completed by | 2022-12-10 | 1927-12-10 | 1932-12-10 | 1952-12-10 | 2057-12-10 | 2062-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2 | 4.6 |  |  | 41.9
RM3 | 4.6 |  |  | 41.9
RM4
RM5 | 4.6 |  |  | 41.85
RM6 | 4.6 |  |  | 41.85
RM7 |  | 4.6 |  |  | 41.85
RM8 |  |  | 4.6 |  |  | 41.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3; Mine infrastructure areas (including major haul roads)
Relevant activities |  |  |  | Infrastructure decomissioning (RM2), determine contaminated land status (RM3), reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 103.9
Commencement of first milestone: <insert milestone reference> |  |  |  | 2043
PMLU |  |  |  | Light grazing
Date area is available | 1947-12-10 | 1952-12-10 | 2057-12-10 |  | 10/12/xxxx
Cumulative area available (ha) | 103.9
Milestone completed by | 1952-12-10 | 2057-12-10 | 2063-12-10 |  | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2 | 103.9
RM3 | 103.9
RM4
RM5 | 103.9
RM6 | 103.9
RM7 |  | 103.9
RM8 |  |  | 103.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4; Residual void
Relevant activities |  |  |  | Reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 13
Commencement of first milestone: <insert milestone reference> |  |  |  | 2043
PMLU |  |  |  | Fauna habitat
Date area is available | 1942-12-10 | 1947-12-10 | 2057-12-10 |  | 10/12/xxxx
Cumulative area available (ha) | 13
Milestone completed by | 1947-12-10 | 2057-12-10 | 1967-12-10 |  | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4 | 13
RM5 | 13
RM6 | 13
RM7 |  | 13
RM8 |  |  | 13
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5; Residual void high wall / low wall
Relevant activities |  |  |  | Reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 54.8
Commencement of first milestone: <insert milestone reference> |  |  |  | 2043
PMLU |  |  |  | Fauna habitat
Date area is available | 1942-12-10 | 1947-12-10 | 2057-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 54.8
Milestone completed by | 1947-12-10 | 2057-12-10 | 1967-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4 | 54.8
RM5 | 54.8
RM6 | 54.8
RM7 |  | 54.8
RM8 |  |  | 54.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7; IPAC and OPAC cell batters
Relevant activities |  |  |  | Reshaping (RM4), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 81.7
Commencement of first milestone: <insert milestone reference> |  |  |  | 2022
PMLU |  |  |  | Light grazing
Date area is available | Prior to 2022 | 2022-12-10 | 2032-12-10 | 2032-12-10 | 2047-12-10 | 2057-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 44.1 | 66.3 |  | 81.7
Milestone completed by | 2022-12-10 | 2027-12-10 | 2037-12-10 | 2042-12-10 | 2052-12-10 | 2062-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2
RM3
RM4 | 44.1 | 66.3 |  | 81.7
RM5 | 44.1 | 66.3 |  | 81.7
RM6 | 44.1 | 66.3 |  | 81.7
RM7 |  |  | 44.1 | 66.3 | 81.7
RM8 |  |  |  |  | 66.3 | 81.7
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8; Exploration tracks and drill pads
Relevant activities |  |  |  | Infrastructure decomissioning (RM2), surface preparation (RM5), revegetation (RM6), target revegetation criteria (RM7), target PMLU (RM8)
Total rehabilitation area size (ha) |  |  |  | 43.9
Commencement of first milestone: <insert milestone reference> |  |  |  | 2022
PMLU |  |  |  | Light grazing
Date area is available | 2022-12-10 | 1927-12-10 | 1932-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 43.9
Milestone completed by | 1927-12-10 | 1932-12-10 | 1937-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1
RM2 | 43.9
RM3
RM4
RM5 | 43.9
RM6 | 43.9
RM7 |  | 43.9
RM8 |  |  | 43.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Installation of capping/cover | Not applicable - only relevant for waste disposal EA rehabilitation areas
RM2 | Infrastructure decommissioning and removal | • All non-required services disconnected and removed • All concrete, bitumen and gravel removed • All operational pipelines drained and removed • All fencing that is not part of PMLU requirements removed • All buildings demolished and/or removed • All machinery and equipment removed • All surface water drainage infrastructure that is not retained in the final landform removed; and • All rubbish removed
RM3 | Determination of contaminated land status | • Where required or applicable, contamination is remediated or removed • Site investigation report prepared by a suitably qualified person which states that the site is safe for the intended use
RM4 | Landform development (reshaping and reprofiling) | • All bulk earthworks and landform works completed • RA1 final landform slope < 8° (14%) • RA7 final landform slope < 9.5° (17%) • RA4 final void floor to be above groundwater table (approx. 280 m AHD or as otherwise determined) • RA4, RA5 final void highwall and low wall maximum slope angles: o Competent rock walls <70° o Competent clays and weathered material <45° o Spoil soils and loose rock faces <25° • Geotechnical assessment confirming that long term geotechnical stability has been achieved for each relevant landform • Installation of graded drains where slope lengths on slopes of 8° (14%) or greater would exceed 160 m constructed to an engineering specification by a suitably qualified person
RM5 | Surface preparation (topsoiling, contour ripping/discing, soil amelioration activities) | • Topdressing material used for each rehabilitation event based on soil testing and agronomic analysis to ensure acceptable sodicity, salinity and pH levels • Visible evidence of ripping/discing along the contour
RM6 | Revegetation (seeding and/or planting) | • Completed seeding of target species at rates determined for each rehabilitation event • Completed planting of tubestock and/or direct seeding of native species at rates determined for each rehabilitation event • >50% survival rate for any given perennial species within 12 months of planting
RM7 | Achievement of target revegetation criteria | Light Grazing and Fauna Habitat PMLUs: • Total percentage of ground foliage cover is >50% • No recorded erosion classifications of ‘Severe’, with stabilisation demonstrated by no increase in erosion ratings over time
RM8 | Achievement of target PMLU | Light Grazing PMLU: • Total percentage of ground foliage cover, organic litter and rock is >75% • A post-mine land suitability of 4 or better • Minimum of 6 pasture and shade tree species (note that shade tree species are to be excluded on RA7) • Evidence of recruitment from rehabilitation monitoring data • No recorded erosion classifications of ‘Severe’, with stabilisation demonstrated by no increase in erosion ratings over time Fauna Habitat PMLU (final void): • Ground foliage cover > 75% • Minimum 14 target vegetation species comprising: o Grasses and forbes ≥ 4 o Mid storey species ≥ 6 o Canopy species ≥ 4 • Evidence of recruitment from monitoring data • No recorded erosion classifications of ‘Severe’ with stabilisation demonstrated by no increase in erosion ratings over time • Fauna survey observations provide evidence of native fauna species utilisation i.e., fauna spotting, scats, and tracks recorded • All safety precautions undertaken in accordance with the relevant legislation—signs comply with AS1319:1994–Safety Signs for the Occupational Environment • Access restrictions; either berms or fencing in place • Void highwalls and low walls are internally draining Water Storage PMLU: • All retained water storages (banks and spillways) to be assessed for safety by an appropriately qualified person • Surface water overflows from retained storages meets the following criteria: o pH: 6.5-9.0 o EC: < 950 µS/cm o SS: < 285 mg/L • Retained storage water quality parameters to be below the ‘low risk’ trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZECC and ARMCANZ 2000) All PMLUs: • Hazard and Safety Assessment demonstrates hazards in rehabilitation areas are of a similar type and not significantly different to hazards in neighbouring similar PMLUs • Surface water draining from rehabilitated areas meets the following criteria: o pH: 6.5-9.0 o EC: < 950 µS/cm o SS: < 285 mg/L o All other surface water quality parameters to be below the ‘low risk’ trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZECC and ARMCANZ 2000) • On-lease monitoring bores meet groundwater trigger levels as per Table 3 of the EA as refined by ongoing water quality monitoring
RM9
RM10
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones
44.1