## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Spoil (<10% slope)
Total rehabilitation area size (ha) |  |  |  | 2037
Commencement of first milestone: RM2 |  |  |  | 2029-12-10
PMLU |  |  |  | Low intensity grazing
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1629.9 | 2037 | 2037 | 2037
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10 | 2075-12-10
Milestone Reference | 2032-12-10: Cumulative area achieved (ha)
RM4 | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1618.5 | 2037
RM9 | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1363.7 | 2037
RM10 | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1363.7 | 2037
RM12 | 146.9 | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1363.7 | 2037
RM14 |  | 146.9 | 279.6 | 462.4 | 494.4 | 789.4 | 1028 | 1618.5 | 2037
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Spoil (>10% slope)
Total rehabilitation area size (ha) |  |  |  | 3164.1
Commencement of first milestone: RM2 |  |  |  | 2029-12-10
PMLU |  |  |  | Marginal grazing
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 2488.9 | 3164.1 | 3164.1 | 3164.1
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10 | 2075-12-10
Milestone Reference | 2032-12-10: Cumulative area achieved (ha)
RM4 | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 2441.2 | 3164.1
RM9 | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 1818.1 | 3164.1
RM10 | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 1818.1 | 3164.1
RM12 | 196.8 | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 1818.1 | 3164.1
RM14 |  | 196.8 | 582.4 | 824.5 | 962.9 | 1353.6 | 1606.6 | 2441.2 | 3164.1
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Reinstated drainage
Total rehabilitation area size (ha) |  |  |  | 93.5
Commencement of first milestone: RM3 |  |  |  | 2039-12-10
PMLU |  |  |  | Native ecosystem
Date area is available | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10
Cumulative area available (ha) | 80 | 80 | 80 | 93.5 | 93.5 | 93.5
Milestone completed by | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 1962-12-10 | 2067-12-10
Milestone Reference | Cumulative area achieved (ha)
RM5 | 80 |  |  | 93.5
RM9 | 80 |  |  |  | 93.5
RM11 | 80 |  |  |  | 93.5
RM13 |  | 80 |  |  |  | 93.5
RM15 |  |  | 80 |  |  | 93.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure area
Total rehabilitation area size (ha) |  |  |  | 675
Commencement of first milestone: RM1 |  |  |  | 2028-12-10
PMLU |  |  |  | Low intensity grazing
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 107.2 | 107.2 | 107.2 | 139.1 | 147.4 | 546.8 | 675 | 675 | 675
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10 | 2075-12-10
Milestone Reference | 2032-12-10: Cumulative area achieved (ha)
RM1 | 2032-12-10: 107.2; 2047-12-10: 139.1; 2052-12-10: 147.4; 2057-12-10: 546.8; 2062-12-10: 675
RM6 | 2032-12-10: 107.2; 2047-12-10: 139.1; 2052-12-10: 147.4; 2057-12-10: 177.2; 2062-12-10: 675
RM9 | 2032-12-10: 107.2; 2047-12-10: 139.1; 2052-12-10: 147.4; 2057-12-10: 177.2; 2062-12-10: 675
RM10 | 2032-12-10: 107.2; 2047-12-10: 139.1; 2052-12-10: 147.4; 2057-12-10: 177.2; 2062-12-10: 675
RM12 | 25 | 107.2 |  |  | 139.1 | 147.4 | 177.2 | 675
RM14 |  | 25 | 107.2 |  |  | 139.1 | 147.4 | 177.2 | 675
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Retained infrastructure
Total rehabilitation area size (ha) |  |  |  | 64.3
Commencement of first milestone: RM15 |  |  |  | 2044-12-10
PMLU |  |  |  | Retained infrastructure
Date area is available | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10
Cumulative area available (ha) | 4.4 | 4.4 | 4.4 | 57 | 64.3
Milestone completed by | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 1967-12-10
Milestone Reference | Cumulative area achieved (ha)
RM17 | 4.4 |  |  | 57 | 64.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Dams
Total rehabilitation area size (ha) |  |  |  | 29
Commencement of first milestone: RM5 |  |  |  | 2029-12-10
PMLU |  |  |  | Low intensity grazing
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 2.8 | 2.8 | 2.8 | 3.4 | 3.7 | 28.9 | 29 | 29 | 29
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10 | 1975-12-10
Milestone Reference | Cumulative area achieved (ha)
RM7 | 2.8 |  |  | 3.4 |  | 28.9 | 29
RM9 | 2.8 |  |  | 3.4 |  |  | 29
RM10 | 2.8 |  |  | 3.4 |  |  | 29
RM12 |  | 2.8 |  |  | 3.4 |  | 3.4 | 29
RM14 |  |  | 2.8 |  |  | 3.4 |  | 28.9 | 29
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Retained dams
Total rehabilitation area size (ha) |  |  |  | 60.5
Commencement of first milestone: RM14 |  |  |  | 2029-07-01
PMLU |  |  |  | Water containment
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 4.9 | 6 | 6 | 7.4 | 7.4 | 39 | 60.5
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10
Milestone Reference | Cumulative area achieved (ha)
RM16 | 4.9 | 6 |  | 7.4 |  | 39 | 60.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | In-pit tailings disposal
Total rehabilitation area size (ha) |  |  |  | 45.8
Commencement of first milestone: RM6 |  |  |  | 2059-12-10
PMLU |  |  |  | Low intensity grazing
Date area is available | 2057-12-10
Cumulative area available (ha) | 45.8 | 45.8 | 45.8 | 45.8
Milestone completed by | 2062-12-10 | 2067-12-10 | 2075-12-10 | 1980-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 18.1 | 27.7
RM3 |  | 18.1 | 27.7
RM8 |  | 18.1 | 27.7
RM10 |  | 18.1 | 27.7
RM12 |  |  | 18.1 | 45.8
RM14 |  |  | 18.1 | 45.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | Other areas of disturbance approved within approved disturbance extent
Total rehabilitation area size (ha) |  |  |  | 137.9
Commencement of first milestone: RM7 |  |  |  | 2039-12-10
PMLU |  |  |  | Low intensity grazing
Date area is available | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10
Cumulative area available (ha) | 40.8 | 40.8 | 40.8 | 137.9 | 137.9 | 137.9
Milestone completed by | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10
Milestone Reference | Cumulative area achieved (ha)
RM9 | 40.8 |  |  | 137.9
RM10 | 40.8 |  |  |  | 137.9
RM12 |  | 40.8 |  |  | 137.9
RM14 |  |  | 40.8 |  | 40.8 | 137.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities |  |  |  | Final void
Total size (ha) |  |  |  | 744
Commencement of first milestone: MM1 & MM2 |  |  |  | 2030-12-10
NUMA |  |  |  | Void
Date area is available | 2027-12-10 | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10
Cumulative area available (ha) | 37 | 165 | 235 | 265 | 265 | 414 | 744 | 744
Milestone completed by | 2032-12-10 | 2037-12-10 | 2042-12-10 | 2047-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10
Milestone Reference | 2032-12-10: Cumulative area achieved (ha)
MM1 | 37 | 37 | 165 | 235 | 265 |  | 744
MM2 | 37 | 37 | 165 | 235 | 265 |  | 744
MM3 |  | 37 | 37 | 235 |  | 265 | 414 | 744
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | • All non-required services disconnected and removed; • Remove all concrete bitumen and gravel roads where not to be retained; • All operational pipelines drained and removed; • All fencing that is not part of PMLU requirements removed; • All buildings demolished and/or removed off-site where not to be retained; • All machinery and equipment removed; • All surface water drainage infrastructure that is not retained in the final landform removed; and • All rubbish removed.
RM2 | In-pit tailings dewatering | • Assessed as geotechnically stable for base layer placement by an appropriately qualified person
RM3 | Base layer placement for in-pit tailings | • All bulk earthworks associated with placement criteria of 1.7m of suitable cover material; • Cover material meets design specifications: o P90 < 250mm; o P50 < 2mm; o P25 < 0.025mm; o Emerson aggregate class: 3-6; o pH: 6-9; o EC (dS/m) < 3500; o ESP (%) < 6; and o Rock armour on external slopes: P90: 250 - 350mm at >75% cover
RM4 | Landform development of spoil (reshaping and reprofiling) | • All bulk earthworks completed; • Flood protection bunds meet design specifications, including minimum rehabilitation grade on slopes; and o Selective placement of non-erosive materials and/or rock mulch protection to ensure landform stability. • Batter slopes meet design specifications; o RA1: 100% slopes are <10% grade; o RA2: 98% of slopes <17% grade and 2% of slopes <21% grade o RA2: Maximum continuous slope length of 133m. • Bench features to dissipate surface water flow; and • As constructed landform achieves design criteria for geotechnical stability - Factor of Safety (FOS) ≥ 1.5.
RM5 | Landform developed of reinstated drainage | • The Mackenzie River Anabranch diversion constructed in accordance with EA - Schedule H Conditions and associated design plans; • All bulk earthworks completed to achieve landform design, including embankments with 1V:6H slope and rock-lining protection; and • Assessed as geotechnical stable by an appropriately qualified person.
RM6 | Landform development of infrastructure areas | • All bulk earthworks completed to reshape landform to final design; • Certification provided by an appropriately qualified person confirms that drainage features are constructed to design specifications; and • As constructed landform achieves design criteria for geotechnical stability - FOS ≥ 1.5.
RM7 | Landform development of dams | • All bulk earthworks completed to reshape landform to final design; • Certification provided by an appropriately qualified person confirms that drainage features are constructed to design specifications; and • As constructed landform achieves design criteria for geotechnical stability - FOS ≥ 1.5.
RM8 | Topsoil placement, sediment control and landform development for in-pit tailings | • Soil health and suitability is assessed and documented by an appropriately qualified person. Where required, ameliorants such as gypsum are added to improve soil quality characteristics; • All bulk earthworks associated with placement of 0.6m of topsoil over tailings completed; • Cover material meets design specifications; and o P90 < 50mm; o P50 < 2mm; o P25 < 0.025mm; o Emerson aggregate class: 3; o pH: 6-9; o EC (dS/m) < 1500; and o ESP (%) < 6; o Organic matter content > 0.5% in the top 50 cm; and o Rock cover: P90: 250 – 350mm at 25% to 35% cover • Installation of monitoring equipment to verify design criteria by an appropriately qualified person • Assessed as geotechnical stable by a suitably qualified person
RM9 | Surface preparation (topdressing, contour ripping, soil amelioration) | • Soil health and suitability is assessed and documented by an appropriately qualified person2. Where required, ameliorants such as gypsum are added to improve soil quality characteristics; • Presence of topsoil with a minimum thickness of 200mm across the rehabilitated area following landform development; • Ripping that penetrates at least 600mm into soil profile/subsoil profile has been completed along the contour of slopes; • Topsoil to meet the following suitability targets; and o pH in the range of 6 - 8.5; o ECSAT (dS/m) ≤4; and o ESP (%) < 6.
RM10 | Revegetation for low intensity grazing and marginal grazing | • Complete seeding of all topsoil surfaces using a selection of the recommended species mix for each soil characteristic type in Table RM10 – Recommended species selected for revegetation or species associated with the intended land use; • Seeding of target key species completed at a sowing rate of 10-15 kg/ha or as specified in Table RM10 – Recommended species selected for revegetation; • Application of hay mulch at time of seeding, at a rate of 8 t/ha
RM11 | Revegetation for native ecosystem | • Complete seeding of all topsoil surfaces using a selection of the recommended species mix in Table RM11 – Recommended species selected for revegetation or species associated with appropriate regional ecosystem; • Revegetation completed for grass mix at a rate of 10-15 kg/ha or as specified in Table RM11 - Recommended species selected for revegetation; • Revegetation completed for tree/shrub mix at 2-3 kg/ha or as specified in Table RM11 - Recommended species selected for revegetation; and • Application of hay mulch at time of seeding, at a rate of 8 t/ha
RM12 | Achievement of target revegetation criteria - low intensity grazing and marginal grazing | • RA1, RA4, RA6, RA8, RA9: Rehabilitation polygons have a median fractional vegetation cover greater than the first quartile of reference polygons for at least 85% of all sample times, as determined using the satellite-derived fractional vegetation cover method • RA2: Total percentage of groundcover to be >80% • No severe nor extreme gully erosion or washout features; and • Weed density not significantly greater than reference sites.
RM13 | Achievement of target revegetation criteria - native ecosystem | • Establishment of stabilising groundcovers species within channels >80% • Establishment of fringing native ecosystem on banks to resemble a benchmark for RE 11.3.3 as follows; o trees ≥ 10 / ha; and o shrubs ≥ 4% cover. • Species richness and composition between the means of grass, forb and woody stem diversity is not statistically significantly different (p>0.05) across equivalent analogue and rehabilitation sites • No severe nor extreme gully erosion or washout features; and • Weed density not significantly greater than reference sites.
RM14 | Achievement of PMLU to stable condition - low intensity grazing and marginal grazing | • Land suitability assessment by an appropriately qualified person certifies that land has achieved a post-mine land suitability class of: o 3 or better for low intensity grazing; and o 4 or better for marginal grazing. • Surface water quality draining from rehabilitated areas complies with the following limits; o pH in the range 6.5 – 8.5; and o field EC (µS/cm) of < 1000 for surface water draining towards Blackwater Creek and of <400 for surface water draining towards the Mackenzie River. • Receiving environment water quality measured at the downstream sites achieves ANZECC guidelines for water quality in aquatic ecosystems or upstream water quality data; • RA8: Geotechnical assessment of in-pit tailings settlement and consolidation by an appropriately qualified person indicating landform stability; • Evidence of recruitment from rehabilitation monitoring data; • No severe nor extreme gully erosion or washout features; and • Assessed as geotechnically stable by an appropriately qualified person.
RM15 | Achievement of PMLU to stable condition native ecosystem | • Receiving environment water quality measured at the downstream sites achieves ANZECC guidelines for water quality in aquatic ecosystems or upstream water quality data; • Evidence of flora recruitment from rehabilitation monitoring data; • Fauna survey observation provides evidence of native fauna utilisation i.e., fauna spotting, scats, and tracks recorded; • No evidence of severe nor extreme gully erosion or washout features; • Installation of fencing to exclude cattle use and prevent erosion; • Monitoring reports indicate design requirements have been met for the Mackenzie River Anabranch diversion in accordance with EA - Schedule H Conditions and associated design plans; • Geotechnical assessment by an appropriately qualified person confirming that long term geotechnical stability has been achieved for each relevant landform; and • Report prepared by an appropriately qualified person confirming the target PMLU has been achieved and the ecosystem is self-sustaining
RM16 | Achievement of PMLU to stable condition - dams | • All retained water storages to be assessed and approved as safe and stable by an appropriately qualified person; and • Retained water storage water quality parameters to be below the trigger values for livestock drinking water defined in Australian and New Zealand Guidelines for Fresh and Marine Water Quality (ANZG 2018)
RM17 | Achievement of PMLU to stable condition -retained infrastructure | • All retained structures and landforms to be assessed and approved as safe and stable by an appropriate qualified person; and • Final landform survey confirms no built structures remain other than those that form part of a landholder agreement.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of final landform design | • Final void highwall with the following angles: o ≤70° for competent rock; and o ≤45° for incompetent rock. • Final void low-wall dumps: o ≤21° average slope angle o Floor preparation of voids by ripping and blasting to raise margins of safety as required • Voids are assessed to be geotechnically stable by an appropriately qualified person; • Predictive modelling undertaken by an appropriately qualified person, confirming that the voids will remain as a groundwater sink and that there is no risk of contamination post mining.
MM2 | Achievement of surface and safety requirements | • Adequate bunding in place, confirming to be geotechnically stable by an appropriately qualified person; o Safety bunds constructed ≥1.5m in height, battered at 1:3 grade, and located within 10m of final highwall crests • Bunding is confirmed to be capable of maintaining stability under a PMF scenario.; and • Perimeter fencing and signage erected to prevent access to fauna and humans
MM3 | Achievement of sufficient improvement | • Voids assessed to be geotechnically stable by a suitably qualified person, achieving: o a modelled FOS of ≥ 1.5 for the in-situ pit walls before maximum in-pit water level is reached; o a modelled FOS ≥ 1.5 for the in-situ pit walls after maximum in-pit water level is reached; o a FOS ≥1.5 spoil pit walls above the maximum in-pit water level; and o an 11.5° angle for the spoil pit walls below the maximum predicted water level. • Certification from an appropriately qualified person that water level in each residual void will not cause environmental harm to the surrounding environment, and the voids act as groundwater sinks to the receiving groundwater environment o Mackenzie North and Plains Pit – water balance modelling confirms that long-term pit water levels will remain below the alluvium and paleochannels for the prevention of potential groundwater contamination
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones