## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 - Main Pit Low Wall
Relevant activities |  |  |  | Rehabilitating pit low wall
Total rehabilitation area size (ha) |  |  |  | 137.04
Commencement of first milestone: RM1 |  |  |  | 2029-08-08
PMLU |  |  |  | Grassy Open Woodlands
Date area is available | 2029-08-08
Cumulative area available (ha) | 137.04 | 137.04 | 137.04 | 137.04 | 137.04 | 137.04 | 137.04 | 137.04 | 137.04 | 137.04
Milestone completed by | 2031-07-13 | 2031-07-24 | 2032-05-24 | 2032-06-01 | 2032-12-24 | 2033-01-24 | 2033-02-01 | 2033-02-10 | 2038-07-02 | 2044-03-31
Milestone Reference | 2031-07-13: Cumulative area achieved (ha)
RM3a | 2031-07-13: 137.04
RM3b | 2031-07-24: 36.65
RM4a | 2032-05-24: 100.39
RM4b | 2032-06-01: 100.39
RM5a | 2032-12-24: 137.04
RM5b | 2033-01-24: 137.04
RM6a | 2033-02-01: 137.04
RM6b | 2033-02-10: 137
RM7 | 2038-07-02: 137
RM9 | 2044-03-31: 137
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 - South Pit Low Wall
Relevant activities |  |  |  | Rehabilitating pit low wall
Total rehabilitation area size (ha) |  |  |  | 98
Commencement of first milestone: RM1 |  |  |  | 2027-12-02
PMLU |  |  |  | Grassy Open Woodlands
Date area is available | 2027-12-02
Cumulative area available (ha) | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
Milestone completed by | 2029-08-08 | 2031-07-28 | 2031-11-13 | 2031-11-22 | 2033-02-05 | 2033-03-21 | 2033-03-28 | 2033-04-04 | 2038-07-02 | 2044-03-31
Milestone Reference | 2029-08-08: Cumulative area achieved (ha)
RM3a | 2029-08-08: 98
RM3b | 2031-07-28: 29.17
RM4a | 2031-11-13: 68.83
RM4b | 2031-11-22: 68.83
RM5a | 2033-02-05: 98
RM5b | 2033-03-21: 98
RM6a | 2033-03-28: 98
RM6b | 2033-04-04: 98
RM7 | 2038-07-02: 98
RM9 | 2044-03-31: 98
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 - South West Dump
Relevant activities |  |  |  | Rehabilitating out of pit dump
Total rehabilitation area size (ha) |  |  |  | 36.49
Commencement of first milestone: RM1 |  |  |  | 2031-12-22
PMLU |  |  |  | Grassy Open Woodlands
Date area is available | 2031-12-22
Cumulative area available (ha) | 21.31 | 21.31 | 21.31 | 21.31 | 21.31 | 36.49 | 36.49 | 36.49 | 36.49
Milestone completed by | 2033-05-22 | 2031-12-04 | 2031-12-15 | 2033-02-15 | 2033-02-24 | 2033-05-29 | 2033-06-06 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3b | 21.31
RM4a |  | 12.36
RM4b |  |  | 12.36
RM5a |  |  |  | 20.9
RM5b |  |  |  |  | 20.9
RM6a | [5 empty] | 36.49
RM6b | [6 empty] | 36.49
RM7 | [7 empty] | 36.49
RM9 | [8 empty] | 36.49
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 - External Dumps_Miscellaneous
Relevant activities |  |  |  | Rehabilitating out of pit dumps
Total rehabilitation area size (ha) |  |  |  | 109.63
Commencement of first milestone: RM1 |  |  |  | 2031-07-13
PMLU |  |  |  | Grassy Open Woodlands
Date area is available | 2031-07-13
Cumulative area available (ha) | 3.03 | 88.71 | 88.71 | 88.71 | 91.66 | 91.66 | 109.63 | 109.63 | 109.63 | 109.63
Milestone completed by | 2031-07-19 | 2033-05-24 | 2032-06-29 | 2032-07-06 | 2033-04-10 | 2033-05-02 | 2033-05-31 | 2033-06-08 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3a | 3.03
RM3b |  | 88.71
RM4a |  |  | 20.93
RM4b |  |  |  | 20.93
RM5a |  |  |  |  | 91.66
RM5b | [5 empty] | 91.66
RM6a | [6 empty] | 109.63
RM6b | [7 empty] | 109.63
RM7 | [8 empty] | 109.63
RM9 | [9 empty] | 109.63
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5 - Haul Roads
Relevant activities |  |  |  | Rehabilitating haul roads
Total rehabilitation area size (ha) |  |  |  | 46.9
Commencement of first milestone: RM1 |  |  |  | 2032-07-06
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2032-07-06
Cumulative area available (ha) | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9
Milestone completed by | 2032-07-12 | 2033-05-21 | 2033-06-18 | 2033-06-25 | 2033-07-02 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3b | 46.9
RM5a |  | 46.9
RM5b |  |  | 46.9
RM6a |  |  |  | 46.9
RM6b |  |  |  |  | 46.9
RM8 | [5 empty] | 46.9
RM10 | [6 empty] | 46.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6 - Mine Industrial Area
Relevant activities |  |  |  | Infrastructure removal and rehabilitation of land
Total rehabilitation area size (ha) |  |  |  | 9.3
Commencement of first milestone: RM1 |  |  |  | 2032-06-22
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2032-06-22
Cumulative area available (ha) | 0 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3 | 9.3
Milestone completed by | 2032-06-22 | 2032-07-31 | 2032-08-07 | 2032-08-14 | 2032-08-22 | 2032-08-29 | 2032-09-05 | 2038-07-02 | 2044-03-31
Milestone Reference | 2032-06-22: Cumulative area achieved (ha)
RM1 | 2032-06-22: 0
RM2 | 2032-07-31: 9.3
RM3b | 2032-08-07: 9.3
RM5a | 2032-08-14: 9.3
RM5b | 2032-08-22: 9.3
RM6a | 2032-08-29: 9.3
RM6b | 2032-09-05: 9.3
RM8 | 2038-07-02: 9.3
RM10 | 2044-03-31: 9.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7 - Orica Compound
Relevant activities |  |  |  | Rehabilitating laydown area
Total rehabilitation area size (ha) |  |  |  | 1.41
Commencement of first milestone: RM1 |  |  |  | 2031-08-05
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2031-08-05
Cumulative area available (ha) | 1.41 | 1.41 | 1.41 | 1.41 | 1.41 | 1.41 | 1.41
Milestone completed by | 2031-08-06 | 2033-04-11 | 2033-05-02 | 2033-05-09 | 2033-05-16 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3b | 1.41
RM5a |  | 1.41
RM5b |  |  | 1.41
RM6a |  |  |  | 1.41
RM6b |  |  |  |  | 1.41
RM8 | [5 empty] | 1.41
RM10 | [6 empty] | 1.41
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8 - Run of Mine (ROM)
Relevant activities |  |  |  | Infrastructure removal and rehabilitation of land
Total rehabilitation area size (ha) |  |  |  | 19.86
Commencement of first milestone: RM1 |  |  |  | 2032-07-24
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2032-07-24
Cumulative area available (ha) | 0 | 19.86 | 19.86 | 19.86 | 19.86 | 19.86 | 19.86 | 19.86 | 19.86
Milestone completed by | 2032-07-24 | 2032-10-12 | 2032-10-25 | 2032-11-14 | 2032-11-28 | 2033-05-03 | 2033-05-11 | 2038-07-02 | 2044-03-31
Milestone Reference | 2032-07-24: Cumulative area achieved (ha)
RM1 | 2032-07-24: 0
RM2 | 2032-10-12: 19.86
RM3b | 2032-10-25: 19.86
RM5a | 2032-11-14: 19.86
RM5b | 2032-11-28: 19.86
RM6a | 2033-05-03: 19.86
RM6b | 2033-05-11: 19.86
RM8 | 2038-07-02: 19.86
RM10 | 2044-03-31: 19.86
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9 - Stripped Topsoil
Relevant activities |  |  |  | Rehabilitating areas that have been stripped of topsoil
Total rehabilitation area size (ha) |  |  |  | 10.63
Commencement of first milestone: RM1 |  |  |  | 2031-08-06
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2031-08-06
Cumulative area available (ha) | 10.63 | 10.63 | 10.63 | 10.63 | 10.63 | 10.63 | 10.63
Milestone completed by | 2031-08-07 | 2033-04-19 | 2033-05-09 | 2033-05-16 | 2033-06-18 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3b | 10.63
RM5a |  | 10.63
RM5b |  |  | 10.63
RM6a |  |  |  | 10.63
RM6b |  |  |  |  | 10.63
RM8 | [5 empty] | 10.63
RM10 | [6 empty] | 10.63
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10 - Topsoil Stockpiles on Natural RL
Relevant activities |  |  |  | Rehabilitating areas following topsoil stockpile removal
Total rehabilitation area size (ha) |  |  |  | 40.4
Commencement of first milestone: RM1 |  |  |  | 2033-05-24
PMLU |  |  |  | Low-Intensity Grazing
Date area is available | 2033-05-24
Cumulative area available (ha) | 40.4 | 40.4 | 40.4 | 40.4 | 40.4
Milestone completed by | 2033-05-30 | 2033-06-20 | 2033-06-28 | 2038-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM3b | 40.4
RM6a |  | 40.4
RM6b |  |  | 40.4
RM8 |  |  |  | 40.4
RM10 |  |  |  |  | 40.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA11
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA11 - North West Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 78.9
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 78.9 | 78.9
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 78.9
RM9 |  | 78.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA12
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 12 - North East Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 69.3
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 69.3 | 69.3
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 69.3
RM9 |  | 69.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA13
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 13 - South East Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 53.6
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 53.6 | 53.6
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 53.6
RM9 |  | 53.6
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA14
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 14 - Creek Diversion North Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 2.5
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 2.5 | 2.5
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 2.5
RM9 |  | 2.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA15
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 15 - Creek Diversion South Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 13.4
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 13.4 | 13.4
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 13.4
RM9 |  | 13.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA16
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 16 - South West dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 103.74
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 103.74 | 103.74
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 103.74
RM9 |  | 103.74
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA17
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 17 - Main Dump
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 46.5
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 46.5 | 46.5
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 46.5
RM9 |  | 46.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA18
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 18 - Sandhurst Creek Diversion
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 67.1
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Grassy Open Woodlands
Date area is available | 2033-07-02
Cumulative area available (ha) | 67.1 | 67.1
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM7 | 67.1
RM9 |  | 67.1
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA19
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 19 - East Irrigation Area
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 20.4
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Low-Intensity Grazing
Date area is available | 2033-07-02
Cumulative area available (ha) | 20.4 | 20.4
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM8 | 20.4
RM10 |  | 20.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA20
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 20 - South Pit High Wall
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 9.8
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Low-Intensity Grazing
Date area is available | 2033-07-02
Cumulative area available (ha) | 9.8 | 9.8
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM8 | 9.8
RM10 |  | 9.8
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA21
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 21 - ROM Dam Surrounds
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 0.9
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Low-Intensity Grazing
Date area is available | 2033-07-02
Cumulative area available (ha) | 0.9 | 0.9
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM8 | 0.9
RM10 |  | 0.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA22
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA 22 - TLO Road
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 2.7
Commencement of first milestone: RM1 |  |  | 2033-07-02
PMLU |  |  | Low-Intensity Grazing
Date area is available | 2033-07-02
Cumulative area available (ha) | 2.7 | 2.7
Milestone completed by | 2033-07-02 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
RM8 | 2.7
RM10 |  | 2.7
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA 1
Post-mining land uses (PMLU)
Rehabilitation area |  |  | IA 1 - Western Residual Void
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 78
Commencement of first milestone: RM1 |  |  | 2042-03-31
PMLU |  |  | NUMA
Date area is available | 2042-03-31
Cumulative area available (ha) | 78 | 78
Milestone completed by | 2043-03-31 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
MM1 | 78
MM2 |  | 78
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA 2
Post-mining land uses (PMLU)
Rehabilitation area |  |  | IA 2 - Southern Residual Void
Relevant activities |  |  | Landform meeting completion criteria
Total rehabilitation area size (ha) |  |  | 11.58
Commencement of first milestone: RM1 |  |  | 2042-03-31
PMLU |  |  | NUMA
Date area is available | 2042-03-31
Cumulative area available (ha) | 11.58 | 11.58
Milestone completed by | 2043-03-31 | 2044-03-31
Milestone Reference | Cumulative area achieved (ha)
MM1 | 11.58
MM2 |  | 11.58
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure Decommissioning and Removal | a) All services disconnected , except those to be retained by landholder by agreement. b) All buildings demolished and removed, except those to be retained by landholder by agreement.
RM2 | Remediation of Contaminated Land | a) Contaminated land assessment by suitably qualified person b) Removal of contaminated land c) Assessment by suitable qualified person that contaminated land has been removed
RM3a | Landform Shaping | External Batters a) Landform profiled to ≤ 25% b) Benches to be installed at 15m vertical lift intervals, width of benches determined by size of equipment delivering topsoil. Low Wall Spoil a) Landform profiled to ≤ 25% b) Benches to be installed at 30m vertical lift intervals , width of benches to be 30m. c) Shaping above 210 RL near Western final void, with any fill below this level at angle of repose d) Shaping above RL 200 near Southern final void, with any fill below this at angle of repose
RM3b | Final Trim | a) Final trim of some areas that have been shaped and require an even surface prior to topsoil application
RM4a | Rock Mulch Haulage | a) Haulage and placement of competent rock mulch onto shaped rehabilitated areas
RM4b | Rock Mulch Application | a) Rock mulched areas reshaped to surface ≤ 25% b) Rock mulch applied at a minimum of 0.5m thick to reshaped surfaces c) Rock mulch not required for shaped areas that are < 5% slope
RM5a | Topsoil Haulage | a) Haulage and placement of topsoil on rock mulch rehabilitated areas b) Haulage and placement of topsoil on topsoil only rehabilitated areas
RM5b | Topsoil Spreading | a) Spreading topsoil ≥ 0.1m thick on rock mulch areas b) Spreading topsoil ≥ 0.2m thick on topsoil only areas
RM6a | Deep Ripping | a) Areas deep ripped to mix topsoil into rock mulch substrate
RM6b | Deep Ripping and Seeding | a) Areas deep ripped on the contour to provide seed bed and surface erosion control b) Seed applied at set rates for Grassy Open Woodlands and Low-Intensity Grazing post mining land uses
RM7 | Revegetation (Grassy Open Woodlands) | a) Vegetation has been established and meets interim Grassy Open Woodlands performance requirements as follows: i) Effective rooting depth > 0.5 m ii) No acid or saline seepage areas iii) Absence of active rills and gullies iv) Ground cover stable or improving (may include dead and alive material or rocky debris) v) Developing vegetation consisting of native trees, shrubs and grasses vi) Areas of contamination have been remediated and monitored
RM8 | Revegetation (Low-intensity grazing) | a) Vegetation has been established and meets interim Low-intensity Grazing performance requirements as follows: i) Effective rooting depth > 0.5 m ii) No acid or saline seepage areas iii) Absence of active rills and gullies iv) Ground cover stable or improving (may include dead and alive material or rocky debris) v) Developing vegetation consisting of native trees, shrubs and grasses vi) Areas of contamination have been remediated and monitored
RM9 | Achievement of a Stable Post Mining Land Use (Grassy Open Woodlands) | a) Rehabilitation dump is geotechnically stable with FOS ≥ 1.5 b) No active gully erosion present c) External batters ≤ 25% slopes covered with minimum 0.5 m thick competent rock mulch d) Top of dump ≤ 5% slopes covered with minimum 0.2 m thick topsoil e) No acid or saline seepage areas f) Water quality run-off EC < 1,000 µS/cm and pH 6.0 – 9.0 g) ≥ 2 native tree and shrub species present h) ≥ 3 perennial grass species present i) Effective rooting depth > 0.5 m j) Invasive weed species comprise < 10% of groundcover k) Livestock excluded from area
RM10 | Achievement of a Stable Post Mining Land Use (Low-intensity Grazing) | a) No active gully erosion present b) All areas have slopes ≤ 5% covered with minimum 0.2 m thick topsoil c) No acid or saline seepage areas d) Water quality run-off < 1,000 µS/cm and pH 6.0 – 9.0 e) Vegetative ground cover ≥ 50% f) ≥ 3 perennial pasture and shrub species present g) Effective rooting depth > 0.5 m h) Invasive weed species comprise < 10% of groundcover
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Achievement of structural stability | a) Highwall and end wall maximum slope ≤ 70 degrees projected to surface b) Assessment report by Registered Professional Engineer of Queensland(RPEQ) on the geotech stability of final voids. c) Closure bund installed minimum 50 m from pit crest or distance equal to FOS of 1.5 d) 0.1 AEP flood event in Sandhurst Creek diversion does not enter final void
MM2 | Achievement of safety and minimisation of environmental harm | a) High wall and end wall bund constructed of competent materials ≥ 2m high and minimum 50 m setback from crest (≥ FOS of 1.5). b) No public access to highwalls / endwalls (bunding / fencing / signage as required). c) Assessment report by Registered Professional Engineer of Queensland (RPEQ) on the geotech stability of final voids d) Surface water and groundwater quality of receiving waters meets the requirements of Schedule W of the Environmental Authority. e) Voids have no adverse environmental impacts on basalt aquifer
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones