## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Infrastructure
Total rehabilitation area size (ha) |  |  |  | 78.15
Commencement of first milestone: RM1 |  |  |  | 2043
PMLU |  |  |  | Beef Cattle Grazing
Date area is available | 2042-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 78.15
Milestone completed by | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 78.15
RM2 | 78.15
RM4 | 78.15
RM5 | 78.15
RM6 | 78.15
RM7 |  | 78.15
RM8 |  | 78.15
RM9 |  | 78.15
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | General mining activity
Total rehabilitation area size (ha) |  |  |  | 445.83
Commencement of first milestone: RM4 |  |  |  | 2029
PMLU |  |  |  | Beef Cattle Grazing
Date area is available | 2029-12-10 | 2034-12-10 | 2039-12-10 | 2043-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 118.87 | 167.75 | 348.6 | 445.83
Milestone completed by | 2031-12-10 | 2036-12-10 | 2041-12-10 | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM4 | 118.87 | 167.75 | 348.6 | 445.83
RM5 | 104.87 | 155.75 | 336.6 | 445.83
RM6 | 104.87 | 155.75 | 336.6 | 445.83
RM7 |  |  | 21.55 | 104.87 | 445.83
RM9 |  |  | 21.55 | 104.87 | 445.83
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Ash and tailings storage
Total rehabilitation area size (ha) |  |  |  | 31.84
Commencement of first milestone: RM3 |  |  |  | 2038
PMLU |  |  |  | Beef Cattle Grazing
Date area is available | 2038-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 31.84
Milestone completed by | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 31.84
RM4 | 31.84
RM5 | 31.84
RM6 | 31.84
RM7 |  | 31.84
RM9 |  | 31.84
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Infrastructure
Total rehabilitation area size (ha) |  |  |  | 67.39
Commencement of first milestone: RM1 |  |  |  | 2043
PMLU |  |  |  | Native Ecosystem
Date area is available | 2042-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 67.39
Milestone completed by | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 67.39
RM2 | 67.39
RM4 | 67.39
RM5 | 67.39
RM6 | 67.39
RM7 |  | 67.39
RM8 |  | 67.39
RM9 |  | 67.39
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | General mining activity
Total rehabilitation area size (ha) |  |  |  | 1447.44
Commencement of first milestone: RM4 |  |  |  | 2021
PMLU |  |  |  | Native Ecosystem
Date area is available | 2021-12-10 | 2024-12-10 | 2029-12-10 | 2034-12-10 | 2039-12-10 | 2042-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 601.91 | 745.9 | 819.13 | 874.51 | 1224.01 | 1447.44
Milestone completed by | 2021-12-10 | 2026-12-10 | 10/21/2031 | 2036-12-10 | 2041-12-10 | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM4 | 601.91 | 745.9 | 819.13 | 874.51 | 1224.01 | 1447.44
RM5 | 601.91 | 721.66 | 813.68 | 869.5 | 1058.61 | 1447.44
RM6 | 601.91 | 721.66 | 813.68 | 869.5 | 1058.61 | 1447.44
RM7 | 152.83 | 213 | 344.51 | 494.51 | 721.66 | 813.68 | 1447.44
RM9 | 152.83 | 213 | 344.51 | 494.51 | 721.66 | 813.68 | 1447.44
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Ash and tailings storage
Total rehabilitation area size (ha) |  |  |  | 79.49
Commencement of first milestone: RM3 |  |  |  | 2021
PMLU |  |  |  | Native Ecosystem
Date area is available | 2021-12-10 | 2021-12-10 | 2031-12-10 | 1931-12-10 | 1938-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 16.36 | 16.36 | 74.67 | 74.67 | 79.49
Milestone completed by | 2026-12-10 | 2031-12-10 | 2036-12-10 | 2041-12-10 | 2046-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM3 | 16.36 | 16.36 | 74.67 | 74.67 | 79.49
RM4 |  | 13.89 | 71.31 | 74.41 | 79.49
RM5 |  | 13.89 | 71.31 | 74.41 | 79.49
RM6 |  | 13.89 | 71.31 | 74.41 | 79.49
RM7 |  |  |  | 13.89 | 71.31 | 79.49
RM9 |  |  |  | 13.89 | 71.31 | 79.49
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Excavated highwalls (general mining activity)
Total rehabilitation area size (ha) |  |  |  | 204.02
Commencement of first milestone: RM4 |  |  |  | 2021
PMLU |  |  |  | Steep Rocky Ecosystem
Date area is available | 2021-12-10 | 2021-12-10 | 2037-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 0.42 | 0.42 | 204.42
Milestone completed by | 2021-12-10 | 2031-12-10 | 2041-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM4 | 0.42 | 0.42 | 204.02
RM6 |  | 0.42 | 204.02
RM7 |  |  | 0.42 | 204.02
RM9 |  |  | 0.42 | 204.02
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8
Relevant activities |  |  |  | Meandu Creek Diversion - South, Central and North (general mining activity)
Total rehabilitation area size (ha) |  |  |  | 18.98
Commencement of first milestone: RM7 |  |  |  | 2021
PMLU |  |  |  | Creek Diversion
Date area is available | 2021-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 18.98
Milestone completed by | 2036-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM7 | 11.35 | 18.98
RM9 | 11.35 | 18.98
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9
Relevant activities |  |  |  | K2E final void, K4E final void (general mining activity)
Total rehabilitation area size (ha) |  |  |  | 107.44
Commencement of first milestone: RM4 |  |  |  | 2038
PMLU |  |  |  | Water Storage
Date area is available | 2038-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 107.44
Milestone completed by | 2041-12-10 | 2051-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM4 | 107.44
RM7 |  | 107.44
RM9 |  | 107.44
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | Generic milestone criteria that apply to all applicable PMLUs: a. Services disconnected and terminated (unless otherwise agreed in consultation with landholders and/or relevant agencies). b. Buildings demolished and removed (unless otherwise agreed in consultation with landholders and/or relevant agencies). c. Concrete, hardstands and roads (bitumen, blue metal, aggregate etc) removed (unless otherwise agreed in consultation with landholders and/or relevant agencies). d. Infrastructure (pipelines, powerlines, fencing, signage etc) not required for PMLUs removed. e. Non-retained boreholes decommissioned and rehabilitated. f. Machinery and equipment not required for rehabilitation removed. Note: For clarity, RM1 is not applicable to the private road linking Nobby Smith Way to the Beef Cattle Grazing area. This is essential infrastructure (refer to Section 4.1.1.6) to provide all weather vehicle access and remains in place as part of the Beef Cattle Grazing PMLU (subject to landholder agreement).
RM2 | Investigation and/or remediation of contaminated land | Generic milestone criteria that apply to all applicable PMLUs: a. Conduct contaminated land investigation to industry standards, in locations where past site activities are a potential source of contamination, as deemed appropriate by an AQP. b. Remediate onsite or remove (as required) contaminated materials from site. c. Remove and dispose of plastic/geofabric liner from Retention Dam (RD) 27 and any other similar (future) installations if required.
RM3 | Installation of cover system over coal combustion products, and tailings storage facilities | Generic milestone criteria that apply to all applicable PMLUs: a. Prepare engineering and design plans for cover systems on coal combustion products and coal tailings (to avoid cover materials from containing NMD/SMD/AMD generating materials and minimise deep drainage by reducing surface water infiltration) that provides: * >2m of NAF material cover over coal combustion products; and * >6m of NAF material cover over coal tailings. b. Capping layer surface to be free draining to avoid surface ponding, in accordance with the engineering design report for the relevant locations (e.g., K2WN ASF/TSF, K4S ASF/TSF and any other locations nominated for storage of these waste types in any future PRCP amendment). c. Complete engineering report for cover that has been certified by an AQP that capping system is built/installed as per design.
RM4 | Landform development and reshaping | Generic milestone criteria that apply to all applicable PMLUs: a. Landform design achieves a Factor of Safety (FoS) ≥1.5* for landform designs. b. For spoil landforms constructed after 2016, material in the upper 6m is NAF. c. Bulk earthworks completed to tolerance of ±2m. Additional PMLU specific criteria for Beef Cattle Grazing: d. Modal terrain slope, with ≥80% of slopes ≤15% gradient and <20% slopes from 15% to 25% gradient. Additional PMLU specific criteria for Native Ecosystem: e. Modal terrain slope with ≥50% of slopes ≤17% gradient. Additional PMLU specific criteria for Steep Rocky Ecosystem: f. Modal terrain slope with gradients up to 80 degrees. Additional PMLU specific criteria for Plantation Forestry: g. Modal terrain slope with ≥50% of slopes ≤17 % gradient. Additional PMLU specific criteria for Water Storage: h. Assessed and certified by an AQP as achieving a stable landform with access/egress provided at ≤15% gradient. * Assessed at the projected stable crest for the Steep Rocky Ecosystem PMLU
RM5 | Surface preparation | Generic milestone criteria that apply to all applicable PMLUs: a. Prior to the application of topsoil erosion & subsidence has been stabilised. b. Topsoil of appropriate chemical properties has been spread to a minimum, on average, thickness of 0.2m as per Table 5-2 in the Revegetation Plan – Appendix L (based on topsoil placement records prior to ripping). c. Topsoiled areas have been deep ripped on contour.
RM6 | Revegetation | Generic milestone criteria that apply to all applicable PMLUs: a. Species selection is in accordance with the specific criteria for each PMLU. b. Species seeding rate and/or tubestock planting rate is in accordance with the requirements of the specific criteria for each PMLU. PMLU specific criteria for Beef Cattle Grazing: c. Sow a seed mix (species and rate) in accordance Table 4-3 in the Revegetation Plan – Appendix L. d. Apply fertiliser as determined from soil testing and plant use requirements. PMLU specific criteria for Native Ecosystem: e. Sow a seed mix (species and rate) in accordance Tables 4-1 & 4-2 in the Revegetation Plan – Appendix L to achieve RE 12.9 – 10.7a. f. Apply fertiliser as determined from soil testing and plant use requirements. PMLU specific criteria for Steep Rocky Ecosystem: g. Sow a seed mix (species and rate) in accordance Tables 4-4 & 4-5 in the Revegetation Plan – Appendix L. (as required), to supplement natural vegetation growth that is assessed against species diversity at site-specific analogue sites. h. Apply fertiliser (as required) as determined from plant requirements. PMLU specific criteria for Plantation Forestry: i. Direct seeding and/or tubestock planting in accordance with Section 4.1.5 of the Revegetation Plan – Appendix L. j. Apply fertiliser (as required) as determined from plant requirements.
RM7 | Achievement of initial surface requirements | Generic milestone criteria that apply to all applicable PMLUs: a. Rehabilitation (assessed as constructed) is geotechnically stable with a FoS ≥1.5*. b. Rehabilitation is non-polluting of surface water and achieves water quality criteria of: * pH: 5.5-9.0 (median); and * EC: <2037 μS/cm (median). Additional PMLU specific criteria for Beef Cattle Grazing: c. Rehabilitation is erosionally stable with persistent groundcover: * >50% for slope gradients ≤18%. * >80% for slope gradients >18% to 25%. * >75% of sward for sown pasture species (i.e., legumes and 3P grasses). * <10% of sward for invasive plants (i.e., weeds of national significance). d. Land suitability class for cattle grazing of 3 or better. Additional PMLU specific criteria for Native Ecosystem: e. Rehabilitation is erosionally stable with persistent groundcover: * >50% for slope gradients ≤18%, or * >80% for slope gradients >18%. f. Native plant species richness similar to RE 12.9-10.7a: * Trees ≥4 * Shrubs ≥6 * Grass ≥4 g. Perennial grass & organic litter cover ≥5%. h. Non-native plant cover ≤25%. Additional PMLU specific criteria for Steep Rocky Ecosystem: i. Presence of bare and vegetated land surfaces with native plant species richness: * Trees ≥ 2 * Shrubs ≥2 * Grass ≥3 j. Perennial grass & organic litter cover ≥10%. k. Non-native plant cover ≤25%.
RM7 cont'd |  | Additional PMLU specific criteria for Plantation Forestry: l. Land suitability class for plantation forestry of 3 or better. m. For Hoop Pine plantations, >150 trees/ha. n. For hardwood plantations, >100 trees/ha. Additional PMLU specific criteria for Creek Diversion: o. Retain records of as-built drawings. p. Prepare assessment report by an AQP certifying that historical creek diversions are operating in accordance with, or otherwise against, ACARP^ (20017, 2014) criteria. Additional PMLU specific criteria for Water Storage: q. Achieve water quality objectives where analytes monitored are to include: TDS: <5,000 mg/L, Calcium: ≤1,000 mg/L, Magnesium: ≤2,000 mg/L, Nitrate: ≤400 mg/L, Nitrite: ≤30 mg/L, Sulfate: ≤1,000 mg/L, Cobalt: ≤1 mg/L, Nickel: ≤1 mg/L, Zinc: ≤20 mg/L, Arsenic: ≤0.5 mg/L, Boron: ≤5 mg/L, Selenium: ≤0.02 mg/L, Molybdenum: ≤0.15 mg/L, Fluoride: ≤2 mg/L. * Assessed at the projected stable crest for the Steep Rocky Ecosystem PMLU ^ Specifically Section 3.0 – Evaluation of diversion performance (e.g., pre-ACARP Criteria) and Attachment A – Diversion Evaluation Framework
RM8 | Water quality at rehabilitated state | For the relevant drainage areas upgradient of CP3: a. Surface water quality in Meandu Creek meets the post closure Water Quality Objectives (WQOs) as shown in Table 8.5 in the TEC Coal PRCP (dated 27 January 2023). b. Aquatic ecology (i.e., aquatic habitat and riparian vegetation) health monitoring is undertaken every 3 years in Meandu Creek, between RD10 and RD1, which shows a progressive improvement, or is similar to, other ephemeral waterways in the region. c. Groundwater monitoring in the NWBV shows groundwater levels are below RL 432.7, at bores GW48 & GW49, and/or no visible seepage expressing to the surface at Bullgang Drain and/or Ramp 7. For the relevant drainage area upgradient of CP4 (Queens West): d. EC levels at EA Compliance bore (TEC Coal EA EPML00709113, dated 3 November 2022), GW39, is not to exceed 3,400 µS/cm - thus indicating no upward trend* in EC levels. For the relevant drainage area associated with location CP2 (Black Creek): e. EC levels in groundwater bore GW73 (on ML6674) not to exceed 11,800 µS/cm indicating no upward trend* in EC levels. * The assessment approach for determining if an upward trend is occurring is to be based on a suitable method as described in DSITI (2017) (e.g., control chart)
RM9 | Achievement of PMLU to stable condition | Generic milestone criteria that apply to all applicable PMLUs: a. Review of risk assessment confirms that safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. b. Certification that landform is geotechnically stable with a FoS ≥1.5*. c. Certification that rehabilitation is non-polluting of surface water and achieves water quality criteria of: * pH1:5: 5.5 - 9.0 (median); and * EC: <2037 μS/cm (median). Additional PMLU specific criteria for Beef Cattle Grazing: d. Certification that rehabilitation is erosionally stable with persistent groundcover: * >50% for slope gradients ≤18%. * >80% for slope gradients >18% to 25%. * >75% of sward for sown pasture species (i.e., legumes and 3P grasses). * <10% of sward for invasive plants (i.e., weeds of national significance). e. Achieves land suitability class for beef cattle grazing of 3 or better. Additional PMLU specific criteria for Native Ecosystem: f. Certification that rehabilitation is erosionally stable with persistent groundcover: * >50% for slope gradients ≤18%, or * >80% for slope gradients >18%. g. Native plant species richness similar to RE 12.9-10.7a: * Trees ≥4 * Shrubs ≥6 * Grass ≥4 h. Tree canopy cover ≥20%. i. Perennial grass & organic litter cover ≥5%. j. Non-native plant cover ≤25%.
RM9 cont'd |  | Additional PMLU specific criteria for Steep Rocky Ecosystem: k. Native plant species richness * Trees ≥2 * Shrubs ≥2 * Grass ≥3 l. Perennial grass & organic litter cover ≥10%. m. Non-native plant cover ≤25%. Additional PMLU specific criteria for Plantation Forestry:** n. Achieves land suitability class for plantation forestry of 3 or better. o. For Hoop Pine Plantations ≥ 150 trees per hectare. p. For Hardwood Plantation ≥ 100 trees per hectare. Additional PMLU specific criteria for Creek Diversion: q. Prepare assessment report by an AQP certifying that historical creek diversions are operating in accordance with, or otherwise against, ACARP^ (20017, 2014) criteria. Additional PMLU specific criteria for Water Storage: r. Water storages contain water of a suitable quality for native wildlife and/or livestock ingestion using the following water quality indicators: TDS: <5,000 mg/L, Calcium: ≤1,000 mg/L, Magnesium: ≤2,000 mg/L, Nitrate: ≤400 mg/L, Nitrite: ≤30 mg/L, Sulfate: ≤1,000 mg/L, Cobalt: ≤1 mg/L, Nickel: ≤1 mg/L, Zinc: ≤20 mg/L, Arsenic: ≤0.5 mg/L, Boron: ≤5 mg/L, Selenium: ≤0.02 mg/L, Molybdenum: ≤0.15 mg/L, Fluoride: ≤2 mg/L. Additional PMLU specific criteria for Landholder Retained Infrastructure:^^ s. Legally binding agreement, for retained infrastructure, executed by both parties. * Assessed at the projected stable crest for the Steep Rocky Ecosystem PMLU ** No milestone criteria apply for the Plantation Forestry PMLU where pre-mining land surface remains and area is undisturbed by mining ^ Specifically Section 3.0 – Evaluation of diversion performance (e.g., pre-ACARP Criteria) and Attachment A – Diversion Evaluation Framework ^^ Landholder Retained Infrastructure PMLU not currently utilised. Not applicable where essential infrastructure has been incorporated into other PMLUs
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones