## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Ancillary infrastructure and services
Total rehabilitation area size (ha) |  |  |  | 179.88
Commencement of first milestone: RM1 |  |  |  | 2048-12-10
PMLU |  |  |  | Native ecosystem
Date area is available | 2048-01-01 | 2050-01-01 | 2051-01-01 | 2056-01-01 | 2061-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 179.88 | 179.88 | 179.88 | 179.88 | 179.88
Milestone completed by | 2049-12-10 | 2050-12-10 | 2055-12-10 | 2060-12-10 | 2065-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 179.88
RM2 |  | 179.88
RM3 |  | 179.88
RM8 |  | 179.88
RM9 |  |  | 179.88
RM11 |  |  |  | 179.88
RM13 |  |  |  |  | 179.88
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Borrow pits and stockpiles
Total rehabilitation area size (ha) |  |  |  | 21.71
Commencement of first milestone: RM4 |  |  |  | 2048-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2048-01-01 | 2049-01-01 | 2054-01-01 | 2059-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 21.71 | 21.71 | 21.71 | 21.71
Milestone completed by | 2048-12-10 | 2053-12-10 | 2058-12-10 | 2063-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM4 | 21.71
RM8 | 21.71
RM10 |  | 21.71
RM12 |  |  | 21.71
RM14 |  |  |  | 21.71
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Dams and diversion structures
Total rehabilitation area size (ha) |  |  |  | 31.63
Commencement of first milestone: RM1 |  |  |  | 2048-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2064-01-01 | 2066-01-01 | 2071-01-01 | 2074-01-01 | 2079-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 31.63 | 31.63 | 31.63 | 31.63 | 31.63
Milestone completed by | 2065-12-10 | 2070-12-10 | 2073-12-10 | 2078-12-10 | 2083-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 31.63
RM2 | 31.63
RM5 |  | 31.63
RM8 |  | 31.63
RM10 |  |  | 31.63
RM12 |  |  |  | 31.63
RM14 |  |  |  |  | 31.63
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mineralised waste
Total rehabilitation area size (ha) |  |  |  | 20.11
Commencement of first milestone:RM2 |  |  |  | 2048-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2048-01-01 | 2059-01-01 | 2060-01-01 | 2063-01-01 | 2068-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 20.11 | 20.11 | 20.11 | 20.11 | 20.11
Milestone completed by | 2048-12-10 | 2059-12-10 | 2062-12-10 | 2067-12-10 | 2072-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM2 | 20.11
RM6 |  | 20.11
RM8 |  | 20.11
RM10 |  |  | 20.11
RM12 |  |  |  | 20.11
RM14 |  |  |  |  | 20.11
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Mining and processing areas
Total rehabilitation area size (ha) |  |  |  | 19.52
Commencement of first milestone:RM2 |  |  |  | 2048-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2048-01-01 | 2049-01-01 | 2050-01-01 | 2053-01-01 | 2058-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 19.52 | 19.52 | 19.52 | 19.52 | 19.52
Milestone completed by | 2048-12-10 | 2049-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM2 | 19.52
RM6 | 19.52
RM8 |  | 19.52
RM10 |  | 19.52
RM12 |  |  | 19.52
RM14 |  |  |  | 19.52
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Tailings Storage Facility (TSF)
Total rehabilitation area size (ha) |  |  |  | 51.06
Commencement of first milestone: RM1 |  |  |  | 2048-01-01
PMLU
Date area is available | 2048-01-01 | 2049-01-01 | 2050-01-01 | 2052-01-01 | 2057-01-01 | 2062-01-01 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 51.06 | 51.06 | 51.06 | 51.06 | 51.06 | 51.06
Milestone completed by | 2048-12-10 | 2049-12-10 | 2051-12-10 | 2056-12-10 | 2061-12-10 | 1966-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 51.06
RM7 |  | 51.06
RM8 |  |  | 51.06
RM9 |  |  |  | 51.06
RM11 |  |  |  |  | 51.06
RM13 | [5 empty] | 51.06
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  | RA7
Relevant activities |  | Exploration
Total rehabilitation area size (ha) |  | 8.32
Commencement of first milestone: RM1 |  | 2048-01-01
PMLU
Date area is available | 2048-01-01 |  | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 8.32
Milestone completed by | 2049-12-10 |  | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM2 | 8.32
RM5 | 8.32
RM8 | 8.32
RM10 | 8.32
RM12 | 8.32
RM14 | 8.32
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA1
Non-use management area (NUMA)
Improvement area |  |  |  | IA1
Relevant activities
Total size (ha)
Commencement of first milestone: <insert milestone reference>
NUMA
Date area is available | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha)
Milestone completed by | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
MM
MM
MM
MM
MM
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | • All buildings and associated infrastructure dismantled and removed offsite • All hardstand and concrete areas decommissioned removed • Fences removed • Pipelines removed • Roads removed (with the exception of those being retained for future site access) • Waste removed • Drillholes, sediment ponds and sumps decommissioned • Machinery/ equipment not required for rehabilitation removed from site
RM2 | Removal of contaminated land | • Contaminated land assessment is completed by a suitably qualified person • Identified contaminated material removed from the mine domain and disposed of within the TSF • Validation sampling determine that contaminant removal has been successful • Validation sampling report accepted by a suitably qualified Contaminated Land Auditor stating that contamination removal has been successful
RM3 | Landform development and reshaping - RA1 | • Landform shaped to be gently sloping characteristic of the natural landform and include Features such as large woody debris or boulders are present to provide suitable habitat for the Purple Neck Rock Wallaby • Landform ripped parallel to landform • RA1 determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM4 | Landform development and reshaping - RA2 | • Landform shaped to be gently sloping characteristic of the natural landform • Landform ripped parallel to landform • RA2 determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM5 | Landform development and reshaping - RA3/RA7 | • General earthworks completed • HPDE Liner removed • Dams filled with NAF or other suitable material. Material placed in 500mm lifts, watered and compacted. • Landform shaped to be gently sloping characteristic of the natural landform • RA3 determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM6 | Landform development and reshaping - RA4/RA5 | • Removal of waste rock. PAF disposed in TSF. NAF utilised in rehabilitation. • Major earthworks completed • Landform shaped to be gently sloping characteristic of the natural landform • RA4 determined to be geotechnically stable by a suitably qualified geotechnical engineer
RM7 | Landform development and reshaping - RA6 | • QAQC testing is completed post construction to determine that depth of layers and permeability is to specified designs . • The construction and maintenance design of the cover system / cap has been certified by an appropriately qualified person that is consistent with the cover design. • Slopes of TSF top to have a grade of 1% with slope lengths of ~2000m at the southern end of the TSF, and 1150m at the northern end. • Certification by an AQP that landform has achieved an acceptable factor of safety • Main TSF embankment formed as a broad spillway rock chute with slopes of 15% with a slope length of ~230 m; • TSF is assessed as geotechnically stable by a suitably qualified geotechnical engineer. Features such as large woody debris or boulders are present to provide suitable habitat for the Purple Neck Rock Wallaby • TSF surface is stable, non-ponding, and impermeable. • Spillway is designed and constructed to support peak flood flow velocity • An average erosion rate <5 t/ha/y • Erosion rilling is <0.2m • No surface ponding. • Installation of erosion and sediment control structures that comply with International Erosion Control Association (IECA).
RM8 | Surface preparation | • Deep ripping of compacted surfaces, at least 300mm into soil profile, where required. • Topsoil placement of a minimum 0.2 m, where required
RM9 | Revegetation (native ecosystem) | •Natural vegetation strikes creates a groundcover >30% of analogue sites •Where natural vegetation strike is not achieved to >30% of analogue sites, direct seeding of native species achieves >30% of analogue sites. •Seeding rate of 4 – 10 kg/ha achieved •Direct seeding species mix is endemic to Regional Ecosystem 1.11.2 and 1.7.7 on RA1 such as Eucalyptus leucophloia, Corymbia terminalis, Corymbia capricornia with a groundcover of Aristida latifolia, Eriachne obtusa,Sporobolus australasicus,Themeda triandra, Triodia pungens •Direct seeding species mix is endemic to Regional Ecosystem 1.11.2 and 1.7.7 on RA6 such as Aristida latifolia, Eriachne obtusa,Sporobolus australasicus,Themeda triandra, Triodia pungens, •Deep rooting vegetation such as Eucalyptus Spp not present on RA6
RM10 | Revegetation (grazing) | • Pasture vegetation seeding creates cover >30% of analogue sites of analogue sites. • seeding rate of 4 – 10 kg/ha achieved
RM11 | Achievement of surface requirements (native ecosystem) | • Weed species in densities less than 10% total coverage • Average erosion rate of <5 t/ha/y with the maximum erosion rate at any point on the landform of <10 t/ha/y. • Surface water quality measured at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Table 3.1 values for aquatic ecosystems (slightly to moderately disturbed). • Stream sediment at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low • Groundwater monitoring at MB5, MB6, MB9S and MB9D complies with ANZECC/ARMCANZ (2000) Table 4.3.2 for livestock drinking water • Soil testing indicates the following parameters are met: • Rootzone EC <0.15mS/cm • Soil pH <9 and >6 as measured at any part of the root zone • Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). • Annual infiltration rates within the TSF decreasing. • Annual TSF seepage volume is decreasing • BioCondition flora surveys indicate that vegetation cover has reached 70% of analogue sites within the same regional ecosystem. • No ponding on the surface of the TSF.
RM12 | Achievement of surface requirements (grazing) | • Weed species in densities less than 10% total coverage • Average erosion rate of <5 t/ha/y with the maximum erosion rate at any point on the landform of <10 t/ha/y. • Surface water quality measured at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Table 3.1 values for aquatic ecosystems (slightly to moderately disturbed). • Stream sediment at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low • Groundwater monitoring at MB5, MB6, MB9S and MB9D complies with ANZECC/ARMCANZ (2000) Table 4.3.2 for livestock drinking water • Soil testing indicates the following parameters are met: • Rootzone EC <0.15mS/cm • Soil pH <9 and >6 as measured at any part of the root zone • Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). •BioCondition flora surveys indicate that pasture covers has reached 70% of analogue sites.
RM13 | Achievement of post-mining land use to a stable condition (native ecosystem) | • Vegetation cover exceeds 70th percentile of analogue sites • Vegetation resilience is achieved with seedlings at 70% of analogue site coverage. • Native fauna observed or indicators of these species have been recorded. • Certification from an REPQ that the domain has achieved stable condition • Certification from an AQP that the landform achieved a factor of safety 1.5. • Surface water quality measured at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Table 3.1 values for aquatic ecosystems (slightly to moderately disturbed). • Stream sediment at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low • Groundwater monitoring at MB5, MB6, MB9S and MB9D complies with ANZECC/ARMCANZ (2000) Table 4.3.2 for livestock drinking water • Soil testing undertaken at 5 yearly intervals indicates the following parameters are met: o Rootzone EC <0.15mS/cm o Soil pH <9 and >6 as measured at any part of the root zone o Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). Annual seepage volume decreasing • No ponding on the surface of the TSF
RM14 | Achievement of post-mining land use to a stable condition (grazing) | • Vegetation cover exceeds 70th percentile of reference site • Vegetation resilience is achieved with seedlings at 70% of reference site coverage. • Certification from an REPQ that the domain has achieved stable condition • Certification from an AQP that the landform achieved a factor of safety 1.5. • Surface water quality measured at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Table 3.1 values for aquatic ecosystems (slightly to moderately disturbed). • Stream sediment at downstream monitoring sites (DR-18, DR-22 and CC-15) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines - low • Groundwater monitoring at MB2 and MB4 complies with ANZECC/ARMCANZ (2000) Table 4.3.2 for livestock drinking water • Soil testing undertaken at 5 yearly intervals indicates the following parameters are met: o PAWC >50 at Red Plain and Pocket soil types o Rootzone EC <0.15mS/cm o Soil pH <9 and >6 as measured at any part of the root zone o Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). Carrying capacity is suitable to support a sustainable level of grazing.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1
MM2
MM3
MM4
MM5
MM6
MM7
MM8
MM9
MM10
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones