## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Infrastructure, offices, laydown, roads, product coal stockpile, drying cells, dams, rail, topsoil stockpiles
Total rehabilitation area size (ha) |  |  |  | 96
Commencement of first milestone: RM1 |  |  |  | 2036-12-10
PMLU |  |  |  | Cattle Grazing
Date area is available | 2036-12-10 | 2039-12-10 |  | 2049-12-10 | 2051-12-10
Cumulative area available (ha) | 51 | 60 |  | 84 | 96
Milestone completed by | 2039-12-10 | 2042-12-10 | 2049-12-10 | 2052-12-10 | 2054-12-10 | 2057-12-10 | 2062-12-10 | 2064-12-10 | 2067-12-10 | 2069-12-10
Milestone Reference | 2039-12-10: Cumulative area achieved (ha)
RM1 | 2039-12-10: 51; 2042-12-10: 60; 2052-12-10: 84; 2054-12-10: 96
RM2 | 2039-12-10: 51; 2042-12-10: 60; 2052-12-10: 84; 2054-12-10: 96
RM3 | 2039-12-10: 51; 2042-12-10: 60; 2052-12-10: 84; 2054-12-10: 96
RM4 | 2039-12-10: 51; 2042-12-10: 60; 2052-12-10: 84; 2054-12-10: 96
RM7 | 2039-12-10: 51; 2042-12-10: 60; 2052-12-10: 84; 2054-12-10: 96
RM10 | 2049-12-10: 51; 2052-12-10: 60; 2062-12-10: 84; 2064-12-10: 96
RM13 | 2054-12-10: 51; 2057-12-10: 60; 2067-12-10: 84; 2069-12-10: 96
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
Note on B8: Hooper, Alicia: Industrial, laydown, roads, coal stps, drying cells less admin/crib/general/workshop
Note on C8: Hooper, Alicia: admin/crib/general/workshop/ some topsoil stockpiles
Note on E8: Hooper, Alicia: Dams, drains
Note on F8: Hooper, Alicia: Rail, load out, DNM

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | ROM Pad
Total rehabilitation area size (ha) |  |  |  | 44
Commencement of first milestone: RM1 |  |  |  | 2036-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2036-12-10
Cumulative area available (ha) | 44
Milestone completed by | 2039-12-10 | 2040-12-10 | 2054-12-10 | 2059-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 44
RM2 | 44
RM3 | 44
RM5 | 44
RM8 |  | 44
RM11 |  |  | 44
RM14 |  |  |  | 44
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Rail, roads, topsoil stockpiles
Total rehabilitation area size (ha) |  |  |  | 33
Commencement of first milestone: RM1 |  |  |  | 2036-12-10
PMLU |  |  |  | Woodland Habitat
Date area is available | 2036-12-10 | 2051-12-10
Cumulative area available (ha) | 5 | 33
Milestone completed by | 2039-12-10 | 2054-12-10 | 2059-12-10 | 2069-12-10 | 1974-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 5 | 33
RM2 | 5 | 33
RM3 | 5 | 33
RM5 | 5 | 33
RM8 | 5 | 33
RM11 |  | 5 |  | 33
RM14 |  |  | 5 |  | 33
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Rail, roads
Total rehabilitation area size (ha) |  |  |  | 0.9
Commencement of first milestone: RM1 |  |  |  | 2036-12-10
PMLU |  |  |  | Water course
Date area is available | 2036-12-10 | 2051-12-10
Cumulative area available (ha) | 0.5 | 0.9
Milestone completed by | 2039-12-10 | 2054-12-10 | 2059-12-10 | 2069-12-10 | 2074-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 0.5 | 0.9
RM2 | 0.5 | 0.9
RM3 | 0.5 | 0.9
RM6 | 0.5 | 0.9
RM9 | 0.5 | 0.9
RM12 |  | 0.5 |  | 0.9
RM15 |  |  | 0.5 |  | 0.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | a) Services disconnected b) Built and service infrastructure demolished and removed (except where agreed in writing by the post-mining land owner/holder) c) Concrete, bitumen and aggregate removed d) Rubbish removed e) No more than 10% visible coaly and carbonaceous mineral waste on surface f) Dried tailings removed g) Water and sediment within dams removed h) Creek crossing culverts removed
RM2 | Remediation of contaminated land | a) Contaminated land investigation completed by a suitably qualified person in accordance with the National Environment Protection (Assessment of Site Contamination) Measures and the Queensland Environmental Protection Act (1994) b) In the event that residual contamination has been identified and presents a potential unacceptable risk to the nominated PMLUs or environmental values, remediation works and/or implementation of management controls will be undertaken c) Where ongoing management of residual contamination is deemed appropriate, a draft Site Management Plan will be prepared for the administering authority’s consideration
RM3 | Landform development and reshaping | a) Tailings drying cells backfill completed b) Dams backfill completed c) Haul road and rail base material removed within 100m of New Chum Creek, and disturbed bed and banks returned to a profile similar to the pre-disturbance condition in accordance with associated riverine and/or operation works permits or associated exemptions (RA3, RA4) d) Landforms reshaped with maximum 10% slopes (RA1, RA2, RA3) e) Landform reshaped to be free-draining and consistent with surrounding topography
RM4 | Surface preparation (cattle grazing) | a) Topsoil is placed at an average thickness of 150mm b) An assessment of soil and growth media characteristics is completed by an appropriately qualified person1, and amelioration and other treatments required identified c) Ameliorant and physical treatments are applied as identified in RM4(b) with the aim of achieving the following primary growth media target criteria2: 1. Surface pH 6 – 9.5 2. Salinity (EC1:5) <0.75 3. Sodicity (ESP) <6 4. Total N >1,000 5. Available P >10 6. Available K >200 7. Organic Carbon >1 d) Rip across contour 1Appropriately qualified person: a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods or literature 2 Target primary growth media criteria are provided as a post-ameliorant target. Initial soil analysis values may be outside of the displayed ranges.
RM5 | Surface preparation (woodland habitat) | a) An assessment of growth media characteristics is completed by an appropriately qualified person1, and amelioration and other treatments required to achieve the following target primary growth media criteria2 1. Surface pH 6 – 9.5 2. Salinity (EC1:5) <0.75 3. Sodicity (ESP) <6 4. Total N >1,000 5. Available P >10 6. Available K >200 7. Organic Carbon >1 b) Ameliorant and physical treatments are applied as identified in RM5(a)d) Rip across contour c) Rip across contour. 1Appropriately qualified person: a person who has professional qualifications, training, skills or experience relevant to the nominated subject matter and can give authoritative assessment, advice and analysis on performance relating to the subject matter using the relevant protocols, standards, methods or literature 2 Target primary growth media criteria are provided as a post-ameliorant target. Initial soil analysis values may be outside of the displayed ranges.
RM6 | Surface preparation (water course) | a) An assessment of growth media characteristics is completed by an appropriately qualified person1, and amelioration and other treatments required identified b) Ameliorant and physical treatments are applied as identified in RM6(a) c) Sediment and erosion controls established in accordance with associated riverine and/or operation works permits or associated exemptions
RM7 | Revegetation (cattle grazing) | a) Completed seeding in accordance with recommended pasture mix (grasses, cover crop and legumes), and seeding rates (up to 25kg/ha) as listed in Table 26 as per Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023
RM8 | Revegetation (woodland habitat) | a) Target primary growth media criteria listed in RM5(a) are achieved based on a number of representative samples determined by an appropriately qualified person1 . b) Completed seeding using a selection of species outlined in: • RA2: Table 28 of the Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023 • RA3: Table 29 of the Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023 c) Seeding must be completed to achieve species richness required by the BioCondition scores outlined in RM14(b) and RM14(c) for RA2 and RA3 respectively. d) Completed seeding as per recommended sowing rates for individual species where possible and total recommended seeding rates for dominant tree species (5kg/ha), mid-storey species (5kg/ha), and groundcover species (5kg/ha) plus 5kg/ha of suitable cover crop (e.g. Echinochloa esculenta).
RM9 | Revegetation (water course) | a) Completed seeding in accordance with recommended species as listed in Table 30 of the Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023 b) Completed seeding as per the recommended sowing rates for individual species where possible and total recommended seeding rates for upper bank (5kg/ha), mid bank (5kg/ha), and lower bank (5kg/ha) plus 5kg/ha of suitable cover crop (e.g. Echinochloa esculenta) as per Table 32 of the Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023
RM10 | Achievement of surface requirements (cattle grazing) | a) Pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per Stocktake: Balancing Supply and Demand (https://futurebeef.com.au/workshops/sustainable-grazing/stocktake-balancing-supply-demand/), as provided in Table 27 of the Progressive Rehabilitation and Closure Plan - Red Mountain Infrastructure, Version 1.0, 6 January 2023, including: • Preferred pasture species (3P grasses2) diversity ≥2 species • Preferred pasture (3P) % DM yield 10-60% • Annual grass DM yield % <70% • Undesirable grasses and other weeds % DM yield <80% • Crown cover (3P grasses2) – at worst, moderate to low density and some plants dead 23P grasses: native and naturalised exotic grass species that are perennial, palatable, and productive plants to stock
RM11 | Achievement of surface requirements (woodland habitat) | a) Total invasive4 plant cover is ≤10% 4Invasive plants: as listed under the Queensland Biosecurity Act 2014
RM12 | Achievement of surface requirements (water course) | a) Revegetation species presence on upper banks, mid-banks and lower banks representative of sown seed mix as detailed in RM9 b) Groundcover3 is >80% on banks c) Total invasive4 plant cover is ≤10%
RM13 | Achievement of post-mining land use to a stable condition (cattle grazing) | a) A hazard assessment has been completed by an appropriately qualified person1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use b) Groundcover3 >50% c) Rainfall runoff from rehabilitation is not significantly different to upstream values for the following: pH, EC and turbidity as per Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023, Appendix 11, Figure 27 d) Deep drainage from the area is not significantly different to EC levels as per Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023, Appendix 11, Figure 27, of: • the EPP (Water) schedule documents water quality objectives for relevant groundwater chemistry zones; or • local water quality objectives developed in accordance with the Queensland Water Quality Guidelines e) Land suitability class ≤3, or not different from pre-mining class if ≥4, as per Table 20 of the Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023. The assessment is to be conducted by an appropriately qualified person1 and completed in accordance with LSA Framework for Open-Cut Coal Mine Rehabilitation 2018 (A rule-set for land suitability assessment of sustainable beef cattle grazing on land rehabilitated after open-cut coal mining in the Bowen Basin Queensland, unless otherwise agreed in writing between the administering authority and the environmental authority holder For RM13(e), if the land suitability class is assessed as being not different from pre-mining class if ≥4 for all or a portion of a rehabilitation area, an assessment of reference sites5 must be carried out to determine if the limitation/s resulting in the class of ≥4 is consistent with that of reference sites. f) Certification by an appropriately qualified person1 that pasture meets a pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per Stocktake: Balancing Supply and Demand (https://futurebeef.com.au/workshops/sustainable-grazing/stocktake-balancing-supply-demand/), as provided in Table 27 of the Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023 5Reference site: representative undisturbed grazing land adjacent to the disturbance area
RM14 | Achievement of post-mining land use to a stable condition (woodland habitat) | a) A BioCondition assessment is completed by an appropriately qualified person using the methodology outlined in the Queensland Herbarium’s BioCondition Assessment Manual version 2.2 and modified in accordance with section 6.1.8 Revegetation of the planning part and displayed in Table 30: The assessable attributes and weightings for deriving the final BioCondition score b) For RA2, the BioCondition assessment required by RM14 demonstrates achievement of 50% of total maximum BioCondition score of undisturbed regional ecosystem 11.5.3. c) For RA3, the BioCondition assessment required by criterion RM14 demonstrates achievement of 50% of total maximum BioCondition score of undisturbed regional ecosystem 11.4.9. d) A hazard assessment has been completed by an appropriately qualified person1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use e) Rehabilitation of RA2 is assessed as geotechnically stable by an appropriately qualified person1 with FoS≥1.5, unless an alternative is justified by an appropriately qualified engineer f) Rainfall runoff from rehabilitation is not significantly different to upstream values for the following: pH, EC and turbidity as per Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023, Appendix 11, Figure 27 g) Deep drainage from the area is not significantly different to EC levels as per Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023, Appendix 11, Figure 27, of: • the EPP (Water) schedule documents water quality objectives for relevant groundwater chemistry zones; or • local water quality objectives developed in accordance with the Queensland Water Quality Guidelines
RM15 | Achievement of post-mining land use to a stable condition (water course) | a) A hazard assessment has been completed by an appropriately qualified person1 to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use b) Groundcover3 on banks >80% c) Rainfall runoff from rehabilitation is not significantly different to upstream values for the following: pH, EC and turbidity as per Progressive Rehabilitation and Closure Plan – Red Mountain Infrastructure, Version 1.0, 6 January 2023, Appendix 11, Figure 27 d) Riparian vegetation consisting of an over-storey, under-storey and groundcover, comparable to an established watercourse reference site6 6Watercourse reference site: representative undisturbed grazing land adjacent to the disturbance areas
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones