## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1_EWRSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Eastern Waste Rock Storage Facility
Total rehabilitation area size (ha) |  |  |  | 197.671
Commencement of first milestone: <insert milestone reference> |  |  |  | 2021-12-10
PMLU |  |  |  | Grazing
Date area is available | 2021-12-10
Cumulative area available (ha) | 197.671
Milestone completed by | 2024-12-10 | 2041-12-10 | 2044-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 32.91
RM4 | 32.91
RM5 | 32.91
RM6 | 197.671
RM7 |  | 63.189 | 79.81 | 197.671
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2_NWRSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Northern Waste Rock Storage Facility
Total rehabilitation area size (ha) |  |  |  | 38.48
Commencement of first milestone: <insert milestone reference> |  |  |  | 2023-12-10
PMLU |  |  |  | Grazing
Date area is available | 2023-12-10
Cumulative area available (ha) | 38.48
Milestone completed by | 2025-12-10 | 2041-12-10 | 2045-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 14.98
RM4 | 14.98
RM5 | 14.98
RM6 | 38.48
RM7 |  | 21.512 | 29.63 | 38.48
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3_SWRSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Southern Waste Rock Storage Facility
Total rehabilitation area size (ha) |  |  |  | 41.407
Commencement of first milestone: <insert milestone reference> |  |  |  | 2024-12-10
PMLU |  |  |  | Grazing
Date area is available | 2024-12-10
Cumulative area available (ha) | 41.407
Milestone completed by | 2026-12-10 | 2041-12-10 | 2046-12-10 | 2126-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 12.54
RM4 | 12.54
RM5 | 12.54
RM6 | 41.407
RM7 |  | 6.578 | 7.49 | 41.407
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4_NNTSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | New Northern Tailings Storage Facility
Total rehabilitation area size (ha) |  |  |  | 116.68
Commencement of first milestone: <insert milestone reference> |  |  |  | 2025-12-10
PMLU |  |  |  | Grazing
Date area is available | 2025-12-10
Cumulative area available (ha) | 116.68
Milestone completed by | 2027-12-10 | 2041-12-10 | 2047-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 13.33
RM4 | 13.33
RM5 | 13.33
RM6 | 116.68
RM7 |  | 101.865 | 115.185 | 116.68
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5_ONTSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Old Northern Tailings Storage Facility
Total rehabilitation area size (ha) |  |  |  | 65.3
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-10
PMLU |  |  |  | Grazing
Date area is available | 2026-12-10
Cumulative area available (ha) | 65.3
Milestone completed by | 2027-12-10 | 2041-12-10 | 2047-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 5.2
RM4 | 5.2
RM5 | 5.2
RM6 | 65.3
RM7 |  | 27.702 | 28.65 | 65.3
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6_STSF
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Southern Tailings Storage Facility
Total rehabilitation area size (ha) |  |  |  | 68.196
Commencement of first milestone: <insert milestone reference> |  |  |  | 2026-12-10
PMLU |  |  |  | Grazing
Date area is available | 2026-12-10
Cumulative area available (ha) | 68.2
Milestone completed by | 2027-12-10 | 2041-12-10 | 2047-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 0.69
RM4 | 0.69
RM5 | 0.69
RM6 | 68.196
RM7 |  | 34.92 | 35.489 | 68.196
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7_Stockpiles
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Stockpiles
Total rehabilitation area size (ha) |  |  |  | 60.94
Commencement of first milestone: <insert milestone reference> |  |  |  | 2027-12-10
PMLU |  |  |  | Grazing
Date area is available | 2027-12-10
Cumulative area available (ha) | 60.94
Milestone completed by | 2030-12-10 | 2041-12-10 | 2050-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM3 | 11.36
RM4 | 11.36
RM5 | 11.36
RM6 | 60.94
RM7 |  | 14.13 | 16.12 | 60.94
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA8_Dams and Sumps
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Dams and Sumps
Total rehabilitation area size (ha) |  |  | 50.187
Commencement of first milestone: <insert milestone reference> |  |  | 2121-12-10
PMLU |  |  | Grazing
Date area is available | 2121-12-10
Cumulative area available (ha) | 50.187
Milestone completed by | 2123-12-10 | 2143-12-10
Milestone Reference | Cumulative area achieved (ha)
RM6 | 50.187
RM7 |  | 50.187
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA9_Roads and Mine Infrast.
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Roads and Mine Infrastructure
Total rehabilitation area size (ha) |  |  | 15.723
Commencement of first milestone: <insert milestone reference> |  |  | 2121-12-10
PMLU |  |  | Grazing
Date area is available | 2121-12-10
Cumulative area available (ha) | 15.723
Milestone completed by | 2123-12-10 | 2143-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 4.08
RM2 | 4.08
RM4 | 4.08
RM5 | 4.08
RM6 | 15.723
RM7 |  | 15.723
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA10_Northern Borrow Pits
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Northern Borrow Pits
Total rehabilitation area size (ha) |  |  | 47.57
Commencement of first milestone: <insert milestone reference> |  |  | 2030-12-10
PMLU |  |  | Grazing
Date area is available | 2030-12-10 | 2032-12-10
Cumulative area available (ha) | 47.57 | 47.57
Milestone completed by | 2032-12-10 | 2052-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 47.57
RM4 | 47.57
RM5 | 47.57
RM6 | 47.57
RM7 |  | 47.57
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA11_Southern Borrow Pits
Post-mining land uses (PMLU)
Rehabilitation area |  |  | RA8
Relevant activities |  |  | Southern Borrow Pits
Total rehabilitation area size (ha) |  |  | 58.78
Commencement of first milestone: <insert milestone reference> |  |  | 2030-12-10
PMLU |  |  | Grazing
Date area is available | 2030-12-10
Cumulative area available (ha) | 58.78
Milestone completed by | 2032-12-10 | 2052-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 58.78
RM4 | 58.78
RM5 | 58.78
RM6 | 58.78
RM7 |  | 58.78
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA12_Scats stockpile
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA12
Relevant activities |  |  |  | Scats Stockpile
Total rehabilitation area size (ha) |  |  |  | 30.78
Commencement of first milestone: <insert milestone reference> |  |  |  | 2027-12-10
PMLU |  |  |  | Grazing
Date area is available | 2027-12-10
Cumulative area available (ha) | 30.78
Milestone completed by | 2030-12-10 | 2050-12-10 | 2121-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 29.47
RM3 | 29.47
RM4 | 29.47
RM5 | 29.47
RM6 | 30.78
RM7 |  | 3.14 | 30.78
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## IA_1_NUMA
Non-use management area (NUMA)
Improvement area |  | IA1
Relevant activities |  | NUMA
Total size (ha) |  | 70.38
Commencement of first milestone: <insert milestone reference> |  | 2021-12-10
NUMA |  | Void
Date area is available | 2021-12-10
Cumulative area available (ha) | 70.38
Milestone completed by | 2121-12-10 09:07
Milestone Reference | Cumulative area achieved (ha)
MM1 | 70.38
MM2 | 70.38
MM3 | 70.38
MM4 | 70.38
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | INFRASTRUCTURE DECOMMISSION AND REMOVAL | • Land no longer need for current or future operations. • Land will not be subject to future ground disturbance • Prepare decommissioning strategy to facilitate works • Infrastructure (i.e. mining and ancillary) removed unless otherwise agreed and asset transfer agreement in place for infrastructure retained. • Rehabilitate boreholes not required for monitoring to ESR/2016/1985 Standard • Disconnect and terminate services (water, electricity, gas)
RM2 | LANDFORM SHAPING | • Bulk earthworks have been completed to achieve final landform design • Install ESC Structures • Report to verify "as constructed" complies with the design
RM3 | COVER SYSTEM INSTALL | • Cover material installed as per design specification (e.g. thickness, compaction, material size etc) • Conformance checks to verify "as constructed" complies with the design
RM4 | FINAL SURFACE PREPARATION | • Remediation of existing erosion/ponding • General and trim earthworks as required • Suitability of growth media tested prior to use and ameliorants applied as required • Apply nominated depth of growth media • Conformance checks to verify "as constructed" complies with the design
RM5 | REVEGETATION (PASTURE GRAZING) | • Rip/plough/tyne growth media (preserving cover system) • Application of ameliorants (application rates to be informed by soil tests) • Apply seed mix at nominated rate
RM6 | ACHIEVEMENT OF REHABILITATED LANDFORM | • Add RA to monitoring program to determine status and requirement for adaptive managmeent • Implement adaptive managmeent requirements from rehabilitation monitoring program
RM7 | ACHIEVEMENT OF PMLU TO STABLE CONDITION | • Infrastructure in RA removed from RA unless required to complement PMLU. • Land is demonstrated through monitoring to be safe, structurally stable, not causing environmental harm and can sustain the PMLU. • Site contamination assessment for entire mine has been prepared by an approved auditor and mine site complies with Contaminated Sites Act 2003 and meets the requirements to be removed from the Environmental Management Register. • Soil surface stability greater than or equal to the lower limit of the average regional range (analogue sites) for three years of monitoring. • Erosion features less than or equal to the upper limit of the average regional range (analogue sites) for three monitoring years. • Rehabilited areas are ≥ 70% of analogue median for three years of monitoring, applicable to: o Native grass cover and diversity o Woody species cover and diversity o Perennial grass species cover and diversity • LFA infiltration index and nutrient cycling index are at least 70% of median for target ecosystem (analogue sites) for three years of monitoring. * Surface water completion criteria meets those established from the Receiving Environment Monitoring Program (REMP).
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Receipt of Water from Surface Water Interception System | Potentially contaminated surface water is captured and transferred to the NUMA to minimise risks to the environment (NB The total catchment area which reports to the NUMA will be minimised progressively as the water quality from each sub-catchment is suitable for release to the offsite environment.
MM2 | Monitoring of geotechnical stability | Monitoring of predicted geological instability to identify risks to the environment
MM3 | Maintaining NUMA Water Level | Ensure NUMA water level is <340mRL and dewatering to achieve levels (if required) Annual water balance modelling shows that the long term water level in the final pit lake will remain below RL 340 m AHD
MM4 | Maintenance of exclusion bund | Exlcusion bund maintained to prevent unintentional access
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones