## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1- Elevated Dumps Upper
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1 - Elevated Landform - Overburden Dumps - Upper
Relevant activities |  |  |  | Overburden / Interburden Waste Dump Tops
Total rehabilitation area size (ha) |  |  |  | 170.079
Commencement of first milestone: RM2 |  |  |  | 2033-01-01
PMLU |  |  |  | Native Bushland
Date area is available | 2031-12-10 | 2036-12-10 | 2042-12-10 | 2047-12-10
Cumulative area available (ha) | 39.868 | 70.251 | 135.541 | 170.079
Milestone completed by | 2036-12-10 | 2041-12-10 | 2047-12-10 | 2051-12-10 | 2056-12-10 | 2061-12-10 | 2067-12-10 | 2071-12-10
Milestone Reference | 2036-12-10: Cumulative area achieved (ha)
RM2 | 39.868 | 70.251 | 135.541 | 170.079 | 170.079 | 170.079 | 170.079 | 170.079
RM4 | 39.868 | 70.251 | 135.541 | 170.079 | 170.079 | 170.079 | 170.079 | 170.079
RM6 | 39.868 | 70.251 | 135.541 | 170.079 | 170.079 | 170.079 | 170.079 | 170.079
RM8 | 2056-12-10: 40; 2061-12-10: 70; 2067-12-10: 136; 2071-12-10: 170
RM10 | 2056-12-10: 40; 2061-12-10: 70; 2067-12-10: 136; 2071-12-10: 170
RM11 |  |  | 70 | 70 | 170 | 170 | 170 | 170
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2-Elevated Dumps Slopes
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2 - Elevated Landform - Overburden Dumps - Slopes
Relevant activities |  |  |  | Overburden / Interburden Waste Dump Slopes
Total rehabilitation area size (ha) |  |  |  | 804.831
Commencement of first milestone: RM2 |  |  |  | 2030-01-01
PMLU |  |  |  | Native Bushland
Date area is available | 2028-12-10 | 2029-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2037-12-10 | 2038-12-10 | 2040-12-10 | 2043-12-10 | 2049-12-10 | 2050-12-10 | 2051-12-10
Cumulative area available (ha) | 33.869 | 78.697 | 129.407 | 191.451 | 350.348 | 426.111 | 440.451 | 475.637 | 498.409 | 518.711 | 542.959 | 578.232 | 719.573 | 752.266 | 804.924
Milestone completed by | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2039-12-10 | 2040-12-10 | 2042-12-10 | 2043-12-10 | 2045-12-10 | 2048-12-10 | 2054-12-10 | 2055-12-10 | 2056-12-10 | 2065-12-10 | 2076-12-10
Milestone Reference | 2033-12-10: Cumulative area achieved (ha)
RM2 | 33.869 | 78.697 | 129.407 | 191.451 | 350.348 | 426.111 | 440.451 | 475.637 | 498.409 | 518.711 | 542.959 | 578.232 | 719.573 | 752.266 | 804.831 | 804.831 | 804.831
RM4 | 33.869 | 78.697 | 129.407 | 191.451 | 350.348 | 426.111 | 440.451 | 475.637 | 498.409 | 518.711 | 542.959 | 578.232 | 719.573 | 752.266 | 804.831 | 804.831 | 804.831
RM6 | 33.869 | 78.697 | 129.407 | 191.451 | 350.348 | 426.111 | 440.451 | 475.637 | 498.409 | 518.711 | 542.959 | 578.232 | 719.573 | 752.266 | 804.831 | 804.831 | 804.831
RM8 | 2065-12-10: 543; 2076-12-10: 805
RM10 | 2065-12-10: 543; 2076-12-10: 805
RM11 | 2045-12-10: 543; 2048-12-10: 543; 2054-12-10: 543; 2055-12-10: 543; 2056-12-10: 805; 2065-12-10: 805; 2076-12-10: 805
1) Insert new columns to the yellow table to include further rehabilitation milestone dates. | bar: 2033-12-10 to 2043-12-10
2) Insert new columns to the blue table to match rehabilitation milestone dates. | bar: 2033-12-10 to 2043-12-10
3) Insert new rows to the blue table to include additional rehabilitation milestone references. | bar: 2033-12-10 to 2043-12-10
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1). | bar: 2033-12-10 to 2043-12-10
| 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## RA3-Backfilled Pits
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3 - Backfilled Pits - Overburden Dumps
Relevant activities |  |  |  | Overburden / Interburden Waste Dumps within Mined Pit Shell
Total rehabilitation area size (ha) |  |  |  | 291.1
Commencement of first milestone: RM2 |  |  |  | 2033-01-01
PMLU |  |  |  | Native Bushland
Date area is available | 2031-12-10 | 2032-12-10 | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2041-12-10 | 2049-12-10
Cumulative area available (ha) | 10.12 | 43.061 | 63.195 | 85.529 | 112.102 | 146.72 | 291.1
Milestone completed by | 2036-12-10 | 2037-12-10 | 2039-12-10 | 2040-12-10 | 2041-12-10 | 2046-12-10 | 2054-12-10 | 2056-12-10 | 2061-12-10 | 2074-12-10
Milestone Reference | 2036-12-10: Cumulative area achieved (ha)
RM2 | 10.12 | 43.061 | 63.195 | 85.529 | 112.102 | 146.72 | 291.1 | 291.1 | 291.1 | 291.1
RM4 | 10.12 | 43.061 | 63.195 | 85.529 | 112.102 | 146.72 | 291.1 | 291.1 | 291.1 | 291.1
RM6 | 10.12 | 43.061 | 63.195 | 85.529 | 112.102 | 146.72 | 291.1 | 291.1 | 291.1 | 291.1
RM8 | 2061-12-10: 112; 2074-12-10: 291.1
RM10 | 2061-12-10: 112; 2074-12-10: 291.1
RM11 | 2046-12-10: 112; 2054-12-10: 112; 2056-12-10: 291; 2061-12-10: 291; 2074-12-10: 291
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## RA4-Tracks_Roads
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4 - Infrastructure Areas - Access Tracks and Haul Roads
Relevant activities |  |  |  | Product Coal Haul Road and other Surface Mine Haulage and Access Roads
Total rehabilitation area size (ha) |  |  |  | 227.9
Commencement of first milestone: RM2 |  |  |  | 2050-01-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2049-12-10 | 2051-12-10 | 2052-12-10
Cumulative area available (ha) | 24.1 | 135.3 | 227.8
Milestone completed by | 2054-12-10 | 2055-12-10 | 2057-12-10 | 2064-12-10 | 2065-12-10 | 2067-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 24.1 | 135.3 | 227.9
RM2 | 24.1 | 135.3 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9
RM4 | 24.1 | 135.3 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9
RM5 | 24.1 | 135.3 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9
RM7 |  |  |  | 24 | 135 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9
RM9 |  |  |  | 24 | 135 | 227.9 | 227.9 | 227.9 | 227.9 | 227.9
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0

## RA5-ROM
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5 - Infrastructure Areas - ROM
Relevant activities |  |  |  | ROM Stockile, Hopper and Crusher/Conveyor
Total rehabilitation area size (ha) |  |  |  | 16.772
Commencement of first milestone: RM1 |  |  |  | 2051-01-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2049-12-10
Cumulative area available (ha) | 16.772
Milestone completed by | 2056-12-10 | 2066-12-11
Milestone Reference | Cumulative area achieved (ha)
RM1 | 16.772 | 16.772
RM2 | 16.772 | 16.772
RM4 | 16.772 | 16.772
RM5 | 16.772 | 16.772
RM7 |  | 16.772
RM9 |  | 16.772
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## RA6-CHPP
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6 - Infrastructure Areas - CHPP General Area
Relevant activities |  |  |  | Coal Preparation Plant
Total rehabilitation area size (ha) |  |  |  | 3.173
Commencement of first milestone: RM1 |  |  |  | 2051-01-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2049-12-10
Cumulative area available (ha) | 3.173
Milestone completed by | 2053-12-10 | 2056-12-10 | 2066-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 3.173 | 3.173 | 3.173
RM2 |  | 3.173 | 3.173
RM4 |  | 3.173 | 3.173
RM5 |  | 3.173 | 3.173
RM7 |  |  | 3.173
RM9 |  |  | 3.173
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## RA7-Mine Infrastructure Area
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7 - Infrastructure Areas - Mine Infrastructure Area
Relevant activities |  |  |  | Area associated with MIA
Total rehabilitation area size (ha) |  |  |  | 8.058
Commencement of first milestone: RM1 |  |  |  | 2051-01-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2049-12-10
Cumulative area available (ha) | 8.058
Milestone completed by | 2053-12-10 | 2056-12-10 | 2066-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 8.058 | 8.058 | 8.058
RM2 |  | 8.058 | 8.058
RM4 |  | 8.058 | 8.058
RM5 |  | 8.058 | 8.058
RM7 |  |  | 8.058
RM9 |  |  | 8.058
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## RA8-Water Management Structures
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA8 - Water Management Structures
Relevant activities |  |  |  | Dams/Drains/Levees
Total rehabilitation area size (ha) |  |  |  | 313.945
Commencement of first milestone: RM1 |  |  |  | 2049-01-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2047-12-10 | 2049-12-10 | 2051-12-10
Cumulative area available (ha) | 72.99 | 80.082 | 313.945
Milestone completed by | 2051-12-10 | 2053-12-10 | 2055-12-10 | 2056-12-10 | 2057-12-10 | 1967-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 72.99 | 80.082 | 314 | 314 | 314 | 314
RM2 |  |  | 73 | 80 | 314 | 314
RM4 |  |  | 73 | 80 | 314 | 314
RM5 |  |  | 73 | 80 | 314 | 314
RM7 | [5 empty] | 314
RM9 | [5 empty] | 314
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0

## RA9-Codisposal Upper
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA9 - Elevated Landform Co-disposal - Upper
Relevant activities |  |  |  | Co-disposal Turkey's Nest Dam Site
Total rehabilitation area size (ha) |  |  |  | 31.1
Commencement of first milestone: RM1 |  |  |  | 2051-01-01
PMLU |  |  |  | Native Bushland
Date area is available | 2049-12-10
Cumulative area available (ha) | 31.1
Milestone completed by | 2053-12-10 | 2056-12-10 | 2076-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 31.1 | 31.1 | 31.1
RM2 |  | 31.1 | 31.1
RM3 |  | 31.1 | 31.1
RM4 |  | 31.1 | 31.1
RM6 |  | 31.1 | 31.1
RM8 |  |  | 31.1
RM10 |  |  | 31.1
RM11 |  | 31 | 31
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## RA10-Codisposal Slopes
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA10 - Elevated Landform Co-disposal - Slopes
Relevant activities |  |  |  | Co-disposal Turkey's Nest Dam Site
Total rehabilitation area size (ha) |  |  |  | 34.2
Commencement of first milestone: RM1 |  |  |  | 2051-01-01
PMLU |  |  |  | Native Bushland
Date area is available | 2049-12-10
Cumulative area available (ha) | 34.2
Milestone completed by | 2053-12-10 | 2056-12-10 | 2076-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 34.2 | 34.2 | 34.2
RM2 |  | 34.2 | 34.2
RM3 |  | 34.2 | 34.2
RM4 |  | 34.2 | 34.2
RM6 |  | 34.2 | 34.2
RM8 |  |  | 34.2
RM10 |  |  | 34.2
RM11 |  | 34.2 | 34.2
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).
| 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## IA1-Final Void inc Ramps
Non-use management area (NUMA)
Improvement area |  |  |  | IA1 - Residual Voids including Ramps
Relevant activities |  |  |  | Final Void and Ramps into Void
Total size (ha) |  |  |  | 171.6
Commencement of first milestone: MM1 |  |  |  | 2050-01-01
NUMA |  |  |  | Non Use Management Area associated with Pit Void
Date area is available | 2048-12-10
Cumulative area available (ha) | 171.56
Milestone completed by | 2053-12-10 | 2055-12-10
Milestone Reference | Cumulative area achieved (ha)
MM1 | 171.56 | 171.56
MM2 | 171.56 | 171.56
MM3 |  | 171.56
1) Insert new columns to the yellow table to include further management milestone dates.
2) Insert new columns to the blue table to match management milestone dates.
3) Insert new rows to the blue table to include additional management milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. MM1).
| 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning & removal | a). All services disconnected. Underground services will remain buried and surface points will be sealed b). All buildings either demolished and removed or relocated off site c). Concrete slabs and footings removed or buried within overburden dump final rehabilitation areas d). Sumps or damps that do not form part of final landform as sediment control structures will be dewatered and where applicable contaminated silt will be removed for licensed disposal e). Sealed asphalt roads, car parks and hardstand areas will have the asphalt removed for reuse or burial within overburden dump final rehabilitation areas and unsealed road, car parks and hardstands will have any contamination removed for licenced disposal f). Hydrocarbon and chemical storage areas will be removed and/or remediated by on-site treatment if required g). All carbonaceous material will be collected from haul roads and disposed in the co-disposal area or buried within the overburden dump final rehabilitation areas h). The contaminated land assessment report prepared by an AQP confirms that the land is not contaminated and is suitable for any use
RM2 | Landform design, reshaping and final contouring, inclusive of drainage features | a). Stable landform and slope angles for out of pit overburden dumps areas as follows: outer batter slopes equal to or less than 5.7°and crest slope a maximum of 2.3° b) Stable landform and slope angles for Co-disposal elevated landform and ROM pads as follows: outer batter slopes equal to or less than 8° and crest slope a maximum of 2.3° c.) Stable landform and slope angles for coal stockpiles and in pit overburden backfill flat to undulating with slopes equal to or less than 4.6° crest slope a maximum of 2.3° d). Stable landform and slope angles for infrastructure areas flat to undulating with slopes equal or less than 2.3° e). Maximum vertical height of out of pit overburden dumps elevated landforms up to 50m f). Maximum vertical height of Co-disposal elevated landform and ROM pad areas up to 18m g). All major earthworks completed h). Contour drains and rock lined drop structures installed as per appropriate design criteria i). Landforms such as the Co-disposal facility have been signed-off as constructed to design
RM3 | Install cover system/cap | a). Cover installed over reject/coal stockpile surfaces (nominally 1m inert overburden)
RM4 | Surface preparation (e.g. topsoil, fertiliser, amelioration agents, mulch or woody debris) | a). Topsoil spread to an minimum depth of 150mm b). Gypsum applied at rates determined by an AQP c). Cultivation and keying of topsoil to subsoil with suitable multi-type ripper and performed parallel to slope contours d). Addition of rock and/or log cover to assist erosion resistance of eventual vegetative ground cover
RM5 | Revegetation (grazing) | a). Pasture seed applied in accordance with rehabilitation specification, i.e. seeding rate, seed composition and cultivation to incorporate seed into the uppermost layer of the growth media b). Seed mix contains a range of native and introduced grass and legume species consistent with surrounding pastural areas (as per seed mix table in PRC plan)
RM6 | Revegetation & habitat development (native bushland) | a). Native seed applied in accordance with rehabilitation specification b). Seed mix contains a suitable range of native tree, shrub and grass species to achieve brigalow and eucalyptus woodland habitat type (as per seed mix table in PRC plan)
RM7 | Achievement of surface requirements (grazing) | a). Species density and diversity achieved is consistent with the sown seed mix, reference sites and surrounding pastural areas b). 80% of the area has a vegetative groundcover >70% for areas of low rock and logs, >50% for areas of high rock and log content c). Growth medium (surface 30cm) pH >5.5 and <9.5; Conductivity <1.0dS/m and ESP<15% d). No new invasive plants and infestation density of invasive plants that were originally present or in low abundance within the area is contained or reduced and consistent with reference sites and surrounding pastoral areas e). Water control structures are either removed or free of active erosion and integrated into permanent landforms f). No severe erosion gullies and erosion rates are less than 40tonnes/ha/year g). pH and EC indicators for surface water runoff demonstrate the water quality is suitable for the receiving environment and are consistent with water quality indicators of the upstream reference site h). The NEPM assessment confirms areas are free of hazardous materials or have been rendered safe
RM8 | Achievement of surface requirements (native bushland) | a). 80% of the area achieves species density and diversity that is greater than 60% of the reference sites and surrounding areas b). 80% of the area has a vegetative groundcover >70% for areas of low rock and logs, >50% for areas of high rock and log content c). Growth medium (surface 20cm) pH >5.5 and <9.5; Conductivity <1.0dS/m and ESP<15% d). No new invasive plants and infestation density of invasive plants that were originally present or in low abundance in the area is contained or reduced e). Key invertebrate groups such as ants and soil faunal communities are re-establishing f). Bird, mammal, reptile and frog communities are becoming established in the rehabilitated sites g). Evidence of food and shelter opportunities for invertebrate and vertebrate species h). Water control structures are either removed or free of active erosion and integrated into permanent landforms i). No severe erosion gullies (<4m² in cross section) and erosion rates are less than 40tonnes/ha/year j). pH and EC indicators for surface water runoff demonstrate the water quality is suitable for the receiving environment and are consistent with water quality indicators of the upstream reference site k). The NEPM assessment confirms areas are free of hazardous materials or have been rendered safe
RM9 | Achievement of post-mining land use to stable condition (grazing) | a). Rehabilitation has been certified by an AQP to be: • structurally stable (FoS ≥ 1.5) and slopes are designed in accordance with EA criteria • erosionally stable: no severe erosion gullies (<4m² in cross section) and erosion rates are less than 40tonnes/ha/year and groundcover established and meets criteria in RM7 b). pH and EC indicators for surface water runoff demonstrate the water quality is suitable for the receiving environment and are consistent with water quality indicators of the upstream reference site c). The rehabilitated land meets Class 4 land suitability for grazing using the Guidelines for agricultural land evaluation in Queensland (2nd edn) (DSITI & DNRM, 2015).
RM10 | Achievement of post-mining land use to stable condition (native bushland) | a). Rehabilitation has been certified by an AQP to be: • structurally stable (FoS ≥ 1.5) and slopes and dump heights are designed in accordance with EA criteria • erosionally stable: no severe erosion gullies (<4m² in cross section) and erosion rates are less than 40tonnes/ha/year and groundcover established and meets criteria in RM9 b). pH and EC indicators for surface water runoff demonstrate the water quality is suitable for the receiving environment and are consistent with water quality indicators of the upstream reference site c). The established native ecosystem has a similar composition to the previous existing woodland ecological communities comprising RE 11.4.8, RE 11.4.9 and RE 11.5.3 and provides habitat opportunities for invertebrate and vertebrate species
RM11 | Install fencing or other infrastructure to support the PMLU | a). Fencing / bunding installed to exclude stock
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1 | Highwall treatment | a). Highwall crest battered back where required to achieve a stable slope angle as specified by an AQP (geotechnical engineer)
MM2 | Achievement of landform design and surface requirements / access controls | a). Highwall as mined weathered average slope angle of 1V and 0.7H (55°) and low wall as backfilled at angle of repose at 1V to 1.35H (36°) b). Abandonment safety bund setback distance is in accordance with calculated geotechnical factor of safety c). Abandonment safety bund constructed of competent rock and to geometry specified to prevent traversing by vehicles d). Residual void maximum depth of 150m e). Residual void outside of PMF f). Abandonment safety bund and ramp into voids revegetated with pasture seed
MM3 | Achievement of sufficient improvement | a). Access to highwall, low wall and ramp batter is restricted by physical barriers and fencing is erected on the outside of the abandonment safety bund to specification (nominally five strand barbed stock fencing) b). Safety signage (design in accordance with Australian Standard) is erected at specified intervals along the fence line (nominally one sign every 100m) c). Certification from an AQP that the level of final void water is significantly below the crest of the pit to avoid the risk of overtopping and causing environmental harm d). Certification from an AQP that the water quality (pH & EC) in the final void does not show a statistically significant change when compared to background data and will not cause environmental harm to the surrounding environment
MM4
MM5
MM6
MM7
MM8
MM9
MM10
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones

## Summary
 | time axis 2026-01-01 to 2088-12-31
 | time axis 2026-01-01 to 2088-12-31
Disturbance
| Pit | 2027-12-31: 65.5007; 2028-12-31: 14.7664; 2029-12-31: 52.4453; 2030-12-31: 130.1684; 2031-12-31: 35.3047; 2032-12-31: 31.0916; 2033-12-31: 25.3315; 2034-12-31: 32.6639; 2035-12-31: 29.1715; 2036-12-31: 25.2084; 2037-12-31: 24.9731; 2038-12-31: 51.9882; 2039-12-31: 63.5992; 2040-12-31: 18.9132; 2041-12-31: 29.6218; 2042-12-31: 27.9469; 2043-12-31: 35.0898; 2044-12-31: 12.7575; 2045-12-31: 1.6056
| Dump | 2027-12-31: 146.5355; 2028-12-31: 159.3292; 2029-12-31: 10.9342; 2030-12-31: 100.8777; 2031-12-31: 145.8226; 2032-12-31: 0; 2033-12-31: 22.2219; 2034-12-31: 0; 2035-12-31: 0; 2036-12-31: 0; 2037-12-31: 0; 2038-12-31: 0; 2039-12-31: 139.5312; 2040-12-31: 0; 2041-12-31: 0; 2042-12-31: 0; 2043-12-31: 0; 2044-12-31: 0; 2045-12-31: 0
| CDA | 2027-12-31: 65.2
| MIA/HR | 2027-12-31: 216.9; 2038-12-31: 43.4
| Water | 2027-12-31: 235.425; 2038-12-31: 78.475
Lookup
| Available |  | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 860.493 | 968.021 | 1139.581 | 1549.797 | 1582.49 | 1980.211 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711
| RM1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.99 | 72.99 | 156.613 | 180.713 | 525.831 | 542.603 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303 | 407.303
| RM2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
| RM3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3
| RM4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
| RM5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.1 | 208.3 | 243.303 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1180.752 | 1213.445 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31
| RM7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 338 | 449 | 477.003 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 182 | 182 | 182 | 182 | 725 | 725 | 791 | 791 | 791 | 791 | 825 | 825 | 825 | 1004.1 | 1004.1 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4
| RM9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 338 | 449 | 477.003 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 182 | 182 | 182 | 182 | 725 | 725 | 791 | 791 | 791 | 791 | 825 | 825 | 825 | 1004.1 | 1004.1 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4
| MM1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
| MM2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
| MM3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
Max Cumulative
| RM1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72.99 | 72.99 | 156.613 | 180.713 | 525.831 | 542.603 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203 | 635.203
| RM2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
| RM3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3 | 65.3
| RM4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
| RM5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.1 | 208.3 | 243.303 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1180.752 | 1213.445 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31 | 1331.31
| RM7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 338 | 449 | 477.003 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 182 | 182 | 182 | 182 | 725 | 725 | 791 | 791 | 791 | 791 | 825 | 825 | 825 | 1004.1 | 1004.1 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4
| RM9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 314 | 314 | 314 | 314 | 314 | 314 | 338 | 449 | 477.003 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903 | 569.903
| RM10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 182 | 182 | 182 | 182 | 725 | 725 | 791 | 791 | 791 | 791 | 825 | 825 | 825 | 1004.1 | 1004.1 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4 | 1331.4
| MM1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
| MM2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
| MM3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
Cumulative Status
Disturbed |  |  | 0 | 729.5612 | 903.6568 | 967.0363 | 1198.0824 | 1379.2096 | 1410.3012 | 1457.8546 | 1490.5185 | 1519.6901 | 1544.8985 | 1569.8716 | 1743.7348 | 1946.8653 | 1965.7784 | 1995.4002 | 2023.3471 | 2058.4369 | 2071.1944 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8 | 2072.8
Available |  |  | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 860.493 | 968.021 | 1139.581 | 1549.797 | 1582.49 | 1980.211 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711 | 2072.711
Regrade |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
Topsoil |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
Reveg |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 895.031 | 1204.852 | 1421.745 | 1574.613 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213 | 1901.213
Void |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56 | 171.56
Certified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 211.56 | 525.56 | 525.56 | 525.56 | 525.56 | 667.56 | 667.56 | 667.56 | 691.56 | 1345.56 | 1373.563 | 1532.463 | 1532.463 | 1532.463 | 1532.463 | 1566.463 | 1566.463 | 1566.463 | 1745.563 | 1745.563 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863
Summary Status
Disturbed |  |  | 0 | 729.5612 | 903.6568 | 967.0363 | 1198.0824 | 1379.2096 | 1410.3012 | 1423.9856 | 1411.8215 | 1390.2831 | 1303.4595 | 1136.5946 | 1234.6948 | 1403.3513 | 1364.7444 | 1337.4102 | 1342.5851 | 1357.3729 | 1370.1304 | 1347.488 | 1312.87 | 1247.58 | 1212.307 | 1212.307 | 1212.307 | 1177.769 | 1177.769 | 1006.209 | 696.388 | 479.495 | 326.627 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027 | 0.027
Available |  |  | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 475.171 | 464.817 | 471.627 | 416.551 | 247.485 | 192.024 | 157.55 | 124.278 | 101.94 | 144.458 | 159.429 | 159.429 | 135.181 | 100.563 | 142.801 | 279.088 | 689.304 | 721.997 | 1085.18 | 1177.68 | 1006.12 | 696.299 | 479.406 | 326.538 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062 | -0.062
Regraded |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Topsoiled |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reveg |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 78.697 | 129.407 | 241.439 | 433.277 | 509.04 | 543.514 | 601.034 | 657.99 | 680.762 | 701.064 | 701.064 | 725.312 | 759.93 | 825.22 | 860.493 | 860.493 | 860.493 | 895.031 | 895.031 | 1066.591 | 1376.412 | 1421.745 | 1534.613 | 1547.213 | 1547.213 | 1547.213 | 1547.213 | 1405.213 | 1405.213 | 1405.213 | 1381.213 | 727.213 | 699.21 | 540.31 | 540.31 | 540.31 | 540.31 | 506.31 | 506.31 | 506.31 | 327.21 | 327.21 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09 | -0.09
Certified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 211.56 | 525.56 | 525.56 | 525.56 | 525.56 | 667.56 | 667.56 | 667.56 | 691.56 | 1345.56 | 1373.563 | 1532.463 | 1532.463 | 1532.463 | 1532.463 | 1566.463 | 1566.463 | 1566.463 | 1745.563 | 1745.563 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863 | 2072.863
Annual Completed
Disturbed |  |  | 0 | 729.5612 | 174.0956 | 63.3795 | 231.046 | 181.1273 | 31.0916 | 47.5534 | 32.6639 | 29.1715 | 25.2084 | 24.9731 | 173.8632 | 203.1304 | 18.9132 | 29.6218 | 27.9469 | 35.0898 | 12.7575 | 1.6056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Regraded |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 44.828 | 50.71 | 112.032 | 191.838 | 75.763 | 34.474 | 57.52 | 56.956 | 22.772 | 20.302 | 0 | 24.248 | 34.618 | 65.29 | 35.273 | 0 | 0 | 34.538 | 0 | 0 | 309.821 | 216.893 | 152.868 | 326.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Topsoiled |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 44.828 | 50.71 | 112.032 | 191.838 | 75.763 | 34.474 | 57.52 | 56.956 | 22.772 | 20.302 | 0 | 24.248 | 34.618 | 65.29 | 35.273 | 0 | 0 | 34.538 | 0 | 0 | 309.821 | 216.893 | 152.868 | 326.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reveg |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.869 | 44.828 | 50.71 | 112.032 | 191.838 | 75.763 | 34.474 | 57.52 | 56.956 | 22.772 | 20.302 | 0 | 24.248 | 34.618 | 65.29 | 35.273 | 0 | 0 | 34.538 | 0 | 0 | 309.821 | 216.893 | 152.868 | 326.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Certified |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 171.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0