## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | North Pit, South Pit, WRD Sediment Dam
Total rehabilitation area size (ha) |  |  |  | 19.5
Commencement of first milestone: RM1 |  |  |  | 2024-06-01
PMLU |  |  |  | Water Storage
Date area is available | 2022-12-10 | 2030-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 19.5 | 19.5
Milestone completed by | 2030-12-10 | 2035-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 19.5
RM3 | 19.5
RM4 | 19.5
RM7 | 19.5
RM11 |  | 19.5
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Waste Rock Dump
Total rehabilitation area size (ha) |  |  |  | 23.4
Commencement of first milestone: RM1 |  |  |  | 2024-06-01
PMLU |  |  |  | Native Ecosystem
Date area is available | 2022-12-10 | 2030-12-10 | 2035-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 23.4 | 23.4 | 23.4
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 23.4
RM14 | 23.4
RM3 | 23.4
RM4 | 23.4
RM5 | 23.4
RM8 |  | 23.4
RM12 |  |  | 23.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Ancillary Infrastructure, ROM, Roads, Exploration, Abandonment Bund
Total rehabilitation area size (ha) |  |  |  | 18.4
Commencement of first milestone: RM1 |  |  |  | 2024-06-01
PMLU |  |  |  | Low Intensity Grazing
Date area is available | 2022-12-10 | 2030-12-10 | 2035-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 18.4 | 18.4 | 18.4
Milestone completed by | 2030-12-10 | 2035-12-10 | 2040-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 18.4
RM2 | 18.4
RM3 | 18.4
RM4 | 18.4
RM6 | 18.4
RM9 |  | 18.4
RM13 |  |  | 18.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Water infrastructure (retain NP Crk Diversion and Levee, Diversion Northeast of NP, Diversion east of WRD Sediment Dam. Decommission all other diversions)
Total rehabilitation area size (ha) |  |  |  | 1.4
Commencement of first milestone: RM1 |  |  |  | 2024-06-01
PMLU |  |  |  | Water Management Infrastructure
Date area is available | 2022-12-10 | 2030-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.4 | 1.4
Milestone completed by | 1930-12-10 | 2035-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 1.4
RM3 | 1.4
RM6 | 1.4
RM10 |  | 1.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure Decommissioning | 1. All services disconnected to redundant infrastructure 2. All road materials (bitumen, gravel) removed (ripped and revegetated) where not to be retained 3. All pipelines drained and removed unless otherwise agreed with landowner 4. All fencing that is not part of the PMLU removed 5. All buildings are demolished and removed 6. Any remaining infrastructure to be transferred to landholder through signed Landholder Agreement 7. All machinery and equipment removed 8. All surface water drainage infrastructure not required in the PMLU has been removed (Where drains or bunding are not required for flood and/or erosion protection they will be levelled or used as fill) 9. All diversions and levees not to be retained are removed 10. All waste material to be removed and disposed of 11. Demonstrate areas which contained ancillary infrastructure does not contaminate receiving waters or surface waters
RM2 | Remediation of contaminated land | 1. All contamination is remediated or removed from site 2. ROM pad excavated to 0.5m (or refusal) and benign surface recontoured 3. Any contamination removed from site has been removed in accordance with relevant regulations 4. A contaminated land investigation document has been prepared by an SQP containing a site suitability statement that states that land is not contaminated and is suitable for the proposed PMLU
RM3 | Landform Development and Reshaping/Reprofiling | 1. All major earthworks completed 2. All erosion and sediment control systems have been installed 3. Bunds and check dams installed across contours 4. Exposed surfaces ripped to prevent erosion 5. The final landform surveyed and certified by a suitably qualified person as per the construction designs
RM4 | Surface Preparation | 1. For revegetated areas, growth media has been applied and spread (to a depth up to 150 mm) 2. An assessment of the placed growth media health and suitability completed by an appropriately qualified person to confirm soil is suitable for target vegetation establishment 3. Any fertilisers/ameliorants recommended as a result of the soil assessment have been applied at the rate recommended by the appropriately qualified person 4. Ripping and/or surface contouring (up to depth of 300mm - depending on compaction of soil) has been undertaken (tyne spacing varies depending on slope) where necessary
RM5 | Revegetation (Native ecosystem) | 1. Seeding has been completed with recommended seeding mix outlined in PRCP at a rate of 1-5kg/ha 2. Measured indices at rehabilitated sites for Native Ecosystems within a 50x5m plot: a) Tree stem count - average of at least 2.5 b) Shrub stem count - average of at least 20 c) At least three of the following tree and shrub species present: Terminalia aridicol, Tephrosia sp., Clerodendrum sp. Indigofera pratensis, Eucalyptus leucipholia, Acacia phlebocarpa, Acacia melleodora; Gossypium australe, Cajanus sp., Grevillea wickhamii d) Percentage groundcover - average of at least 18% flora cover e) At least three of the following Ground cover species present: Triodia pungens, Eriachne mucronate, Enneapogon oblongus, Abultion sp., Glycine sp., Cenchrus ciliaris, Heteropogon contortus, Cymbopogon bombycinus.
RM6 | Revegetation (Water management infrastructure / Low intensity grazing) | 1. Seeding has been completed with recommended species mix (as per PRCP) at a rate of 1-5kg/ha 2. Measured indices at rehabilitated sites for Low Intensity Grazing within a 50x5m plot: a) Tree stem count - average of at least 2.0 b) Shrub stem count - average of at least 22 c) At least three of the following tree and shrub species present: Terminalia aridicol, Tephrosia sp., Clerodendrum sp. Indigofera pratensis, Eucalyptus leucipholia, Acacia phlebocarpa, Acacia melleodora; Gossypium australe, Cajanus sp., Grevillea wickhamii d) Percentage groundcover - average of at least 18% flora cover e) At least three of the following Ground cover species present: Mnesitha farmmosa, Aristida lygrometrica, Triodia pungens, Eriachne sp., Themeda triandra, Acacia phlebocarpa.
RM7 | Achievement of surface requirements (Water storage) | 1. The voids have been certified as geotechnically stable by a suitably qualified person 2. RPEQ inspection of regulated structure (until de-registered) 3. Residual Voids have restricted access by means of: a) Fence and abandonment bund unless existing topographical barriers exist b) Appropriate signage 4. Voids / Water Storage remaining to be transferred to landholder through signed Landholder Agreement
RM8 | Achievement of surface requirements (Native ecosystem) | 1. Measured indices at rehabilitated sites for Native Ecosystems within a 50x5m plot: a) At least three of the tree and shrub species, and three of the ground cover species listed in RM5 are present b) Tree height - average of at least 4.2m c) Tree canopy cover - average of at least 12% d) Tree stem count - average of at least 2.5 e) Shrub canopy cover - average of at least 12% f) Percentage groundcover - average of at least 18% flora cover g) Fauna habitat features score ratings (as per landscape function analysis method) - fallen Logs 0.5, Hollows 0.5, Stones 1, Boulders 1, Large Boulders 0.5, Rock Crevices 1 h) Evidence that fauna is not compromising the integrity of the cover system when assessed by a suitably qualified person 2. Erosion - Where there are erosion features on a landform, they must not prevent reinstatement of the nominated post mining land use. No active gullies > 1 m deep observed during rehabilitation monitoring 3. Safe to humans and wildlife - Safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use.
RM9 | Achievement of surface requirements (Low intensity grazing) | 1. Exploration disturbances are capped, backfilled and grouted (if required) and disturbance areas are scarified for revegetation 2. Measured indices at rehabilitated sites for Low Intensity Grazing within a 50x5m plot: a) At least three of the tree and shrub species, and three of the ground cover species listed in RM6 are present b) Tree height - average of at least 4.2m c) Tree canopy cover - average of at least 10% d) Shrub canopy cover - average of at least 10% e) Tree stem count - average of at least 2.2 f) Shrub stem count - average of at least 21.7 g) Percentage groundcover - 25% flora cover h) Fauna habitat features score ratings (as per landscape function analysis method) - Fallen Logs 0, Hollows 0.5, Stones 1, Boulders 1, Large Boulders 0, Rock Crevices 1. i) Erosion - Where there are erosion features on a landform, they must not prevent reinstatement of the low intensity grazing PMLU. No active gullies > 1 m deep observed during rehabilitation monitoring j) Absence of seepage expressing at the surface k) Safe to humans and wildlife - Safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use l) Stable - rehabilitation is geotechnically stable (factor of safety ≥1.5)
RM10 | Achievement of post mining land use (Water management infrastructure) | 1. A suitably qualified person certifies that the leveees and diversions retained convey a peak flow for a 1:1,000 year annual exceedance probability rainfall event 2. Certified as conforming with design documents and functioning as designed when assessed by a suitably qualified person 3. Certification from an suitably qualified person that the area has achieved a safe and stable condition with no signs of active erosion >30 cm wide or deep 4. Geomorphology of the receiving environment has not been altered when assessed by a suitably qualified person 5. Certification by a suitably qualified professional that a stable low intensity grazing PMLU has been achieved
RM11 | Achievement of post mining land use (Water storage) | 1. Sediment and erosion control structures removed once disturbed areas are stabilised 2. Void water quality is no greater than ANZECC stock water quality trigger values for pH (5-9), Sulfate (2000mg/L), As 0.5mg/L, Cd 0.01 mg/L, Cu 1 mg/L Pb 0.1 mg/L and Zn 20 mg/L, Total Dissolved Solids 5,000 mg/L, Sodium 200 mg/L, Chloride 250 mg/L, Nitrate 100 mg/L, Nitrite 3 mg/L, Ammonia 10 mg/L, Total Hardness 1,000 mg/L as CaCO3, Calcium 500 mg/L, Magnesium 150 mg/L, Copper 0.1 mg/L, Zinc 5 mg/L, Iron 10 mg/L, Manganese 1 mg/L, Fluoride 2 mg/L 3. Groundwater levels surrounding pits are within standing water levels of between 8 - 22 m BGL 4. Signed landholder agreement for transfer of ownership for water storages 5. Certification from an appropriately qualified person that the water storages have achieved a safe and stable condition suitable for use as water storages 6. Voids can be demonstrated by a suitably qualified person as acting as groundwater sinks
RM12 | Achievement of post mining land use (Native ecosystem) | 1. Sediment and erosion control structures removed once disturbed areas are stabilised 2. Erosion assessment of final landform: no subsidence or significant (>1m deep) erosion gullies for at least three (3) years); drainage follows intended and appropriate drainage paths 3. Certification from an appropriately qualified person the WRD cover system is performing as required to achieve a non-polluting landform based on installed infiltration / seepage monitors 4. Future preferred cover SVFlux water balance performance criteria for wet, dry and average year rainfall is: Dry year: Rainfall 117.2 mm, Stored infiltration 15%, Seepage 0%, Actual evaporation 85%, Runoff 0% Average year: Rainfall 463.4 mm, Stored infiltration 11%, Seepage 2%, Actual evaporation 87%, Runoff 2% Wet year: Rainfall 1,198.0 mm, Stored infiltration 9%, Seepage 6%, Actual evaporation 75%, Runoff 10% 5. Vegetation communities demonstrate sustainability through the presence of flowers, fruits, seeds, and/or juvenile species as listed in RM5 6. Certification by a suitably qualified professional that weeds and pest species are in densities no greater than at analogue sites 7. Maintenance requirements for rehabilitated land is no greater than that required for the land prior to its disturbance 8. Surface water quality meets ANZECC stock water (beef cattle) values for pH (5-9), Sulfate (2000mg/L), As 0.5mg/L, Cd 0.01 mg/L, Cu 1 mg/L Pb 0.1 mg/L and Zn 20 mg/L 9. Groundwater quality is comparable with pre-mining water quality and meets ANZECC stock water (beef cattle) values for pH (5-9), Sulfate (2000mg/L), As 0.5mg/L, Cd 0.01 mg/L, Cu 1 mg/L Pb 0.1 mg/L and Zn 20 mg/L, Total Dissolved Solids 6,000 mg/L, Sodium 200 mg/L, Chloride 250 mg/L, Nitrate 100 mg/L, Nitrite 3 mg/L, Ammonia 10 mg/L, Total Hardness 1,000 mg/L as CaCO3, Calcium 500 mg/L, Magnesium 150 mg/L, Copper 0.1 mg/L, Zinc 5 mg/L, Iron 10 mg/L, Manganese 1 mg/L, Fluoride 2 mg/L. 10. Rehabilitated landforms have achieved a factor of safety (≥1.5) 11. Rehabilitated landforms have achieved a stable condition when assessed by a suitably qualified person, including consideration of: a) Compliance with design requirements b) Differential settlement or oxidation of material has not resulted c) Absence of salt rise d) Concentration of surface water flow e) All infrastructure to remain is fit for purpose (including culverts) 12. Certification by a suitably qualified professional that a stable native ecosystem PMLU has been achieved
RM13 | Achievement of post mining land use (Low intensity grazing) | 1. Sediment and erosion control structures removed once disturbed areas are stabilised 2. Erosion assessment of final landform: no subsidence or significant (>1m deep) erosion gullies for at least three (3) years); drainage follows intended and appropriate drainage paths 3. Vegetation communities demonstrate sustainability through the presence of flowers, fruits, seeds, and/or juvenile species as listed in RM6 4. Weed species are in no greater number (ground cover and/or number of individuals) than are present in analogue sites 5. Maintenance requirements for rehabilitated land is no greater than that required for the land prior to its disturbance 6. Surface water quality meets ANZECC stock water (beef cattle) trigger values for pH (5-9), Sulfate (2000mg/L), As 0.5mg/L, Cd 0.01 mg/L, Cu 1 mg/L Pb 0.1 mg/L and Zn 20 mg/L 7. Groundwater quality is comparable with pre-mining water quality and meets ANZECC stock water (beef cattle) trigger values for pH (5-9), Sulfate (2000mg/L), As 0.5mg/L, Cd 0.01 mg/L, Cu 1 mg/L Pb 0.1 mg/L and Zn 20 mg/L, Total Dissolved Solids 5,000 mg/L, Sodium 200 mg/L, Chloride 250 mg/L, Nitrate 100 mg/L, Nitrite 3 mg/L, Ammonia 10 mg/L, Total Hardness 1,000 mg/L as CaCO3, Calcium 500 mg/L, Magnesium 150 mg/L, Copper 0.1 mg/L, Zinc 5 mg/L, Iron 10 mg/L, Manganese 1 mg/L, Fluoride 2 mg/L 8. Certification by a suitably qualified professional that a stable low intensity grazing PMLU has been achieved 9. Certification by a suitably qualified professional that weeds and pest species are in densities no greater than at analogue sites.
RM14 | Installation of cover system/cap | 1. Reprofile of WRD batter slopes to prevent erosion, to <36 degrees to the angle of repose 2. Water shedding cover system and monitoring infrastructure (such as volumetric water content (VWC), matric suction sensor, or similar) have been installed 3. WRD is capped and rock mulch is applied 4. Representative sampling of capping material demonstrates absence or negligible levels of PAF or other contaminated material as assessed by suitably qualified person 5. Stable landform of ≥1.5 factor of safety and angle of <25% for final landform design (WRD) assessed by a suitably qualified person 6. Groundwater monitoring program confirms cap is functioning as designed and there is no migration of contaminants.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabiitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones